## MALAPPURAM
MALAPPURAM BUDGET 2016-2017
Head of Account : 4059þ01þ051þ96þLand Revenue
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of a building for village office, Pulamanthole | 61/6 | Order no .LRM2-20829/07 dtd 03/11/2010 | 13.2 | DR-5/2010-11 Dated 11-02-2011 | 13.2 | 25/02/2011 | 2011-05-04 | 2011-08-19 | 2012-04-18 | work completed |  | 1120824
2 | Construction of a building for village office and Revenue Inspector office at Manjeri | 62/6 | Order no .LRM2-45770/08 dtd 12/05/2010 | 9.4 | DR-4/2010-11 Dated 12-08-2010 | 9.4 | 18/08/2010 | 2011-05-04 |  | 6 Month | work completed |  | 1018745
Head of Account : 4059þ01þ051þ95þREGISTRATION
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Kondotty. Construction of Building for Sub-Registrar Office, Kondotty | 15/9498 | G.O. (Rt) No. 1047/09/PWD dtd. 14.7.09 for Rs.49 lakhs | 49 Lakhs | CR 16/2009-2010 of SE, PWD (B&LW) Kozhikode Rs.22Lakhs | 22 lakhs |  | SE(K) 22/2009-2010 dtd. 07.12.2009 | 2009-12-07 | 30/09/2010 | work completed |  | 1944646
2 | Perinthalmanna: Construction of Building for Sub Registrar Office | 16/9 | GO(Rt) No.227/2013/T.D Dtd.TVM 15/03/2013 | 50 Lakhs | DR 28/2043-15 dt 30/08/2014 for Rs 50 Lakhs | 5000000 |  | EE(BM)16/2015-16 dtd.16.07.2015 | 24/07/2015 | 2016-07-01 | The work was included in LAC-ADS and work completed. |  | 3071256
Head of Account : 4059-01-051-90- TREASURY
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Constructin of a building for Sub Treasury Tirur | 9/13 | [8 empty] | work transferred to INKEL
2 | Constructin of a building for Sub Treasury Kottakkal | [9 empty] | work transferred to INKEL
Head of Account : 4059-60-051-98-JUDICIARY
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of a building for Judicial first class magistrate Court | 32/43 | [8 empty] | CJM court is included in the court complex building which is under construction
2 | Construction of a building for court complex, Tirur | 33/43 | G.O(Rt)No.1046/09/PWD/TVM Dated | 237 Lakhs | 83/CE/BL 2009-10 dt 07/11/2009 | 190 Lakhs |  | 3/SEJ/EKM/09-10 dtd:17.07.2010 | 24.08.2011 |  | work completed |  | 16939333
3 | Construction of Court complex Nilambur | 34/43 | [8 empty] | land not yet finalised
4 | Perinthalmanna. Construction of Court complex Perinthalmanna. | 35/43 | G.O(Rt)No.565/2012/PWD/TVM Dated 31.03.2012 Rs 930 Lakhs | 930 Lakhs | 95/CE/BL 2012- 2013 dt 30/03/2013 for 1000 Lakhs | 1000 Lakhs | 06.09.2013 | .23.05.2014 | 30.05.2014 | 28.03.2017 | work completed |  | 57141762
5 | Construction of building for Family court Malappuram | 37/43 | [8 empty] | Architectural drawing to be obtained
Head of Account : 4059-60-051-86-PWD WORKS
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of a building for B3 Block at civil station , Malappuram | 73/23 |  |  | 63/CE/B&LW/2003-04 dated 21/01/2004 | 340 Lakhs | 24/03/04 | 14/01/2005 |  | 24 Month | work completed |  | 36327579
2 | Construction of a building for Mini Civil Station, Kuttippuram | 74/23 | GO (Rt) No.763/08/PWD dtd. 27.05.08 | 200 Lakhs | 105/CE/B&LW/2008-09 dated | 200 Lakhs | 30/04/2009 | 15/12/2009 | 2009-08-14 | 2011-01-03 | work completed |  | 20351822
| Construction of a building forThirunnavaya, Krishi Bhavan | 75/24 | [8 empty] | Estimate now in other Department
| Construction of a building for Mini Civil Station,Wandoor | 76/24 | [8 empty] | Land not available
| Renovation of RDO Office, Perinthalmanna | 77/24 |  |  |  |  | 2013-07-30 | 2013-10-07 | 2013-10-30 | 2014-07-31 | work completed
| Construction of a building for Fire Station Tirur | 78/24 | GO (Rt) No. 1184/2009 PWD dtd 14-08-2009 | 178Lakhs | 54 CE / B&LW/10-11 DT 12-07-2010 | 178Lakhs |  | 16-11-2011 | 0 | 9 month | work completed |  | 25860430
7 | Kondotty. Construction Rest house,Kondoty. | 79/24 | GO (Rt) No.1187/09/PWD dtd. 14.8.09 for Rs.59 lakhs | 59 Lakhs | 189/CE/B&LW/2009-2010 dated 19.03.2010 Rs.62Lakhs | 62 Lakhs |  | SE(K) 4/2010-2011 dated 07.05.2010 | 13.03.2011 |  | work completed |  | 5264484
| Construction of a building for Nannamukku polytechnic | 80/24 | GO (Rt) No.1046/09/PWD dtd. 14.7.09 for Rs.250 lakhs | 250 Lakhs | [6 empty] | Work canceled
| Construction of classrooms for +2 at Cheriyamundam GHS | 81/24 | GO (Rt) No.1048/09/PWD dtd. 14.7.09 of PWD (G) Dept for Rs.125 lakhs | 125 Lakhs | 123/CE/B&LW/09-10 dtd 31.12.2009 of the CE, Bldgs, TVm for Rs.14.35 Lakhs | 14.35 Lakhs |  | SE(K)15/2010-11 dtd.30.06.2010 | 04.07.2011 |  | civil & electrical work completed |  | 18536837
| Construction of new block for Kalpakanchery GHS | 82/24 | GO (Rt) No.1184/09/PWD dtd. 14.8.09 of or Rs.150 lakhs | 150 Lakhs | 121/CE/B&LW/09-10 dtd 31.12.2009 of the CE, Bldgs, TVm for Rs.150 Lakhs | 150 Lakhs |  | SE(K)8/2010-11 dtd.29.05.2010 | 04.06.2011 |  | work completed |  | 9717495
| Construction of new block for Kuttippuram GHS | 83/24 | GO (Rt)No.1184/2009/PWD dtd 14-8-2009 | 205 Lakhs | 10/CE/B&LW/2010-11 dtd20-04-10 | 205 Lakhs |  | SE(K) 63/2010-11 dtd 10-3-2011 | 21.06.2010 | 20.12.2011 | work completed |  | 25142107
| Kondotty. Construction of Building for Sub-Registrar Office, Kondotty | 84/24 | G.O. (Rt) No. 1047/09/PWD dtd. 14.7.09 for Rs.49 lakhs | 49 Lakhs | CR 16/2009-2010 of SE, PWD (B&LW) Kozhikode Rs.22Lakhs | 22 Lakhs |  | SE(K) 22/2009-2010 dtd. 07.12.2009 | 06.08.2010 |  | Repetition
| Budget work - 2013-14- Construction of building for Govt.Ayurveda Dispensary at Parappur in MPM dist | 259/37 | GO(Rt) No. 1245/2014/PWDdt 02.09.2014 for Rs. 50.00Lak | 50 Lakhs | DR/57/2014-15 dt 23.01.2015 for Rs.57.50Lakh | 57.5 Lakhs | 50.00 lakhs | EE9BM) 69/2016-17 dt 03.01.2017 |  |  | Column work in progress |  | 6318595
| Construction of building for Avukkadar Kutty Naha PWD Complex at Parappanangadi | 292/41 | GO(Rt)No.1295/2015/PWD dated.Tvm.19.11.2015. |  | No.2755/2015-16 dt 21.01.2016 |  |  | SE(K) 67/2016-17 dt 24.03.2017 | 15.03.2016 | 14.09.2017 | third floor slab casted
| Construction of four storied building for Mini Civil Station Nilambur in Malappuram District- | 293/41 | G.O (RT) No. 1671/2015/pwd dated 12-11-15 | Nilambur | Reg.No.1544/2016-17 dt 14.07.2016 for Rs.15.25 Crore | 15.25 crore |  |  |  |  | compound wall work in progress
| Construction of First Floor of PWD Rest House at Kondotty in Malapuram | 294/41 | GO(Rt) No.1134/2015/PWD dated 31.07.2015 | 65 Lakhs | 2788/2015-16 dtd.22.01.2016 for 65 lakhs | 65 Lakhs | 10.06.2016 | EE(BM)54/201617 dt 15.10.2016 |  |  | structure completed
| Construction of building for PWD Rest House Parappanangadi | 295/41 | GO(Rt) No.931/2015/PWD dated 02.07.2015 | 500 lakhs | 2515/15-16 dtd: 14.01.2016 for Rs.500 Lakhs. | 500 lakhs | 05.02.2016 | SE(K)86/2015-16 dtd: 22.02.2016. | 2.03.2016 | 01.09.2017 | finishing work in progress
| Budget work 2015-16(special sanction):- Construction of building for Rest House Manjeri in Malappuram District | 296/41 | Go(Rt.)No.596/2015/PWD dated 04/05/2015 | Manjeri | ORDER No.MLPM/2015-2016/2015/3150 Dated:28-09-2015 | 300.00 lakhs |  | SE(K)93/2015-2016.DATED-03-03-2016 | 18.12.2015 | 2017-06-17 | Finishing work in progress Time of extension granted
Head of Account : 4059-60-051-86-PWD WORKS
cq] (e-£-¯nÂ)
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Kondotty. Construction Rest house,Kondoty. | 15/48 | GO (Rt) No.1187/09/PWD dtd. 14.8.09 for Rs.59 lakhs | 59 lakhs | 189/CE/B&LW/2009-2010 dated 19.03.2010 Rs.62Lakhs | 62 lakhs |  | SE(K) 4/2010-2011 dated 07.05.2010 |  | 13.03.2011 | work completed & final bill paid |  | 5264484
2 | Providing Additional Block to Rest House Kuttippuram | 16/48 | [8 empty] | Hindrance free land not available
Head of Account : 4059-60-051-85-FIRE AND RESCUE
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Tirur. Construction of new building for fire and rescue Station,Tirur | 16/50 | G.O.(Rt) No.1184/09/PWD dated 14.07.2009 for Rs.178 lakhs | 178 lakhs | 54CE/B&LW/10-11 dated 12.7.2010 for Rs.178 lakhs | 178 lakhs |  | SE (K) 30/2011-12 dtd. 16.11.11 |  | 25.08.2012 | work completed
2 | Construction of building for fire and rescue Station,Valanchery | 17/50 | [8 empty] | Land not available
3 | Budget work 2015-16 Construction of Fire and Resque station. Manjeri | 18/50 | [8 empty] | Land not handed over
Head of Account : 4202-02-103-99
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of building for THS Perinthalmanna(IHRD) | 25/340 | G.O.(Rt) No.1184/09/PWD dated 14.07.2009 for Rs.178 lakhs | 67lakh | DR 3/2014-15 dt 30/05/2014 | 67 lakhs |  | EE(BM) 48/2014-15 dtd 21-02-2015 | 2015-03-03 | 2016-01-02 | completed
3 | Construction of building for THS Manjeri | 28/340 | [8 empty] | Estimate submitted for AS
Head of Account : 4059-60-051-72
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14
klari
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of building for Police Dispensary at Klari MSP | 42/59 | GO(Rt)No.2132/2013/ Home dated Tvm 31.07.2013 | 50 lakhs | DR 78/2013-14 dated 03.10.2013 | 50 lakhs |  | EE(BM)20/2014-15 dated 26.09.2014 |  |  | Work completed |  | 5465760
2 | Tanur: Construction of Tanur Mini Civil Station Building | 43/59 | GO(Rt)No.11185/2013/PWDdt.TVM05/08/2013 for 343.5L | 343 Lakhs | 48/CE/BL/ 2013-14 dt.2/12/2013 for 343.5lakhs | 343.5 Lakhs |  | SE(K)28/2015-16,dt 31-08-2015 |  |  | Work completed
3 | Extension of Mini Civil Station, Tirurangadi | 44/59 | GO(RT)No.781/2015/PWD dated Tvm 04.06.2015 of Public Works (E) Dept. | Revenue | 1294/2015-16 DT.25-09-2015 | 10000000 |  | EE(BM)75/2015-16 DT 24-02-2016 |  |  | Work completed |  | 2924215
4 | Perinthalmanna: Construction of Civil Station(PWD Complex, Village Office etc)at Perinthalmanna | 45/59 | GO(Rt) No.713/2013/PWD. Dtd.TVM 13/05/2013 | 10000000 | DR 80/2013 14 dt 13/11/2013 | 10000000 | 2014-03-05 | EE(BM)46/2014-15 dtd.10-02-2015 | 2015-02-18 | 2016-02-17 | Work arranged through LAC ADS Work completed |  | 10325924
Head of Account : 4216-01-106-98 GOVERNMENT QUARTERS
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Renovation of Governemnt Quarters at Malappuram. | 42/75 | [8 empty] | Estimate under preparation
3 | Construction of a building for Revenue Divisional Office, Tirur | 115/80 | [8 empty] | Land not available
3 | Construction of a building for NGO quarters phase II | 21/73 | [8 empty] | work completed |  | 140.57 Lakhs
Head of Account : 4216-01-700-87 JUDICIAL OFFICERS QUARTERS
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of building for Judicial Officers Flat Type Quarters | 5./80 | [8 empty] | Estimate submitted for AS
160 | Judicial Quarters Ponnani | 13/81 | [8 empty] | Land not identified
| Rennovation of judicial quarters in Malappuram District. | 52/84 | [8 empty] | Estimate under preparation
Head of Account : 4202-01-202-93
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
77 | Construction of building for Government Vocatinal Higher Secondary School Kondotty | 15/302 | G.O. (Rt) No.241/2012/PWD dated 16.02.2012 Rs. 50Lakhs | 56 Lakhs | Reg No 177/CE/BLDS/2011-2012 DT 31.03.2012 For Rs 56 lakhs | 56 Lakhs | EE(M) 7/12-13 Dt: 14.09.2012 | Mohammed Ashraf | 22.09.2012 | 21.05.2012 | Work Completed
77 | Construction of Hall cum Cllass Room Block for Government UP School Mundothuparambu | 14/302 | GO(Rt)No.3229/2015/G.Edn. Dtd 04.08.2015 of Rs.165,00,000/- | 165 lakhs | Reg No.2774/2015-16 dated 22.01.2016 for Rs.165/- lakhs of SE KKD | 165 lakhs |  | SE(K)89/2015-2016 dated 01.03.2016 | 05.03.2016 | 04.03.2017 | finishing work in progress
Head of Account : 4202-01-202-92
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Construction of a building for Government Vocational Higher secondary school, Manjeri | 5/303 | [8 empty] | work completed |  | 3601242
Head of Account : 4202-02-103-95 PHC
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | construction of a building for PHC Angadippuram (20 Bedded) | 02/393 | [8 empty] | Land not available
2 | Edapatta: Construction of Building for PHC Edapatta | 3/392 | GO(Rt) No.13566/2013/H&FWD. Dtd.TVM 16/04/2013 | 7000000 | DR 42/2013-14 dt 12/08/2013 | 7000000 | 2013-10-29 | EE(BM) 54/13-14 dated 03.03.2014 | 2014-03-18 | 2014-10-17 | Work arranged under LAC ADF work completed | completed | 4513598
3 | Construction of New Block for PHC vazhakkadu | 6/392 | [8 empty] | work completed
4 | Elamkulam. PHC ELAMKULAM | 7/392 | G.O. (Rt) No.1767/2011/h&fwd dated tvm 06.05.2011 | 50.05Lakhs | 30/CE/BL/2012-13 Dt 19/05/2012 | 50.05Lakhs | 2012-10-17 | EE(BM)1/2013-14 dtd.23-04-2013 | 2013-05-02 | 2013-09-19 | Work arranged under NABARD Work completed |  | 6242130
5 | New building for Cherukavu PHC, Malappuram | 8/392 | GO (Rt) 1085/2014/H&FWD dt 29.03.2014 for Rs.52Lakhs | 52.00 Lakh | DR/70/2014-15 dt 30.03.2015 |  |  | EE(BM)45/2016-17 dt 06.09.2016 | 09.09.2016 | 08.07.2017 | Work started
6 | PHC MELATTUR | 20/393 | G.O. (Rt) No.1767/2011/h&fwd dated tvm 06.05.2011 | 50.51 Lakhs | 176/CE/BL/2011-12 dated31/03/2012 | 50.51 Lakhs | 2012-10-17 | EE(BM)02/2013-14 dtd 23-04-2013 | 2013-06-25 | 2014-04-30 | Work arranged under NABARD Work completed
Head of Account : 4202-02-800-95 ITI BUILDING
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Construction of a building for ITI staff quarters, nilambur | 10/364 | [8 empty] | Estimate under preparation
| Construction of a building for Gvernment ITI Puzhakkattiri | 34/365 | [8 empty] | Land not available
| Construction of a building for Gvernment ITI Maranchery | 47/366 | [8 empty] | Land not available
Head of Account : 4202-01-203-99 SECONDARY EDUCATION, SCHOOLBUILDING
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of a building for MSP Higher Secondary School, Malappuram | 8/289 | [8 empty] | work completed |  | 6666476
2 | Construction of a building for GHSS Athavanad | 22/290 | [8 empty] | work completed
3 | Construction of a building for GHSS kuttippuram (New block) | 24/290 | GO (Rt)No.1184/2009/PWD dtd 14-8-2009 | 205 Lakhs | 10/CE/B&LW/2010-11 dtd20-04-10 | 205 Lakhs |  | SE(K) 63/2010-11 dtd 10-3-2011 | 21.06.2010 | 20.12.2011 | work completed |  |  | 25142107
4 | Providing Office Room at GMLP School, paravanna | 55/272 | [8 empty] | work completed
5 | Construction of 10 Class Room building for Government UP School Koodasseri Tirur | 66/293 | GO(Rt)8/ 2013/PWD dt.TVM 21.01.2013 for70 lakhs | 70 Lakh | DR-86/2013-14 dated 31.12.2013 for 80 lakhs | 80 lakhs | 29.10.2014 | EE(BM)2/2015-16 dtd.10.4.2015 | 08.01.2015 | 07.11.2015 | work completed | work completed
6 | Construction of GUPS Klari | 67/293 | GO.(Rt)No.487/2013/PWD dated 30.03.2013 Rs.125Lakhs | 125 lakhs | CR/17/2013-14 dated 25.01.2014 for 110 lakhs | 110 lakhs |  | SE(K)15/2014 | 07.04.2014 | 06.04.2015 | work completed |  | 5465760
7 | Construction of class room for GUPS Trikkulam | 68/293 | GO.(Rt)No.487/2013/PWD dated 30.03.2013 Rs.400Lakhs | 400 lakhs | Reg.No.25/CE/Bl/2013-14 dated 09.10.2013 |  | 05.12.2014 | SE(K)27/2015-16 dtd.26.08.2015 | 01.09.2015 | 31.03.2016 | structure work for GF, FF completed and wiating for KMBR excemption.
8 | Kuzhimanna: Construction of Building for GHSS , Kuzhimanna | 111/297 | G.O (Rt.) No.1289/213/ G. Edndt 19.03.2013 | 40 lakhs | DR 31/2013-14 dated 03.08.2013. 40 lakhs | 40 lakhs |  | EE(BM)36/2015-16 dt 19.11.2015 |  |  | Structure completed
9 | Vazhakkad: Govt HSS Vazhakkad, Ground Development | 112/297 | GO(Rt)No.956/2013/ G.Edn dated 27.02.2013 | 25 Lakhs | DR/15/2013-14 dated 18.07.2013 | 25 Lakhs |  | EE(BM)34/13-14 dated 13/01/14 | 23.02.2014 | 22.10.2014 | completed |  | 5278914
10 | Construction of Building for College of Applied Science, -IHRD-Muthuvallur | 113/297 | GO(Rt0 No.1357/2013/Hedn dt 28.06.2013 for rs 30.L | Rs.30 Lakhs | DR/1045/2015-16 dt 10.09.2015 |  |  | EE(BM)53/2015-16 -Dated 30-12-2015 | 04.03.2016 | 03.11.2016 | completed
11 | Chullikode:Construction of Building for GHSS Chullikkode | 114/297 | GO(Rt)No.1286/2013/G.Edn. dated 18.03.2013 | 50Lakhs | DR/52/2013-14 dated 17.08.2013 |  |  | EE(BM)01/14-15 dated 12/05/14 | 05.10.2013 | 05.06.2014 | work completed |  | 5019057
12 | LAC - ADF Construction of Building for GHSS ,Maranchery in Malappuram District | 115/297 | GO(Rt)No.1361/201G.Edn. dtd.22.03.2013 forRs.53,00,000/- | 53 l akhs | DR-57 /2013-14 dated17.08.2013 Rs.53 Lakhs | 53 lakhs |  | EE (BM) 37/2013-14 dated 22.01.2014 |  |  | work completed |  | 4703481
13 | LAC- ADF - Construction of Higher Secondary School Building for GH School Palapetty in Malappuram District | 116/297 | GO(Rt)No.1362/2013/G. Edn.dtd.22.03.2013 for Rs.33,60,000/- | 33.6 lakhs | DR-58/2013-14 dated 17.08.2013 Rs. 33.60 Lakhs | 33.6 lakhs |  | EE (BM) 4/2014-15 dated 26.05.2014 |  |  | work completed |  | 3467828
14 | LAC - ADF Construction of Building for PCNGHSS, Mookkuthala in Malappuram District | 117/297 | GO(Rt)No.1363/2013/G.Edn. dtd.22.03.2013 for Rs.50,00,000/- | 50 lakhs | DR-56/2013-14 dated17.08.2013 Rs. 50 Lakhs | 50 lakhs |  | EE (BM) 38/2013-14 dated 22.01.2014 | 22.01.2014 | 21.09.2014 | work completed |  | 4811096
15 | Cheriyamundam: Construction of Compound Wall at GHS Cheriyamundam | 118/297 | GO(Rt) No. 11114/2013/gen.edn. dt.17/03/2013 Rs.45 lakhs | 45 Lakh | DR/29/2013-14 dt.2/8/2013 | Under 5054-80-800-67(NP)45Lakhs |  | EE(BM)12/2014-15 dtd 10.07.2014 |  |  | work completed
16 | GMUPS -Kizhissery-Kuzhimanna | 119/298 | G.O (Rt.) No.1262/2013/ G. Edn dt 16.03.2013 | 30lakhs | DR/14/13-14 dated 18.07.2013 for 25 lakhs | 25 lakhs |  | EE(BM)62/13-14 dated 25/2/14 |  |  | work completed
17 | Tirur: Construction of Building for GVHSS for Girls, Tirur | 148/300 | GO(Rt)No.954/2013/Gen/ Edn dt.27/02/2013 for 50L | 50 Lakhs | DR19/2013-14 dated 18.07.2013 | 50 Lakhs |  | EE/BM/2/2014-15 dtd.12.05.2014 |  |  | work completed |  | 38255070
18 | Construction of Building for Trikkulam GUP School Auditorium | 149/300 | GO(Rt)No.2152/2013/ Gnl/Edn.dated Tvm 23.05.2013 | 50 lakhs | DR-66/2013-14 EE, Mlpm 03.09.2013 45 lakhs | 45 Lakhs |  | EE(BM)26/2014-15 dated 18.10.2014 |  |  | work completed |  | 4350703
19 | LAC - ADF Construction of Plus Two Block at Thavannur Kelappaji GVHSS | 150/300 | AS.No.GO(Rt)No.959/013/G.Edn.dtd.27.02.2013 for Rs.125.L | 125 lakhs | CR /03/2013-14 dated 19.06.2013 of SE, Kozhikode RS.125 Lakhs | 125 lakhs |  | SE (K)44/2014-15 dated 13-02-2015 | 11.05.2014 | 10.05.2015 | work completed
Head of Account : 4202-01-203-96 COLLEGE HOSTEL BUILDING
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Tirur. Construction of staff quarters in Govt.college,Tirur. | 51/322 | GO (RT) No.1164/09 /HEDN dt 30.07.09 Rs.95 lakhs | 95 lakhs | 11/CE/B&LW/2010-11 dated 03.05.2010 Rs.103Lakhs | 103 lakhs |  | SE(K)40/10-11 dated 08.12.2010 |  |  | Completed |  | 12282363
2 | Construction of Library block at G overnemnt college,Tirur | 52/322 |  | H Edn |  | 160 Lakhs |  |  |  |  | Revised Estimate to be submitted
3 | Construction of compound wall in TMG College,Tirur | 53/322 | 978/2013/H.Edn dated 31.05.2013 (H.A/c 4202-01-203-99) | Rs.40 L | DR 92/2013-14 dtd 24.02.2014 for Rs.45 L | Rs.45 L |  | EE(M)36/14-15 dtd 08.12.2014 |  |  | work completed |  | 15434022
4 | Construction of Hostel building for girls in PTM college Perinthalmanna | 59/323 | G.O. (Rt) No.356/2013/PWD dated 14-03-2013 Rs.150Lakhs | Rs.150Lakhs | D.R./85/2013-2014 dated 21.12.2013 | Rs.150Lakhs | 2014-09-26 | EE(BM)35/2014-15 Dt.17.11.2014 | 22/1/2015 | 2016-04-21 | work completed |  | 14390428
Head of Account : 4210-01-110-90 WOMEN & CHILDREN HOSPITAL
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
148 | Construction of Women & Children hospital Manjeri | 4/384 | [8 empty] | work completed |  | 75130640
134 | Additional facilities for W&C Hospital Ponnani | 7/384 | GO.(Rt)No.1070/2013/PWD dated 25.03.2013 Rs.360 Lakhs | 360 Lakhs | Reg. No.15/CE/B2/2014-15 dt 12.08.2014 for Rs.360 Lakh | 360 lakhs | 07.08.2015 | SE(K)24/2016-17 dt 23.06.2016 | 30.06.2016 | 01.01.2018 | Retaining wall completed. super structure of compound wall in progress
BUDGET 2016-2017
Head of Account : 4403-103-98 POULTRY
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| construction of shed to poulty farm and staff quarters at Malappuram | 9/580
| construction of building for poulty farm at Athavand | 10/580 | GO(Rt)No 528/11/AD dt 14/03/2011 | 6474855 | 31/CE/BL/2011-12 Dt 30/06/2011 | 6500000 | 2011-09-26 | SE(K) 28/2011-12 dt 16/11/2011 | 2011-11-25 | 2012-08-22 | Work completed
Head of Account : 4210-02-103-99
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Ayurveda Hospital, Tirur | 01/397 |  |  | 70 Lakhs | [5 empty] | Proposed land is paddy field. Hence permission to be got from Revenue Department for conversion of land.
2 | Providing Additional Floor to Ayurveda Hospital, Valluvmbram | 2/397 | [8 empty] | Estimate to be submitted
3 | Construction of a building for Ayurveda Dispensary Cherukavu | 6/397 | [8 empty] | Estimate to be submitted
4 | Valanchery: Construction of Building for PHC Valanchery | 13/397 | GO (Rt) No.816/2013/H&FWD Dtd.TVM 12.03.2013 | 5000000 | DR 33/2013-14 dt 03/08/2013 | 5000000 | 2013-12-17 | EE(BM) 41/2014-15 Dtd.27.12.2014 |  |  | G F Slab shuttering in progress
5 | Edayoor: Construction of Building at Vadakkumpuram for PHC Edayoor | 14/397 | GO (Rt) No.1040/2013/H&FWD Dtd.TVM 25.03.2013 | 5000000 | DR 32/2013-14 dt 03/08/2013 | 5000000 | 2013-10-29 | EE(BM) 30/2014-15 Dtd.09.01.2014 | 31.01.2014 | 31.08.2014 | Civil and electrical work completed.
Head of Account : 4210-02-110-89 Homeopathy
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alamkode: Construction of Building for Alamkode Homeo Hospital | 15/402 | Health |  | 25 lakhs | [5 empty] | Land not avaiable
Head of Account : 4210-03-105-99 Nursing School
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Rennovation works to Nursing School Manjeri | 1/419 |  | 120 | [6 empty] | work completed
Head of Account : 4225-01-277-98 SC-ST Development_Pre Metric Hostel
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of building for Premetric Hostel at Thrikkalangode | 14/492 | [8 empty] | Investigation work tendered
2 | Construction of building for Premetric Hostel at Thiruvali | 15/492 | [8 empty] | Land not available
3 | Construction of building for Premetric Hostel at kondiparamba | 16/492 | GO (Rt)No.494/2015/SC/STDD dtd20-03-2015 | 115 Lakhs | [6 empty] | Draft drawing approved and sent for preparation of detailed drawings
4 | Construction of building for Premetric Hostel at Edapal | 17/492 | [8 empty] | Land not available
Head of Account : 4225-01-800-89
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
2 | Construction of building for ayyankali bhavanam | 22/497 | [8 empty] | Land not avaiable
3 | Construction of building fo ITC pathayikkarar | 34/497 | [8 empty] | work transferred to KSCI
4 | Construction of building for ITC keraladeeshwaram | 35/497 | GO(Rt)313/09 dtd.03.03.2009 of the SCST Dev. Dept for Rs.60 L | 60 L | 60/CE/B&LW/09-10 dtd 08.10.2009 for Rs.60 L | 60 L |  | 16.08.2010 | 26.08.2010 | 25.04.2011 | work completed | work completed
5 | Construction of building for ITI keraladeeshwaram | 47/498 | [8 empty] | Repetition
6 | Construction of building for ITC pandikkad |  | AS No.GO (Rt) 343/08 SCST DD dtd. 19.03.08 for Rs.51,37,881 | 5137881 | 112/CE/B&LW 08-09 dtd. 07.02.2009 | 63 Lakhs | 0 | SE(K)24/2009-2010 dated 0812.2009 | 2009-12-14 | 2010-10-31 | work completed
Head of Account : 4225-02-277-94
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of building for ashram school complex | 1/504 |  |  |  | 0 | 0 | 10 | 0 | 10 | Workcompleted
Head of Account : 4235-60-800-98-Social Justice
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Construction of building for government rescue home Thavanur | 1/588 | [8 empty] | work completed
| Renovation of building for custodial care home government rescue home Thavanur | 12/589 | [8 empty] | work transferred to KHRWS
| Construction of building for mahila mandiram | 17/589 | [8 empty] | work transferred to KHRWS
Head of Account : 4403-102-99-
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
89 | Construction of building for training centre at Malappuram | 7/574 |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | Land not avaiable
Head of Account : 4202-02-104-99-Technical High School Building
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Renovation of staff quarters at polytechnic perinthalmanna | 16/341 | [8 empty] | Estimate under preparation
2 | Construction of compound wall,atPolytechnic perinthalmanna | 17/341
3 | Construction of building for Polytechnic hostel kottakkal | 17/341 | [8 empty] | work completed
4 | Construction of compound wall, water tank platform, borewell and provision of interlock tiles for the staff quarters of Kottakkal Polytechnic | 17/341 |  |  | DR/2226/2015-16 dt 29.12.2015 for rs 20.50 L | 20.5 Lakhs |  | EE(BM) 01/2016-17 dated 20-05-16 |  |  | work completed
5 | Construction of a building for Kottakkal Polytechnic hostel | 35/342 | [8 empty] | work completed
6 | Construction of a staff quarters for Kottakkal Polytechnic | 51/271 | [8 empty] | work completed
7 | Perinthalmanna. Cunstruction of Library for Polytechnic College,Perinthalmanna. | 53/344 | G.O(Rt) No.1869/09 dated 12.11.2009 for Rs.53 lakhs | 53 Lakhs | 28/CE/BL/2011-12 dtd. 28.06.2011 Rs.53Lakhs | 53 Lakhs | 2011-08-27 | SE(K)33/10-11 dated 25.11.2011 | 2012-06-22 | 2012-12-21 | work completed
8 | construction of malaysian library block at perinthalmanna | 81/345 | [8 empty] | work can not be identified
9 | construction of compoundwall | 82/345 | [8 empty] | work can not be identified
10 | providing 4 nos class room at govt. polytechnic perinthalmanna | 83/345 | G.O(Rt) No.1315/2011/PWD dated 28.08.2011 | 50 Lakhs | 74/CE/BL/10-11 dtd. 30.07.2010 | 50 Lakhs | 2011-01-28 | SE(K)24/11-12 dated 04.11.2011 | 2011-11-11 | 2012-07-10 | work completed
11 | Construction of Civil Block in Govt. Polytechnic College, Perintalmanna. | 115/348 | GO.(Rt)No.1132/2014 dated 11.06.2014 | 250 L | TSNO:92/2015-16 DATED-13-05-2015 |  |  | SE(K)68/2015-16 DATED-19-01-2016 | 27.01.2016 | 26.01.2017 | structure completed
12 | Polytechnic Nannamukku | 75/345 | G.O.(Rt) No1046/09/PWD dated 14.07.2009 Rs250Lakhs | 250 lakhs | [6 empty] | work cancelled
Head of Account : 4059-60-051-88-Jail
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Improvements to Sub Jail,Tirur | 7/46 | [8 empty] | Estimate underpreparation
2 | Renovation works to Sub Jail perinthalmanna | 8/46 | [8 empty] | competed
Head of Account : 4225-02-800-91-Training centers
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
12 | Construction of building fo ITC pathayikkarar | 34/497 | [8 empty] | work transferred to KSCI
3 | Keraladeeswarapuram. ITC, Kerala deeswarapuram. | 35/497 | AS No.GO (Rt) 313/09 dtd. 03/03/09 of the SC ST Development department for Rs.60 lakhs | 60,00,000 | 60/CE/B&LW/09-10 dtd. 08.10.2009 Rs.60Lakhs | 60,00,000 | SE (K) 26/2010-11 dtd. 16.08.10 |  | 26.08.2010 | 25.04.2011 | work completed
4 | Construction of building for ITI keraladeeshwaram | 47/499 | [8 empty] | Repetition
5 | Pandikkad. ITC,Pandikkad. | 12/500 | AS No.GO (Rt) 343/08 SCST DD dtd. 19.03.08 for Rs.51,37,881 | 5000000 | 112/CE/B&LW 08-09 dtd. 07.02.2009 Rs.63Lakhs | 63 Lakhs |  | SE(K)24/2009-2010 dated 0812.2009 | 2009-12-14 | 2010-10-30 | work completed
Head of Account : 4202-01-201-99 Secondary School Buildings
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Constrction of Building for GMUPS Parakadavu, Munniyoor Grama Panchayath | 13/287 | AS.No.GORt)No.7441 3/G.Edn.dtd.21.02.2013 | 90 lakhs |  |  |  | EE(BM)51/13-14 dated 21.12.2014 |  |  | work completed
2 | Construction of Class room building for Government HSS Peruvallur | 14/287 | GO(Rt)No.1284/ 2015/G.Edn dated 30.03.2015 Rs.50 lakhs | 5000000 | 2015-2016/2013-2014-56 dated 30.06.2015 for Rs.50 lakhs | 5000000 |  | EE(BM) 68/2015-16 Dated 12-02-2016 | 17.02.2016 | 16.12.2016 | work completed
3 | University Campus: Construction of Building for GMHSS ,Calicut University Campus | 15/287 | AS.No.GO(Rt)No.8851 3/G.Edn.dtd.23.02.2013 | 61.66 lakhs | DR/01/2013 14dated10.04.2013 |  |  | EE(BM)17/2016-17 dt 13.06.2016 dated 18.12.2013 | 10.12.2013 | 17.08.2014 | work completed |  |  | Nil
4 | Construction of a building for GUP school AR Nagar | 16/287 | [8 empty] | work completed
5 | COSTRUCTION OF BUILDING IN GVHSS AT PULLANUR (2012-13) | 17/287 | GO(RT) NO:949/2014 G.EDN 27/02/2013 | 75 L | DR 26/2013-14 DT 02/08/13 |  |  | EE(B)28/14-15 dt 21-10-14 | 7156706 | 10096681 | work completed
6 | Construction of building for GUPS Pathappiriyam | 18/287 | GO ( Rt) No 1300/2013 G edn dated 19/03/2013 | 30.00 lakhs | DR 35/2013-14 dated 03/08/2013 for Rs 30.00lakhs |  |  | EE(BM)18/2014-15 dated 29/08/2014 | 2816629 | 3520786 | work completed
7 | Construction of building for GHSS Kavanur | 19/287 | GO ( Rt) No 1264/2013 G edn dated 16/03/2013 | 50.00 lakhs | DR 36/2013-14 dated 03/08/2013 for Rs .50.00lakhs |  |  | EE(BM)39/2013-14 dated 27/01/2014 | 4363577 | 4787117 | work completed
8 | Construction of building for GMUPS Areacode | 20/287 | GO ( Rt) No 906/2013G edn dated 23/02/2013 | 30.00 lakhs | DR 44/2013-14 dated 13/08/2013 for Rs 30.00lakhs |  |  | Agt. No EE(BM)44/2013-14 dated 10/02/2014 | 2463613 | 3267353 | work completed
Head of Account : 4202-02-103-99 Technical High School building
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
165 | Construction of building for THS Perinthalmanna | 25/340 | G.O. (Rt) No.1725/2013/PWD dt 21-02-2013 rs.67Lakhs | 67lakh | DR 3/2014-15 dt 30/05/2014 | 67lakh | 2014-08-04 | EE(BM) 48/2014-15 dtd 21-02-2015 | 2015-03-03 | 2016-01-02 | Plastering wor in progress | 6856180
| Construction of building for THS Manjeri | 28/340 | [8 empty] | work completed
Head of Account : 4210-01-110-93 Allopathy
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Construction of a building for Staff quarters at Taluk Hospital, Nilambur | 20/380 | [8 empty] | LSGD work
Head of Account : 4059-60-051-73 court building
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of a building for court complex Manjeri | 16/62 | Go(Rt.)No.2948/2014/home dated TVM 07/11/2014 | 1200 Lakhs | Order No.2015-2016/2014-15 1530 dated 21-04-15 vide ref 54/2015-16 Rs. 112100000 | 1121 Lakhs |  | No.1/SE(J)/EKM/2016-17 dt 17.06.2016 | 09.12.2016 | 08.06.2019 | Foundation work in progress
Head of Account : 4202-01-800-88-(NP) LAC-ADS
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Auditorium for GLP School , Parambil peedika. | 15/330 | [8 empty] | work completed |  | 2987385
2 | Construction of building for Panchayath office Parappur | 16/330 | G.O(MS)No.534/ 2014/LSG dated 25.02.2014 | 44 Lakhs | DR/16/14-15 dtd: 22.07.2014 | 44 Lakhs |  | EE(BM)55/2015 dtd: 11.01.2016 |  |  | Work completed |  | Nil
3 | LAC - ADF Construction of Plus Two Block at Thavannur Kelappaji GVHSS | 17/330 | AS.No.GO(Rt)No.959/013/G.Edn.dtd.27.02.2013 for Rs.125.L | 125 lakhs | CR /03/2013-14 dated 19.06.2013 of SE, Kozhikode RS.125 Lakhs | 125 lakhs |  | SE (K)44/2014-15 dated 13-02-2015 |  |  | work completed |  | 16026759
4 | Construction of GFLPS Ponnani in Malappuram District | 18/330 | GO(Rt) No.3362/2015/G Edn dated 11.08.2015 | 5350000 |  |  |  | PRICE No.1935/2015-16 dtd.07.12.2015 |  |  | transffered to COSTFFORD
5 | Construction of Building for GHSS ,Marancheri (First floor) in Malappuram District | 19/330 | GO(Rt) No.2602/2015/G Edn dated 30.06.2015 | 5000000 | 2317/2015-16 dt 04.01.2016 (PRICE) | 5000000 |  | EE(BM)21/2016-17 Dt 23.06.2016 |  |  | work completed
6 | LAC - ADS - 2014-15. Construction of School building to GHSS Veliyankode in Malappuram District.(Ponnani LAC) | 20/330 | GO(Rt) No. 3170/2015/G.Edn Dt.01.08.2015 for Rs.44 Lakh | 44.00Lakh | 2273/2015 - 2016 (PRICE) dated 01.01.2016 | 44.00Lakh |  | EE(BM) 50/12016-17 dt 30.09.2016 |  |  | objection on the position of the building in the site from the School Authorities, Hence work not started
7 | Thavannur: Construction of Higher Secondary School Building GHSS, Kadanchery | 21/330 | GO(Rt)No.1786/2014/G.Edn dated 08.05.2014 | 100 lakhs | DR/39/2014-15 dt 14.11.2014 | 100 lakhs |  | EE (BM)43/2015-16 dated 11/12/2015 |  | Velayudhan .M | work completed
8 | Construction of class room building for Government LP School Olakara | 22/330 | GO(Rt)1712/2015/G Edn Dt 08/05/2015 | 4000000 | Reg.No.1004/2015-16 dt 07.09.2015 | 4000000 |  | EE(BM)69/2015-16 dt 16.02.2016 |  |  | work completed
9 | Construction of Toilet Block in Govt.Arts & Science College, Kondotty | 23/331 | G.O RT No.1331/2015/H.Edn TVM dated 09/06/2015 | 2500000 | 1044/2015-2016(PRICE)dt 10-09-2015 Rs 25 lakh | 2500000 |  | EE(BM)64/2015-16 DATED 06-02-2016 |  |  | atructural work completed. Superstructure work started fi ground and first floor
10 | Construction of building for Government HSS, Purathur | 24/331 | GO(Rt)11941/2015/G.Edn. Dated 22.05.2015. | 150 Lakhs |  | 150 Lakhs |  | SE(K)7/2015-16 dtd 28.01.2016 |  |  | finishing work in progress
11 | LAC-ADS-2014-2015-Construction of Semi-permanent building Government College, Tanur. | 25/331 | GO(Rt)No1942/2015/G.Edn. Dated 22.05.2015 for Rs.50 lakhs | 15000000 | 2878/2015-16 dtd 27.01.2017 | 15000000 |  | Agt.No.SE(K)40/2015-16 dtd.17.10.2015. |  |  | work completed |  | 1776565
12 | Construction of Class room building for Government HSS Peruvallur | 26/331 | GO(Rt)No.1284/ 2015/G.Edn dated 30.03.2015 Rs.50 lakhs | 5000000 | 2015-2016/2013-2014-56 dated 30.06.2015 for Rs.50 lakhs | 5000000 |  | EE(BM) 68/2015-16 Dated 12-02-2016 |  |  | work completed |  | 2400433
13 | Construction of Building for Govt. High School,Neduva | 27/331 | GO(Rt)No.3908/2014/G.Edn dated .Tvm, 29.09.2014 | 11600000 | CR/20/2014-15 dtd 14.11.2014 for Rs.116 lakhs | 11600000 |  | SE(K)2/2015-16 dtd 21.04.2015 |  | V.Venugopal, Kurumbathur | work completed |  | 6213893
14 | Construction of class rooms for GLPS parambilpeedika | 28/331 | [8 empty] | work completed |  | 2987385
15 | Construction of Higher Secondary Building for GHSS Kokkur in Malappuram District | 29/331 | G.O(Rt)No.2265/2014/G Edn. Dated 10.06.2014 for Rs.70 lakhs. | 70 Lakhs | DR/83/2014-15 dt 31.03.2015 | 70 Lakhs |  | EE(BM)87/2015-16 dt 04-03-2016 |  | Velayudhan | work completed
16 | Construction of building for GHS Vadasseri | 30/331 | GO ( Rt) No 1182/2014 G edn dated 04/03/2014 | 40.00 lakhs | DR/81/14-15 dated 31-03/15 for 40 lakhs | 40.00 lakhs |  | EE(BM) 76/2015-16 dt 24-02-2016 |  | AbdualSalam | work completed
17 | Construction of building for Seethi haji memmorial GHSS Edavanna at kunduthodu | 31/331 | GO ( Rt) No 5020/2014G edn dated 17/11/2014 | 50.00 lakhs | DR/91/2014-15 dt 31.03.2015 | 50.00 lakhs |  | EE(BM)47/2016-17 dt 09.09.2016 |  |  | site levelling in progress
18 | Construction of building for GHSS Karakkunnu | 32/331 | GO ( Rt) No 963/2013 G Edn dated TVM 27/02/2013 | 60.00 lakhs | DR 25/2013-14 dated 02/08/2013 for Rs 60.00lakhs | 60.00 lakhs |  | EE(BM)46/2013-14 dated 18/02/2014 |  |  | work completed |  | 6344360
19 | 2013-14 Construction of building for GVHSS Nellikuth | 33/331 | GO ( Rt) No 3254/2014 G Edn dated TVM 13/08/2014 | Education | DR 41/2014-15 dated 19-11-2014 for 50 lakhs | 50.00 lakhs |  | Agt No. EE (BM)45 / 2015-16 dated 16.12.2015 |  |  | work completed
20 | Construction of School building to GBHSS Veliyankode in Malappuram District | 34/331 | [8 empty] | repetiion
21 | Construction of building for GHS Perakamanna, Othai | 35/331 | GO ( Rt) No 5303/2014 G edn dated TVM 28/11/2014 | 40.00 lakhs(50 L) | DR/85/14-15 dated 31-03/15 for 40 lakhs | 40.00 lakhs(50 L) |  |  | EE(BM) 33/201617 dt 27.08.2016 |  | Roof slab casted
22 | Construction of building for GUP school chungathara. | 36/332 | [8 empty] | work completed
23 | Construction of building for GMLP School Chandakunnu | 37/332 | [8 empty] | work completed
24 | Construction of a GMLPS, Oorakam-Keezhu Muri-Nelliparamba | 38/332 | G.O. (Rt) No.213990/2012/PWD dated 31-12-2012Rs167L | 192.50 L | CR/20/2013-14 dt 05.11.2013Rs185L | 192.50 L |  | SE(K)37/2014-15 dt 30.12.2014 |  |  | work completed |  | 11042463
25 | NABARD- Additional infra stucture work like Class room etc in GHSS Perassannur | 39/332 | G.O. (Rt) No.6021/2015/G.Edn dt TVM 26.12.2015 | 400 Lakh | Part TS issued 2308/2016-17 dt 28/8/16 of SE KKD | 400 Lakh |  | AEE(PB) 15/2016-17 dt 05/10/2016 |  |  | Design Received, Structural design works in progress.
Head of Account : 4202-02-800-86
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Constructing building for GVHSS (Boys) Vengara | 9/370 | GO(Rt)No 2140/2012/PWD Dt. TVM 24-12-2012 Rs.320.00 Lakhs | 320 lakhs | Reg No.14/CE/Bldgs/2014-15 dtd.12.08.2014 for 325.00 Lakh | 300 lakhs |  | SE(K)3/15-16 dtd.24.04.2015 |  |  | civil & electrical work completed
2 | Construction of building for Govt Arts and Science College,Kondotty Phase -I | 11/370 | GO(Rt)No.1126/2014/ H.Edn. Dated 12.06.2014013 | 4200000 | DR-20/14-15 dated 08.08.2014 for 42 lakhs | 4200000 |  | EE(BM)04/15-16 dated 13/04/2015 |  |  | Civil & electrical Work Completed.
3 | Construction of building for Govt Arts and Science College,Kondotty Phase -II | 12/370 | GO(Rt)No.1125/2014/H.Edn Dated 10.06.2014 for 250 Lakhs | 25000000 | 2586/2015-16 dtd:16.01.2016 for Rs.250 Lakhs | 25000000 |  | SE(K)91/2015-16 dtd 03.03.2016 |  |  | 250 LAKF
4 | Karingappara: Construction of Building at GUPS Karingappara Ozhoor grama Panchayath | 13/370 | GO(Rt) No. 3017/2013/ gen.edn. dt.20/07/2013for 50Lakhs | 50Lakhs | DR/67/2013-14 dt.9/9/2013 | 50Lakhs |  | EE(BM)48/2013-14 dtd 20.02.2014 |  |  | Civil and electrical completed
5 | LAC-ADF-Tirur Constituency-Renovation works to Government Schools in Tirur Constituency in Malappuram District | 14/370 | Tirur | Education |  | 425 Lakhs | GO(Rt)No.2151/2013/Gen/ Edn dtd.Tvm.23/05/2013 | 19/CE/BL/2013-14 dtd.10.09.2013 | SE(K)3/2014-15 dtd.08.05.2014 |  | completed
6 | Additional Block GHSS, Paravanna | 15/370 | Tirur | Education |  | 100 Lakhs | GO(Rt)No.952/2013/Gen/ Edn dt.27/02/2013 | DR23/2013-14 dated 18.07.2013 | EE/BM/30/2014-15 dtd.30.10.2014 |  | Civil work completed, no fund for electrical work
7 | LAC -ADF-Construction of building for Gov. Manavedan Higher Secondary School at Nilambur in Malappuram in Nilambur Constituency. (2012-13). | 16/370 | GO(Rt) No. 2235/2013/G.Edn dated 28/05/2013 for Rs 50 Lakhs | 50 Lakhs | DR/77/2014-15 dt 30.03.2015 | 50 Lakhs |  | EE (BM) 25/2016-17 dt 25.06.2016 | 16/07/2017 | 15/03/2017 | Second floor roof slab completed , masonary work in progress
8 | Construction of a Building for GHSS Pookkottumpadam (Second Floor) in Nilambur LAC) Malappuram District | 17/370 | G.O.(Rt)No. 210/2016/ G.edn dt TVM 19.01.2016 for 50 Lakh | 50.00 lakhs | 3563/2015-16 (PRICE) dt 24.02.2016 | 50.00 lakhs |  | EE(BM)43/2016-17 dt.05.09-2016 | 14/09/2016 | 13/07/2017 | finishing work in progress
9 | COSTRUCTION OF BUILDING IN GVHSS AT IRUMBHUZI (2012-13) | 18/370 | GO(RT) NO:947/2014 G.EDN 27/02/2014 | 50L | DR 20/2013-14 DT 28/06/13 | 50L |  | EE(BM)09/14-15 dt 17-06-14 |  |  | work completed
10 | Construction of building for ITI, Cheriyamundam | 19/370 | GO(Rt)No.1289/2014/LBR dtd.18.09.2014. 359 lakhs | 359 lakhs | 494/2015-16 dtd.15.07.2015 of Chief Engineer, .Bldgs. Tvm. | 359 lakhs |  |  |  |  | retaining wall work in progress
Head of Account : 4509-01-051-72
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Budget work - 2015 - 16. Construction of Village office cum Twin Quarters for Vettilappara Village Office in Malappuram District. | 30/69 | GO(RT)No.2888/2015/RD Dated 04.06.2015 | 50.00L |  | 50.00L |  | EE(BM)59/2016-17 dt 27.10.2016 | 28-10-2016 | 27-8-2017 | Finishing work in progress
2 | Budget work -2015 - 16. Construction of Village office cum Residential Quarters for Keezhuparamba Village Office in Malappuram District. | 31/69 | GO(RT)No.2888/2015/RD Dated 04.06.2015 | 50.00L | 1778/2015-2016 (PRICE) dated 27.07.2016 | 50.00L |  | EE(BM)64/2016-17 dt 01.11.2016 |  |  | Roof slab casted
3 | Construction of a bulding for twin Quarters & Village office at Moorkanad | 32/69 | GO(RT)No.2888/2015/RD d t04.06.2016 | 50.00L | 3623/2016-17 dt 28.12.2016 (PRICE) | 50.00L |  |  |  | Muhammed K | Land is not Hindrance free | 3510123 | 10 Months
4 | Annual plan 2015-16 Construction of Residential Quarters Building and Reccord room in Karuvarakundu village office in Malappuram district. | 33/69 | GO(Rt) No.2888/15/RD Dated TVM 04/06/2015 Rs 50 lakhs | Revenue | Reg.no.2964/2016-17 dt 28.10.2016 | 50 lakhs |  |  |  |  | Land is not Hindrance free
5 | Construction of a bulding for twin Quarters & Village office at Edappal | 34/69 | GO (Rt) No 615/2013/G.Edn dt 11/02/2013 | Education | CR/8/2013-14 dt 19.08.2013 | 12500000 |  | SE(K)45/2014-15 Dtd.16.02.2015 |  | Manzil Constructions Kochi | Land is not Hindrance free
Head of account : 4210--02-800-95-Projects under LAC-ADS (NP).
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of PHC building, Kuzhimanna | 26/406 | G.O (Rt.) No.3810/2014/H&PWD dt 26.11.2014 | 2500000 | DR/61/2014-15 dt 25.02.2015 | 2500000 |  |  |  |  | plinth beam completed
2 | Construction of Ayurveda Dispensary Kurambathur Melmathur Smarka Building | [9 empty] | work completed
3 | Construction of Ayurveda Dispensary Thirurangadi | 54/409 | G.O (Rt.) No.1626/2013/H&PWD dt 13.05.2013 | 50 Lakhs | DR/37/2013-14 dt | 50 Lakhs |  | EE(BM)53/2013-14 dt 01.03.2014 |  |  | work completed |  | 4965273
4 | Construction of Ayurveda Dispensary Kurambathur Melmathur Smarka Building | 52/409 | [8 empty] | Repetition
5 | Kuttippuram: Construction of Building for CHC Kuttippuram | 55/409 | GO (Rt) No.3518/2013/H&FWD Dtd.TVM 18.10.2013 | 4700000 |  |  | GO (Rt) No.3518/2013/H&FWD Dtd.TVM 18.10.2013 |  |  |  | Put on tender
6 | LAC ADS 2013-14:Construction of building for CHC Mankada | 56/409 | GO(Rt) No. 1956/2014/H& FWD Dtd.06/02/2014 for Rs.40Lakh | 4000000 | DR/25/2014-15 dt 30.08.2014 | 4000000 |  | EE(BM)59/2015-16 dt 22.01.2016 |  |  | work completed |  | 5022929
7 | LAC ADS 2013-14:Construction of building for CHC Kalikavu | 57/409 | GO(Rt) No.2280/2014/H&FWD Dt.05.07.2014 | 5000000 | DR/55/2014-15 dtd23.01.2015 for EE,PWD(B)Dvsn,Mlpm.50Lakhs | 5000000 |  | EE(BM)12/2016-17 dt 08.06.2016 |  | Aboothahir K,MANZIL Constructions. | Masonry work in progress
8 | LAC ADS 2013-14:Construction of building for CHC Karuvarakundu | 58/409 | GO(Rt) No.2059/2014/H& FWD Dt.24.06.2014 | 5000000 | DR-19/2014-15 Dt.07.08.14 of EE,PWD(B)Dvsn,Mlpm | 5000000 |  | EE(BM)24/2015-16 dated 08.09.2015 |  | EE(BM)24/2015-16 dated 08.09.2015 | Work completed |  | Rs.60,52,086.00.00/-
9 | LAC ADF 2012-13:Construction of New block building for CHC at wandoor | 59/409 | GO(Rt) No. 2407/2014/H& FWD Dt.17/07/2014 for Rs.50Lakh | 5000000 | DR/51/2014-15dt 08.01.2015 Rs.50L | 5000000 | EE(BM) 65/15-16 dated 01.02.2016 | DR/51/2014-15dt 08.01.2015 Rs.50L | 2016-01-08 | 2016-11-07 | Work completed |  | 5912392
10 | Construction of New Block Buildig for Taluk Hospital Malappuram | 60/410 | GO(Rt) 3717/2015/H&FWD dt TVM 18.11.2015 | 345 Lakh | 3903/2016-17 dt 25.01.2017 for rs 345 Lakh | 345 Lakh |  |  |  |  | SN issued
11 | COSTRUCTION OF BUILDING FOR GOVT: HOMOEO DISPENCERY AT ANAKKAYAM(2013-14) | 61/410 | GO(RT) NO:3082/2014 H&FWD 17/09/2014 | 25 L | DR-68/2014-15 dated 30-3-15 | 25 L |  | EE(BM15/2016-17 dt 10.06.2016 |  |  | Completed
12 | Construction of building for PHC Poovathikkal in urangattiri gramapanchayath | 62/410 | GO ( Rt) No 3455/2014 H & FWD dated TVM 24/10/2014 | 25.00 lakhs | DR/86/14-15 dated 31-03/15 for 25 lakhs | 25.00 lakhs |  | EE(BM)09/2016-17 dt 04.06.2016 |  | Abdul Hameed MK | work completed
13 | Construction of building for PHC Poovathikkal in urangattiri gramapanchayath | 63/410 | GO ( Rt) No 3811/2014 H&fwd dated 26/11/2014 | 75.00 lakhs | D8-89/2014-15 dt-31-03-2015 Rs75 Lakh | 75.00 lakhs |  | EE(BM)81/2015-16 dt 03-03-2016 |  | Mohammed Ashraf | Finishing work in progress
14 | Construction of building for PHC karulayi | 64/410
15 | LAC -ADF-Construction of building for Govt.Ayurveda Hospital Mamankara at Vazhikkadavu in Nilambur Constituency (2014-15). | Health | G.O (Rt) No. 2012/2015/H&FWD Dated 29/06/2015 | 25 L | 3814/2015-16 dt 02.03.2016(PRICE) |  |  | EE(BM)57/2016-17 dt 27.10.2016 |  | Sebastian VJ | Agreement Executed |  | 2350619/- | 2441823
16 | COSTRUCTION OF BUILDING FOR PHC VENGALUR PANAYI AT ANAKKAYAM(2013-14) |  | GO(RT) NO:3790/2014/ H&WD dated 25/11/2014 | Health Dpt | DR-988/2015-16 dated 6-9-15 | 30 L | EE(BM)83/2015-16 dt 4-3-16 |  |  |  | Masonry work in progress
17 | COSTRUCTION OF BUILDING FOR PHC IN ATHANIKKAL AT POOKOTTUR(2013-14) | Health | GO(RT) NO:3456/2014 H&FWD 24/10/2014 | 35 L | DR/58/2014-15 dated 2/02/15 |  | EE(BM)27/2015-16 dated 23.09/15 |  | 25/09/2015 | 24/7/2016 | work complete
Head of Account : 4235-60-800-98
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[11 empty] | civil | electrical
498 | Repair and maintanance of old Pratheeksha Bhavan Building for accomodating Childrens Home Thavanoor | 55/596 | GO(Rt)No.471/2015/SJD dated 30.07.2015 | 11,60,000 lakshs | 3291/2015-16 dt 15.02.2016 | 11,60,000 lakshs |  | EE(BM)30/2016-17 dt 04.08.2016 |  |  | completed
497 | Repairs and maintanance of Rescue Home Thavanoor | 58/596 | GO(Rt)No.383/2015/SJD dated 18.06.2015 | 1430,000 lakhs | Reg No.1454/2016-17 dt 11.07.2016 | 1430,000 lakhs |  | EE(BM)41/2016-17 dt 03.09.2016 |  | K.Moossa | completed
501 | Social Justice Complex, Thavanur Chidrens Home (Boys) Chidrens Home (Girls), CWC & JJB. | 59/596 | GO(Rt)No.281/2014/SJD dated 28.04.2014 | 484.685 Lakh | 1619/2016-17 dt 19.07.2016 | 484.685 Lakh |  |  |  | K.Aboobacker | Agreement Executed
Head of Account : 4235-02-102-96
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
193 | Social Justice Department-Plan fund 2014-15-Construction of Building for Anganwadi No.100 in Muthuvallur Panchayath in Malappuram district | 25/605 | ICDS-A7-18498/14 dated 13.09.2014 | Rs.11.66 Lakhs | 1101/2015-16 dated 13/09/2015 for Rs. 1166000 | Rs.11.66 Lakhs |  | EE(BM) 82/2015-16 DATED 03/03/2016 |  | Ramakrishnan K, Muthuvallur | Work completed
194 | Social Justice Department-Plan fund 2014-15-Construction of Building for Anganwadi Centre No.05 in Pulikkal Panchayath in Malappuram district | 26/606 | ICDS-A7-18498/14 dated 13.09.2014 for 11.60 Lakhs | Rs.11.66 Lakhs | 1098/2015-2016 Dated:12-09-2015 for Rs. 1166000 | Rs.11.66 Lakhs |  | EE(BM) 65/2015-16 DATED 06/02/2016 | 2016-04-03 | 2016-03-09 | Masonry completed. Slab shuttering in progress.
ioÀjIw : 4202þ03þ800þ91 þF³.kn.kn.acma¯v ]WnIÄ
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
125 | Construction of Administrative Block building (Training Academy) Ground floor of 29(K) Bn, NCC, Calicut University Campus, Malappuram - Phase I | 21/308 | G.O(Rt)NO.2569/14/H.Edn. dated 28.10.2014 for 487 lakhs | 487 lakhs | No.53/2015-16 dtd 21.04.2015 | 487 lakhs |  |  | SE(K)81/2015-16 dtd 10.02.2016 |  | Work completed |  | 31843120
ioÀjIw : 4210þ02þ110þ98þ {KmaoWtlman-tbm-¸Xn- Unkvs]³kdnIfpsS iàn-s¸-Sp-¯Â (\-_mÀUv klm-bw)
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
152 | Vattamkulam. Building for Homeo Hospital,Vattamkulam.. | 411/1 | GO (Rt) No 1046/09/PWD Dtd.14/07/2009 Rs.140Lakhs | Rs.140Lakhs | DR-1/09-10 dated 26.05.2009 Rs.140Lakhs | 5000000 |  | EE(M)3/09-10 dated 04.07.2009 | 2009-07-06 | 2009-12-09 | Civil & electrical completed
ioÀjIw : 4210--þ02þ-110-þ96þ {KmaoWtlman-tbm-¸Xn- Unkvs]³kdnIfpsS iàn-s¸-Sp-¯Â (\-_mÀUv klm-bw)
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
[11 empty] | civil | electrical
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Annual plan 2012-2013 Construction of building for new maternity wing to Taluk Head quarters Hospital Tirurangadi in Malappuram DT. | 16/399 | GO.(Rt)No.3292/2012/H & Fwd dated 05.10.2013 Rs.322Lakhs | 322 lakhs | Reg: 2697/2015-2016 Dated 19-01-2016 for RS 322.00 Lakhs of EE (B)TVM | 322 lakhs |  | SE (K) 88/2015-16 Dated 22-02-2016 |  | 12 months | Finishing work in progress
2 | Thuvvur: Construction of Building for PHC, Thuvvur |  | GO (Rt) No.817/2013/H&FWD Dtd.TVM 12.03.2013 | 25 Lakhs | DR-7/2013-14 dtd 28.06.2013 | 25 Lakhs | 2013-07-30 | EE(BM) 8a/2013-14 dated 05.09.2013 | 2013-11-05 | 2014-12-26 | Civil work completed.
3 | Construction of New Block Buildig for Taluk Hospital Malappuram |  | GO(Rt) 3717/2015/H&FWD dt TVM 18.11.2015 | 345 Lakh | 3903/2016-17 dt 25.01.2017 for rs 345 Lakh | 345 Lakh |  |  |  |  | Land not handed over by the department | completed | 4513598
4 | Construction of a building for PHC Edapatta | 21/399 | GO(Rt) No.13566/2013/H&FWD. Dtd.TVM 16/04/2013 | 7000000 | DR 42/2013-14 dt 12/08/2013 | 7000000 | 2013-10-29 | EE(BM) 54/13-14 dated 03.03.2014 | 2014-03-18 | 2014-10-17 | Work arranged under LAC ADF work completed (Repetation)
4202 01 202 93
Sl.No. | NAME OF WORK | REF TO BUDGET BOOK | AS NO &DATE | AS AMOUNT | TS NO & DATE | TS AMOUNT | TENDER DATE | AGREEMENT DATE | DATE OF COMMENCEMENT | SCHEDULED COMP DATE | PRESENT STAGE |  | EXPENDITURE SO FAR | EXPENDITURE IF ANY
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
470 | Construction of a building for GLPS Mundothuparambu | 14/302 | GO(Rt)No.3229/2015/G.Edn. Dtd 04.08.2015 of Rs.165,00,000/- |  | Reg No.2774/2015-16 dated 22.01.2016 for Rs.165/- lakhs of SE KKD |  |  | SE(K)89/2015-2016 dated 01.03.2016 | 2016-08-03 | 07.03.2017 | finishing work in progress
471 | Construction of Building for GVHSS Kondotty | 15/302 | [8 empty] | Agreement executed