## budget (hidden)
KERALA PUBLIC WORKS DEPARTMENT
BUILDINGS DIVISION, ALAPPUZHA
PROGRESS REPORT OF BUDGET WORKS AS ON 30.11.2015
Sl.No | Name of work | Budget Page no.& item no | A.S No. Date & Amount | T.S No. Date & Amount | Agt.No & Date Name of Contractor | Est. PAC/Qtd Rate/ Agreed. PAC | Date of commencement | Date of completion as per agreement | Date of extended completion, if any | Name of Constituency | Present Stage | Physical Progress (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
I. BUDGET WORKS
1 | 4059-01-051-94 STATE EXCISE - Construction of building for Excise complex Kuttanad | 10/6 1 L | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kuttanad | Structural design awaited. |  | alp
2 | Construction of building for Excise complex Cherthala | 10/7 1 L | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Estimate to be revised based on 2014 DSR as requested by Excise Commissioner, Tvm. |  | ctl
3 | 4059-01-051-86 PUBLIC WORKS (CIVIL WORKS) - Stimulus package - Constrcution of building for THS Krishnapuram. | 17/33 0.10 L | GO(Rt)No. 1187/09/PWD dt. 14.08.09 for 40 L | 40/SEBSC/ 09-10 Dt: 30/11/09 for Rs: 44L | 99/SEBSC/09-10 dt 20/02/10 P. Kala Kailas | 3781836/ 9.9% above/ 4010241 | 03.04.10 | 9 Months 02.01.11 | Nil | Kayamkulam | Work Completed | 100 | hpd
4 | Construction of new building for Govt Girls H.S.S. Haripad. | 33/266 1L | Go(Rt) No 1973/12/PWD dt 26/11/12 for Rs 200 L | 42/SCBSC/ 2012-13 dt 08/03/13 for 200L | 3/SEBSC/ 13-14 dt 15/04/13. J Nizar | 18687954/0.3% below /18631809 | 15/04/13 | 10 Months upto 14.02.14 | Nil | Haripad | Work completed. | 100 | hpd
5 | Constructionof New Educational complex, Chengannur | 33/260 1L | GO(Rt) No. 715/2014/PWD dtd. 29.05.2014 for Rs. 500 L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | AS obtained. Estimate to be prepared. Soil investigation to be conducted total station completed. AR drawing obtained. Structural design to be obtained
6 | 4059-60-051-98 ADMINISTRATION OF JUSTICE - Construction of five story building for court complex at Chengannur | 34/17 NIL | GO(Rt)No. 565/12/PWD dt.31.03.12 for Rs.515 L | 87(a)/CE/BL/ 2012-13 dt 26/03/13 for Rs 592L | 4/SEJ/EKM 2014-15 dtd. 01.08.14 General Manager KSCC Ltd. TVM | 40973675 19% above E/R 48758673 | Nil | Nil | Nil | Chengannur | First Floor Roof work completed. Column work of 4th floor in progress | 30 | cgr
7 | Construction of Court Complex, Kayamkulam | 34/18 NIL | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kayamkulam | Soil investigation report received. Architectural Drawing received. Structural Design received estimate under preparation. |  | hpd
8 | Munsiff Court, Hripad | 51/5 0.9L | GO(Rt)No. 1184/09 dt.14.08.2009 (from Budget Book) | [6 empty] | Haripad
9 | Sub Court, Chengannur | 51/6 89.83L | GO(Rt)No. 565/12/PWD dt.13.03.2012 (from Budget Book) | [6 empty] | Chengannur
10 | 4216-01-700-87 JUDICIAL OFFICERS QUARTERS Construction of Judicial Officers Qrs at Alappuzha (10 Nos) | 69/10 10961000 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to CE on 21/06/13 for Rs. 514L for A.S. |  | alp
11 | Construction of Judicial Officers Quarters at Kayamkulam | 69/11 0.24L | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kayamkulam
12 | Construction of Judicial Officers Quarters at Chengannur (4 Nos) | 70/31 11.82 L | GO(Rt) No. 995/2014/Home dt. 26.03.14 for Rs. 225L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | AR drawing to be obtained. Land to be obtained from concerned department. |  | cgr
13 | 4210-01-203-99 EDUCATION_UNIVERSITY: Construction of new building for Govt. Arts and Science College at Ambalappuzha | 285/50 2.2L | GO(Rt)No.237/12/H.Edn dt. 01.02.12 for 12.20 C | 22/CE/BLW 12-13/dt 16/05/13 for Rs 14.3 Crore | 71/SEBSC/12-13 dt. 29.09.12 J Abdul Vahid | 135464086/3.6 % below / 130587379 | 04.10.12 | 03.10.14 | Nil | Ambalapuzha | Work completed. | 100 | alp
14 | 4202-02-103-99 TECHNICAL EDUCATION - NABARD - RIDF -XVII Construction of THS Haripad | 303/2 46.2L | G.O (Rt) No.570/12/ H.Edn. dt.19-3-12 for Rs.285 L | 46/CE/BLDG/ 12-13 dt: 16/6/12 for Rs: 285L | 102/SEBSC/12-13 dt 07/01/13. M.Ismail Kutty | 27263907/23.3% above/ 33261967 | 11.01.13 | 18 Months up to 14.07.2014 | Nil | Haripad | Work completed. | 100 | hpd
15 | Construction of Compound wall in THS, Krishnapuram | 304/19 NIL | G.O (Rt) No.2105/2014/ H.Edn. dt.30.08.14 for Rs.54.5L | ALP/2015-16/2015/1249 dtd. 20/06/15 for Rs.54.5L (Through PRICE) | 15/EE/15-16 dt. 17/09/15 | Nil | Nil | 3 Months upto | Nil | Kayamkulam | Work in progress.
16 | 4202-02-104-99 POLYTECHNIC Construction of Auditorium and Library building for Govt. Women's Polytechnic Kayamkulam | 308/46 7.18 L | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kayamkulam | Estimate to be prepared. |  | hpd
17 | Construction of staff quarters and Principals Quarters in Govt. Women's Polytechnic, Kayamkulam | 308/47 0.14 L | GO(Rt)No.2485/2013/H.Edn. Dt. 26.12.13 for Rs.8.45 C | Nil | Nil | Nil | Nil | Nil | Nil | Kayamkulam | Investigation and detailed design completed. Detailed estimate submitted to SE for Rs. 8.45C on 04/06/15 for T.S.through PRICE. |  | hpd
18 | Construction of new building for Administrative block for Govt. Polytechnic at Cherthala | 309/57 14.35 L & 313/5 14.35 L | G.O(Rt.)No. 1529/2014/ H. Edn. Dt. 07.07.2014 for Rs. 560 L | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Estimate submitted to SE for T.S through PRICE on 15.11.2015. |  | ctl
19 | Construction of Laboratory block for Govt. Polytechnic college, Cherthala | 309/58 0.43 L | GO(Rt)No.912/12/H.Edn. Dt. 18.05.12 for 5 C | 79/CE/BL/12-13 dt 29/09/12 for Rs 5Crore | 5/SEBSC/13-14 dt 19/04/13 Sabu.PL | 38895652/4% above/ 40451478 | 24/04/13 | 42117 | Nil | Cherthala | Structure work completed Mansory Work in progress. | 60 | ctl
20 | 4210-02-103-95 PRIMARY HEALTH CENTRES Construction of new IP Ward in PHC, Kalavoor | 354/27 NIL | GO(Rt) No. 3125/2014/H&FWD dtd. 22/09/14 for Rs. 35 L | 34/EE/14-15 dtd. 31/10/11 for Rs. 35L | Nil | Nil | Nil | Nil | Nil | Alappuzha | Estimate submitted to CE on 12.02.2014 for Rs. 36 L under LAC ADS proposed by Dr. T.M. Thomas Issac, MLA Alappuzha Constituency. AS obtained. Tendered with date as 03.12.2014. No response. Retendered with date as 21.01.2015.No response. Quotation invited two times. No response.The fact reported to CE for further Direction. |  | alp
T.D.MEDICAL COLLEGE, ALAPPUZHA
21 | Govt. TDMCH Complex Vandanam - Alappuzha - Renovation of OP block A&B, C, D&E, F blocks | 376/2 48.97L | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to Director Medical Education, TVM on 23.08.2013 for Rs. 98 L . Estimate return by DME. To be revised with DSR 2014 |  | spl
22 | TDMCH Vandanam, Alappuzha construction new Adminstrative block cum Examination hall in TDMC compound - phase - I | 377/20 24486000 | G.O(Rt) No. 2882/2014/H&FWD dtd. 23.08.2014 for Rs. 500L | Nil | K.V.Joseph & Sons | Nil | Nil | Nil | Nil | Ambalapuzha | Work started.
23 | TDMCH Vandanam, Alappuzha construction new Adminstrative block cum Examination hall in TDMC compound - phase - II | 377/20 24486000 | G.O(Rt) No. 1643/2015/ H&FWD dtd. 02.06.2015 for Rs. 3 Crores | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Detailed estimate under preparation.
24 | Construction of Flat type eight storied Residential Quarters for P.G Doctors in Govt. T.D Medical College, Alappuzha | 377/21 13223000 | G.O (Rt)No.3763/2013/H&FWD dt.11/11/2013 for Rs.2500 L | Go.(Rt)No. 780/2015/PWDdtd. 04.06.2015 for Rs. 2500L | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Pile cap completed.
25 | 4225-01-277-91 Post Metric Hostel Post Metric Hostel for Girls at Kayamkulam | 451/1 1L | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kayamkulam
26 | Construction of Post Metric Hostel for girls at Cherthala | 451/8 1L | Order No. Edn-C3-23056/07 dtd. 10.03.2014 of the Director SC Development Dept. for Rs. 3.96 Crore | Nil | Sri. Roys John | Nil | Nil | Nil | Nil | Cherthala | S.N. issued
27 | 4210-02-110-86 AYURVEDA Construction of 10 nos. pay wards at Govt.Ayurveda Hospital,Cherthala. | 362/1 NIL | GO(Rt) No.2329/2013/H&FWD dtd. 02/07/13 for Rs.40 L | 42/EE/ 13-14 dtd. 27/01/2014 for Rs. 40 L | Nil | Nil | Nil | 6 months | Nil | Cherthala | Quotation sanction obtained. Agreement to be executed. Address to DMO (ISM) for depositing the balance amount. |  | ctl
28 | 4225-01-800-89-11 PRE EXAMINATION TRAINING CENTRE Construction of building for Pre Examination Centre at Block office Muthukulam.Haripad. | 453/21 1L | GO(Rt.)226/ 2014/SC/STDD dtd. 07.02.2014 for Rs. 170 L | Nil | J.Manzoor | Nil | Nil | Nil | Nil | Haripad | Work started. S.N issued. |  | hpd
29 | Agricultural Department - Repair work at Regional A.I.Center, Cherthala | 529/32 0.65L | GO(Rt.) No. 1591/2014/AD dtd. 28.08.2014 for Rs. 7.05L | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Work tendered. No response. Retenderd no response. Quotation invted no response. Re -quotation to be invited.
30 | 5452-01-800-98 BUILDINGS UNDER PLAN Department of tourisum - construction of additional story to the Govt. Guest House, Alappuzha | 570/33 0.08L | Order No. HB3.6150/2013 dtd. 26.01.2014 of the Director Dept. of tourisum for Rs. 140 L | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | Finishing work in progress. | 25 | spl
Executive Engineer

## non-budget (hidden)
PROGRESS REPORT OF NON BUDGET WORKS AS ON 30.11.2015
Sl. No | Name of work | A.S No. Date & Amount | T.S No. Date & Amount | Agt.No & Date Name of Contractor | Est. PAC/Qtd Rate/ Agreed. PAC | Date of commencement | Date of completion as per agreement | Date of extended completion, if any | Name of Constituency | Present Stage | Physical Progress (%) |  | Red - Completed | Blue - Ongoing work | Violet- Tendered
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Court Complex, Haripad Phase II | G.O (Rt.) 3740/2013 Home dtd. 9/12/2013 for Rs. 234L | 4/SEJ/EKM/ 14-15 dt. 26.09.14 for Rs. 249L | 2/SEJ/EKM/ 15-16 dtd. 25.06.15 Sri. Lalji. | 22798042 23.69% above 28198898/- | Nil | 15 months upto | Nil | Haripad | Column work in progress |  | hpd
2 | Re-construction of the existing wooden staircase of the Pricipal District Judges Chamber (behind the District Court, old block) at District Court complex, Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | Estimate for Rs. 9.9L submitted to CE for AS through Price by SE, Judicial. |  | spl
3 | District Court, Alappuzha improvements for the rear courtyard of Dirstict Court building, Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | Estimate for Rs. 9.995L submitted to CE for AS through Price by SE, Judicial. |  | spl
4 | Construction of Electrical Room and water sump at Court Complex, Haripad. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Estimate for Rs. 3699500 to be submitted to CE for AS through PRICE
5 | VOCATIONAL HIGHER SECONDARY SCHOOLS Construction of building for Govt. VHS School for Girls, Chengannur, Alappuzha | GO(Rt)No.4583/13/Gl.Edn dt. 30-10-2013 for Rs.50 L | 11/EE/14-15/ dtd. 31.05.14 for Rs. 52 L | Nil | Nil | Nil | Nil | Nil | Chengannur | Work tendered with date as 8/7/14. But no response. Re-tendered with date as 2/8/14. 1 No. tender received from Hariharakumar with 13.33% above. Submitted to SE for approval. Tender Sanction received but firm period expired.So Contractor not willing to execute agreement and requested to release EMD. So tender cancelled and Quotation invited with date as 04.08.15. Quotation received from Sri.J.Manzoor at 19.9% above estimate rate, submitted to SE for approval. |  | chr
6 | Construction of building for Govt. VHS School, Chunakkara, Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikara | Detailed estimate for Rs. 152L submitted to the Director, VHSE, TVM by CE on 18.06.2014 for AS. |  | hpd
7 | Construction of building for GHSS Chunakara, Alappuzha | GO(Rt)No.4781/13/Gl.Edn dt. 12-11-2013 for Rs.125 L | 53/SEBSC/13-14 dtd. 20/10/2014 for Rs. 143.75L | 22/SEBSC/14-15 dtd. 25.09.14 Sri. J. Nizar | 13354867 17.25% above 15658582 | Nil | 10 months upto | Nil | Mavelikara | Plinth completed. Column work in progress. |  | hpd
8 | Construction of AEO Office Haripad. | GO(Rt) No.241/12/PWD dt 16/02/12 for Rs 50 L | 46/EE/BL 12-13 dt 23/06/12 for Rs 57.5 L | 103/SEBSC/ 12/13dt 07/01/13. M. Ismail Kutty | 5045911/13.9% above /5747293 | 14.01.13 | 8 months up to 13.09.13 | Nil | Haripad | Work completed | 100 | hpd
9 | Construction of building for Educational Complex, Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Rough cost estimate for Rs. 5.25Crore submitted to CE for AS vide lr. No. A5/913/2005 dtd. 21/06/13 |  | alp
10 | HIGHER EDUCATION Construction of Compound wall and trainage at Govt. College, Ambalappuzha | GO(Rt) No.2031/15/H.Edndt 05/08/15 for Rs 125L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate for Rs. 125L submitted to SE for T.S on 18/11/15 through PRICE
11 | Construction of Auditorium and Library in Raja Ravi Varma College of Fine Arts, Mavelikara | GO(Rt)No.946/14/H.Edn dt. 19-05-2014 for Rs.150 L | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikara | AS obtained. Strctural Design to be prepared. |  | hpd
12 | Construction of a new building for Govt. S.V. Higher Secondary School, Kudassanad | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikara | Estimate for Rs. 100L submitted CE for AS. Vide Lr. No. A10/436/14 dtd. 24/04/14. To be revised. |  | hpd
13 | Construction of new building for Govt.H.S.S Ala, Chengannur | GO(Rt)No152/2015/G.Edn dt. 13.01.2015 for Rs.172.5 L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | Estimate for Rs. 172.5L submitted to SE for T.S on 18911/15 through PRICE
14 | Construction of new class room for Govt. H.S.S Ayaparamplu Haripad | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Estimate for Rs. 190 L to be submitted to SE for A.S. through PRICE.
15 | Construction of class room for Govt. H.S.S. Thalavady in Alappuzha District | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kuttanadu | Estimate for Rs. 160L submitted to SE for A.S.on 27/11/15 through PRICE
16 | IHRD- Grant-in-aid -2014-15- Construction of Ground floor of the main building of college of Applied Science, Haripad | Go(Rt) No. 1052/2014/ H.Edn. Dtd. 30/05/2014 for Rs. 130L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Estimate for 243L. Submitted to SE for revised A.S. |  | hpd
17 | IHRD - Construction of roofing above the main building -interior work at college Engineering Cherthala | Go(Rt) No. 2446/154/ H.Edn. Dtd.18.09.2015 for Rs. 25L | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Estimate to be prepared. |  | hpd
18 | IHRD - Renovation of old building of College of Engineering, Chengannur | Go(Rt) No. 2446/154/ H.Edn. Dtd.18.09.2015 for Rs. 24.98L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | Works estimate to be prepared
19 | TECHNICAL EDUCATION Maintenance and modification works of the old buildings of Raja Ravi Varma College of Fine Arts, Mavelikara | Order No.D4/7903/14 dt. 01-03-2014 of Director of Technical Education for Rs.10 L | 17/EE/14-15 dtd. 01.07.14 for Rs. 10 L | 18/EE/14-15 dtd. 04.09.14 Sri. M.R. Chandrangadhan | 999974 7.3% below 926976 | Nil | 3 months upto | Nil | Mavelikara | Finishing work in progress.
20 | Construction of new Administrative Block for Govt. ITI Chengannur | GO(Rt) No.403/2014/LBR dt 20/03/14 for Rs. 77 L | 30/EE/13-14 dt 08/10/14 for Rs 77 Lacs. | 18/EE/15-16 dtd. 23.09.15 Sri. Benu Varghese |  | Nil | Nil | Nil | Chengannur | Agreement executed. Work cannot be started yet due to objection from ITI authorities. |  | chr
21 | Womens Polytechnic College, Kayamkulam - flooring with tiles | D4/16869/15 dtd.18.06.2015of T.Edn. for Rs. 24.98L | Nil | Nil | Nil | Nil | Nil | Nil | Kayamkulam | AS.obtained to be tendered.
22 | Construction of Electrical Controll Room at Govt. ITI,Chengannur | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | Estimate for Rs. 16.70L to be submitted to SE for A.S. through PRICE.Fund to be transferred from Chief Electrical Engineer.
23 | GENERAL EDUCATION Construction of new building for Govt. U.P.School Nangiarkulangara, Haripad, Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Estimate for Rs. 100L Submitted to SE for A.S through PRICE.
24 | HOMEO : Construction of addl Kitchen block,Gen Ward & Lab for District Homeo Hospital Alappuzha | Order No.P2/02/10/DH/Tvm dt. 19.10.10 for 50 L | CE/BLDG/Alpy/1858/2011-12 dt 17/06/11 for 52 L | 67/SEBSC/11-12 dt 25/01/12. B Harikrishnan | 4457156/ 13.2% above 5045501 | 06.02.12 | 9 months upto 05.11.12 | Nil | Ambalapuzha | Plastering work completed. Roof slab of kitchen casted. Work standstill. | 70 | alp
25 | MEDICAL COLLEGE Alappuzha -Construction of water tank of 5 Lakh litters capacity at MCH Vandanam. | GO(Rt) No.350/11/PWD dt. 28.02.11 for 200 L | 111/CEBL/11-12 dt 25/01/12 for Rs 230 L | 72/SEBSC/12-13 dt 29/09/12. J Abdul Vahid. | 22490245/14.3% above 25706350 | 41070 | 12 Months upto 05.10.13 | Nil | Ambalapuzha | Pump house slab concrete in progress. 5 stages completed. | 25 | spl
26 | Construction of 2 floors of Trauma Care Unit in Govt. TDMCH, Alappuzha (Phase I) | G.O (Rt)No.4039/2013/H&FWD dt.05/12/2013 for Rs.10 Crores | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Detailed estimate for Rs. 13.79 Crore(including 2nd Phase) submitted to CE for T.S. on 13.07.2015 through PRICE.Tendered by date 03.12.2015 |  | spl
27 | Construction of 2 floors of Trauma Care Unit in Govt. TDMCH, Alappuzha (Phase II) | G.O (Rt)No.1642/2015/H&FWD dt.02.06.2015 for Rs.3.79Crores | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Detailed estimate for Rs. 13.79 Crore(including 2nd Phase) submitted to CE for T.S. on 13.07.2015 through PRICE.Tendered by date 03.12.2015
28 | Govt. TDMCH Complex, Vandanam, Alappuzha - Construction of Substation and diesel Generator room (Appendix -C- of "Construction of Trauma care unit" Phase 1 and II) | G.O (Rt)No.4039/2013/H&FWD dt.05/12/2013 for Rs.10 Crores | 828/2015-16 dtd. 07/08/15 through PRICE for Rs. 97.95L (Through PRICE) | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Part T.S.issued. Work tendered with date as 18.08.2015 and opened on 22.08.2015 at 11 A.M.No response. Retender invited with date as 07.09.2015. No response. Quotation invited on 06.10.2015. Lowest quotation received form Sri. Tomy Joseph. To be submitted to SE for apporval.
29 | Construction of Toilet, Ceiling and partition in 3rd floor of old block I&II for poviding Central Library in Govt. T.D.Medical, College, Alappuzha | G.O(Rt) No. 2168/2015/ H&FWD dtd. 10.07.2015 for Rs. 21.27L | 827/2015-16 dtd. 07/08/15 through PRICE for Rs. 21.27 L | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | T.S.issued. Work tendered with date as 18.08.2015 and opened on 22.08.2015 at 11 A.M. No response. Retendered with date as 07/09/15. No response. Quotation invited on 06.10.2015. Lowest quotation received from Sri. V.Shaji. To be submitted to SE for approval.
30 | Construction of 180 capacity two numbers Gallery type Lecture Hall at TDMC Alappuzha | G.O(Rt) No. 1621/2015/ H&FWD dtd. 30.05.2015 for Rs. 3 Crores | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Detailed estimate submitted to SE through PRICE on 27.11.2015 after rectifing the points noted by CE for T.S.
31 | Construction of Additional block for college of Pharmsutical Science at Govt. TDMC Alappuzha | G.O(Rt) No. 1626/2015/ H&FWD dtd. 01.06.2015 for Rs. 2.20 Crores | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Detailed estimate submitted to SE through PRICE on 28.09.2015 for T.S.Tendered by dt.03.01.2016
32 | Construction of Central Library cum Lecture Hall complex in TDMC Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | AR drawing received. Tentative structure design for estimate purpose obtained from CE design TVM and forwarded to AEE on 05.08.2014 for preparing the estimate for AS |  | spl
33 | Construction of balance portion of Men's hostel at Govt. College of Nursing, Alappuzha | GO(Rt) No.412/2014/H&FWD. dt 04/02/2014 for Rs 1.26 Crore | Nil | Sri.J.Abdul Vahid | Nil | Nil | Nil | Nil | Ambalapuzha | AS obtained. Work tendered twice by SE. No response. Quotation Sanctione awaited. |  | spl
34 | MCH, Alappuzha Construction of building adjacent to the present CT Scan Centre. | Order No. RSBY/15/2014/MCHA dtd. 01/09/2014 for Rs.49.45 L | 32/EE/14-15 dtd. 18.10.14 for Rs. 46L | 30/EE/14-15 dtd. 03.02.2015 M/s. J&J Associates, Kochi | 4057145 12.5% above 4564288/- | Nil | 6 months upto | Nil | Ambalapuzha | Work completed | 100
35 | Govt. TDMCH Complex Vandanam - Alappuzha - Maintenance of I1, I2 Block and attached Ramp for the year 2014-15 | F.S.No. 100/EE/2014-15 dtd. 19.02.2015 for Rs. 17.54L | 42/EE/14-15 dtd. 19.02.2015 for Rs. 17.54L | 07/EE/15-16 dtd. 20.07.15 M/s. J&J Associates, Kochi | 1752849 14.54% above 2007713 | Nil | 3 months upto | Nil | Ambalapuzha | Work completed | 100
36 | Govt.TDMCH Complex, Vandanam -Alappuzha - Special repair works to Peadiatric Surgery OT and Nuero Surgery OT in the 4th Floor of 'K' Block | Order.No.CE/BL/ALPY/797/15 dtd. 13..02.2015 for Rs. 7L | 45/EE/14-15 dtd. 28.02.2015 for Rs. 7L | 08/EE/15-16 dtd. 20.07.15 M/s. J&J Associates, Kochi | 699687 13.46% above 793865/- | Nil | 3 months upto | Nil | Ambalapuzha | Work completed | 100
37 | Govt. TDMC, Alappuzha Special repair works in Nuerology Ward, NICU, Trauma Care unit isolation ward and minor repairs of ABCDE Block | Order.No.A7/6461/2014/ TDMCA dtd. 07/02/2015 of the Principal, TDMC, Alapuzha for Rs. 12L | 46/EE/14-15 dtd.28.02.2015 for Rs. 12L | 20/EE/15-16 dtd. 25.09.15 Sri. Shaji. V. | 1199496 11.9% above 1342236 | Nil | 3 months upto | Nil | Ambalapuzha | Agreement executed. Work nearing completion
38 | Govt. TDMCH Complex,Vandanam, Alappuzha Annual maintenance of Diagnostic Block J1,J2,&J3 for the year 2014-15 | F.S.No. 121/EE/Spl/14-15 dtd. 10.03.2015 for Rs. 17.83L | 47/EE/14-15 dtd. 10.03.2015 for Rs. 17.83L | 01/EE/15-16 dtd. 20.04.2015 Sri. C.F. Georgekutty | 1777870 1.77% below 1746402 | Nil | 3 months upto | Nil | Ambalapuzha | Work Completed | 100
39 | Govt. TDMCH, Vandanam modificatiion works to Gynac operation theatre in first floor of 'K' Block | order .No. A7/11292/2013/GTDMCA dtd. 21/03/2015 of the Principal, TDMC, Alappuzha for Rs. 6.23L | 51/EE/14-15 dtd 30.03.2015 for Rs. 6.23L | 19/EE/15-16 dtd. 25.09.2015 Sri. Shaji.V | 620539 9.63% above 680297 | Nil | 2 months upto | Nil | Ambalapuzha | Work Completed
40 | Govt. TDMCH, Vandanam special repair works providing partition and ceiling IC Unit and Ward in 4th floor of I1 ,I2 Block | Order.No. CE/BL/ALPY/2196/15 dtd. 27.03.2015 for Rs. 10L | 02/EE/15-16 dtd. 20.04.2015 for Rs. 10L | 21/EE/15-16 dtd. 20.11.2015 Sri. G.Vishambaran | 994452 9.9% above 1092903 | Nil | 3 months upto | Nil | Ambalapuzha | Nearing completion
41 | Imporvement of widening of campus road infront of J1,J2,J3 Block in Govt. TDMCH,Vandanam, Alppuzha | Order.No. CE/BL/ALPY/2195/15 dtd. 27.03.2015 for Rs. 10L | 04/EE/15-16 dtd. 20.04.2015 for Rs. 10L | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Work tendered.No response . Retender invited on 13.07.2015. No response. Quotation invited with date as 04.08.2015.No response. Re-quotation invited on 15.09.2015. No response again quotation invited on 26.09.2015. Lowest Quotation received from M/s. J&J Associates, Kochi. Submitted to SE for approval.
42 | Govt. TDMCH, Vandanam Alappuzha - Construction of connection passage to Psychatry OP to Psychiatry Ward | Order.No. A7/6461/2014/ GTDMCA dtd. 09/04/2015 of the Principal, TDMC, Alapuzha for Rs. 15L | 13/EE/15-16 dtd. 15.05.2015 for Rs. 15L | 22/EE/15-16 dtd. 23.11.15 Sri.D.Abraham | 1499804/- 10% above 1649784/- | Nil | 3 months upto | Nil | Ambalapuzha | Work started.
ASSET MAINTENANCE OF TDMC ALAPPUZHA
43 | ASSET MAINT-13-14 Maintenance of D& E Block | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to the principal TDMC Alappuzha on 17/04/2013.(Rs 36.37 L) |  | spl
44 | ASSET MAINT-13-14 Maintenance of C& F Block | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to the principal TDMC Alappuzha on 17/04/2013.(Rs 39.54 L) |  | spl
45 | ASSET MAINT-13-14 Renovation of old block I&II at MCH Vandanam. | GO(Rt) NO.2175/2013/H&FWD dt 21/06/2013 for Rs 205 Lakhs. | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | AS obtained. Estimate submitted to SE for TS on 28.02.2014. Tendered by SE. LMR submitted to SE. |  | spl
46 | ASSET MAINT-13-14 Urgent maintenance to the Medical College Building at TDMC Vandanam. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to the principal TDMC Alappuzha on 17/04/2013.(Rs 1.50 L) |  | spl
47 | ASSET MAINT-13-14 Urgent repair works to various students Hostel(6 Numbers) at TDMC Compound Vandanam. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to the principal TDMC Alappuzha on 17/04/2013. Rs 631 L) |  | spl
48 | ASSET MAINT-13-14 Urgent repair works to various Staff Quarters (10Numbers) at TDMC Compound Vandanam. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to the principal TDMC Alappuzha on 17/04/2013.(Rs 380 L) |  | spl
49 | ASSET MAINT-13-14 Maintenance of A&B Block | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate submitted to the principal TDMC Alappuzha on 22/04/2013.(Rs 36.37 L) |  | spl
50 | SCHOOL NURSING,ALAPPUZHA Renovation works of Kitchen Block | Order No. CE/BLDGS/ ALPY/2676/15 dtd. 31/03/15 for Rs. 9.99L | 06/EE/15-16 dtd. 20.04.15 for Rs. 9.99L | 24/EE/15-16 dtd. 26.11.2015 Sri. P.T.Sebastian | 969559/- 10% above 1066515/- | Nil | 3 months upto | Nil | Ambalapuzha | Work started
51 | Construction of a Maternity ward in Terrace floor of Jubilee building in Taluk Head Quarters Hospital, Cherthala | GO(Rt) No. 3292/2012/H&FWD dtd. 05.10.2012 for Rs. 130 L | 10/SEBSC/14-15 dtd. 29.08.14 for Rs. 130L | Sri. Roys John | Nil | Nil | Nil | Nil | Cherthala | Roof slab 1/3 rd casted |  | ctl
52 | General Hospital Alappuzha - Renovation works including Electrical and Plumbing work for improving the quality of hospital as per KASH | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Detailed estimate for Rs. 50L submitted to SE buildings, TVM through PRICE for AS. |  | spl
53 | Health & Family Welfare Department -Annual Plan 2014-15 Implementation of Plan Scheme - Strengthening of Institutions under DHS 13th FCA Trauma care - General Hospital, Alappuzha - Civil work of Trauma Care Unit | GO(Rt.) 2191/14/ H&FWdtd. 30.06.2014 for Rs. 28 L | 889/2015-16 dtd. 19/08/15 for Rs.28L (through PRICE) | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | T.S issued. Tendered with date as 07/09/2015. Lowest Tender recived from J&J Associates. To be submitted to SE for approval.
54 | W&C Hospital, Alappuzha Renovation work of W&C Hospital, Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | 35% work completed, Painting work in progress
55 | SC/ST DEPARTMENT Construction of Compound Wall, Sheet Roofing and other essential renovation works in MRS Alappuzha | GO(Rt.) 366/14/ SCSTDD dtd. 21.02.2014 for Rs. 230 L | 25/SEBSC/14-15 dtd. 27/11/14 for Rs. 230L | 21/SEBSC/15-16 dtd. 21/8/15 Sri Rashid .A Vahid | 22416341/- 23402660/- | 21/08/15 | 12 Months upto | 20.8.16 | Ambalapuzha | Work started. |  | alp
56 | I&PRD Construction of a building for District Intormation Office, Alappuzha | GO(Rt.) 146/15 I &PRD dtd. 24.03.15 for Rs. 25 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | A.S.obtained. To be tenderd. | A/.Sp | ctl
57 | Construction of building for Mini civil station Annex Cherthala. | GO(Rt) No. 350/11/PWD dt. 25.02.11 for Rs. 606L | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Proposal submitted with G+1 floor due to the lack of fund as suggested by CE. TS awaiting. Estimate submitted for new buildings in Rest House Compound for shifting Offices functioninig in the proposed site for Mini Civil Station Annex for T.S. |  | ctl
58 | Construction of Mini Civil Station at Mannar, Chengannur. | GO(Rt)No.965/13/PWD dt 09/07/13 for Rs 175 L | Nil | Harihara Kumar | Nil | Nil | Nil | Nil | Chengannur | T.S. obtained. Tender Sanctionobtained, Agt to be executed |  | chr
59 | Construction of Building for Aroor Police Station | GO(Rt.) No. 1184/09/PWD dtd. 14.08.09 for Rs. 125L | Nil | Nil | Nil | Nil | Nil | Nil | Aroor | Estimate submitted to CE on 23/08/2013 for Rs 455 L. Land to be identified. |  | ctl
AYURVEDA
60 | Construction of new building for Ayurveda Hospital at Chengannur Phase -I | GO(Rt) No.1818/2015/H&FWD dated 16.06.20154 for Rs. 24L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | AS obtained. Detailed estimate under preparation. Soil investigation Conducted.
PUBLIC HEALTH CENTER
61 | Construction of new building at PHC Cheppad, Alappuzha | GO(Rt) No.2980/2014/H&FWD dated 30.08.2014 for Rs. 100L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | AS obtained. To be tendered | 90 | hpd
ANIMAL HUSBANDARY
62 | Construction of Ground floor of Two Tier Building for Breeder shed at Puliyoor Village Campus of Central Hatchery, Chengannur | Order No. M2/93/62/2014/Plg dtd. 20.03.2014 of Director Animal Husbandary Dept. TVM for Rs. 50 L | 5/EE/14-15 dtd. 17.05.2014 for Rs. 50 L | 23/EE/14-15 dtd. 04.11.2014 Sri. Hariharakumar | 4549647/ 1.20% below/ 4495051 | Nil | 9 months | Nil | Chengannur | Work completd | 100 | chr
63 | Construction of First floor of Two Tier Building for Breeder shed at Puliyoor Village Campus of Central Hatchery, Chengannur | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | Estimate for Rs. 35 L to be submitted to SE through PRICE
64 | Construction of Two storied Brooder shed at Central Hatchery, Main campus, Chengannur | GO(Rt) No.567/15/AD 21.03.2015 for Rs. 78L | ALP/15-16 / 2015/1877 dtd. 29.07.15 forRs. 78L | 17/EE/15-16 dtd. 23.09.15 Sri.Vinod kumar M.R | 7694092 4.68% below 7334008/- | Nil | 12 months | Nil | Chengannur | Agreement executed. Work in progress.
65 | Providing sheet roof for existing building and repair works to ADCP office Alappuzha | GO(Rt) No.60/2014/AD dt 09.01.2014 for Rs. 10 L | 52/EE/13-14 dtd. 12.03.2014 for Rs. 10 L | 20/EE/14-15 dtd. 10/10/14 Berley Varghese | 999654 9% above 1087315/- | Nil | 3 months | Nil | Alappuzha | Agreement executed. Work can not be started yet, bottleneck-11 KV H T line |  | alp
VETERINARY
66 | Construction of new Building for veterinary Hospital Kattanam Alappuzha | Order No. M2/29756/2014/plg dtd. 24/10/2014 of Animal Husbandary TVPM. for Rs. 34L | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikara | AS obtained. Detailed estimate under Scrutiny. T.S to be issued and To be tendered
67 | Construction of new building for veterinary Hospital Kavalam Alappuzha | Order No. M2/35087/2014/plg dtd. 04/05/2015 of the Director of Animal Husbandary TVPM. for Rs. 35L | 1687/2015-16/20.11.15 , 35 L, thru price | Nil | Nil | Nil | Nil | Nil | Kuttanad | AS obtained. Detailed estimate under Scrutiny. T.S to be issued and To be tendered
68 | Construction of new building for veterinary Polyclinic, Chengannur, Alappuzha | Order No. M2/11045/2015/plg dtd. 29/05/2015 of the Director of Animal Husbandary TVPM. for Rs. 28L | 1679/2015-16/20.11.15 , 28 L, thru price | Nil | Nil | Nil | Nil | Nil | Chenganur | AS obtained. Detailed estimate under Scrutiny. T.S to be issued and To be tendered
69 | Construction of a quarters building 1 No. for veterinary surgeon at Muthukulam veterinery hospital | Order No. M2/29510/2013 of the Director Animal Husbandary Dept. for Rs. 29.5L | 40/EE/13-14 dt 27/01/14 for Rs 29.5 L | 2/EE/14-15 dtd. 02.07.2014 Sri. Vinod Kumar | 2773393 ER 2773393 | Nil | 6 months upto | Nil | Haripad | Work completted | 100 | hpd
70 | Modernisation of Vetinery Polyclinic, Cherthala, Alppuzha -Extension of small Animent Sugery block | Order No. M2/13804/2015/ Plg dtd. 12/08/15 of the Director Animal Husbandary Dept. for Rs. 19.2L | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Estimate fo be prepared. | 100
TREASURY
71 | Construction of new building for Sub Treasury Edathua (Balalnce work) | G.O(Rt)No.8519/05/Fin dt.2/12/05 for Rs.30 L | 20/SEBSE/05-06 dt 14/05/06 for Rs 34.5 L | 32/SEBSC/06-07 dtd. 09.03.07 Varghese Kannampally | 2423211 35% E/R 3087562 | 27.07.10 | 9 months upto 26-04-11 | 30.09.12 | Kuttanad | Held up due to dispute about the boundry of plot. Case pending in Munciff Court, Alappuzha. |  | alp
72 | Construction of Sub Treassury at Nooranadu | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikara | Estimate for Rs. 60L submitted to SE for A.S on 22/09/15 through PRICE.
SOCIAL JUSTICE DEPARTMENT
73 | Construction of building for Anganavadi No. 53 at Bharanicavu in Noornad Panchayath | GO(Rt) No. 99/2014/SJD dtd. 11.02.2014 for Rs. 8 L | 20/EE/14-15 dtd. 15.07.14 for Rs. 8L | 27/EE/14-15 dtd. 13.01.15 Rajan K | 793691 15% above 912745 | Nil | 3 months up to | Nil | Mavelikara | Completed | 100 | hpd
74 | Construction of building for Anganavadi No. 57 at Bharanicavu in Noornad Panchayath | GO(Rt) No. 99/2014/SJD dtd. 11.02.2014 for Rs. 8 L | 21/EE/14-15 dtd. 15.07.14 for Rs. 8L | 28/EE/14-15 dtd. 13.01.15 Rajan K | 793691 15% above 912745 | Nil | 3 months up to | Nil | Mavelikara | Completed | 100 | hpd
75 | Construction of building for Model Agnanavady No. 29 at Muthukulam (additional ) in Krishnapuram Gramapanchayat | Order No. ICDS/A7-29728/13 dtd. 31.12.2013 for Rs.20L | 49/EE/14-15 dtd.30.03.15 for Rs. 20L | 2/EE/15-16 dtd. 27.04.2015 Sri. S.Regunathan | 1860502 0.01 % below 1860316 | Nil | 6 months upto | Nil | Kayamkulam | Completed |  | hpd
76 | Construction of building for Model Agnanavady No. 89 at Avalukkunnu in Alappuzha Muncipality | Order No. ICDS/A7-29728/13 dtd. 31.12.2013 for Rs.20L | 18/EE/14-15 dtd. 07.07.2014 for Rs. 20 L | 03/EE/15-16 dtd. 04.05.15 Sri. Sajimon E.V | 1932196 34.43% above 2532168 | Nil | 6 months upto | Nil | Alappuzha | Agreement executed. |  | alp
77 | Construction of building for Model Agnanavady No. 11 at Veliyanadu in Kavalam Gramapanchayath | GO(Rt.) No. 485/2014/SJD dtd. 5.8.2014 for Rs. 11.66L | 1772/2015-16/26-11-15, 11.66 L | Nil | Nil | Nil | Nil | Nil | Kuttanad | AS obtained. Estimate under scrutiny. T.S to be issued and to be tendered. |  | alp
78 | Construction of building for Model Agnanavady No. 7 at Muthukulam (additional) in Devikulangara Gramapanchayath | GO(Rt.) No. 485/2014/SJD dtd. 5.8.2014 for Rs. 11.66L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | AS obtained. Dispute regarding land.Letter to Director, Social Justice Department |  | hpd
79 | Construction of building for Model Agnanavady No. 13 at Muthukulam (additional) in Devikulangara Gramapanchayath | GO(Rt.) No. 485/2014/SJD dtd. 5.8.2014 for Rs. 11.66L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | AS obtained. Dispute regarding land. Letter to Director, Social Justice Department |  | hpd
80 | Construction of building for Model Agnanavady No. 83 at Mararikulam South Gramapanchayath Near Railway gate Pathirappalli, Alappuzha. | GO(Rt.) No. 518/2013/SJD dtd. 17.10.2013 for Rs. 20L | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | AS obtained. Work tendered . No response. Quotation invited. No response.Re-Quotation invited . Quotation received from Sri.T.A Raphel. To be submitted to SE for approval |  | alp
81 | Construction building for Angnavadi No:114 at Muthukulam Grama Panchayath | GO(Rt.) No. 332/2015/SJD dtd. 05/06/2015 for Rs. 13L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | A.S. obtained. Estimate Under Preparation
82 | Construction of building for Agnavady Nol 86 in Kanjikkuzhy( instead of Agnavady No. 27 in Cherthalarth village. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Estimate to be prepared. No land
DEPOSIT WORKS
83 | Renovation works to the DTPC Office Building (3 Nos)near BoatJetty Aappuzha | Or No.P5/17607/2012 dt 22/10/12 for Rs 5 L | 14/EE/13-14 dt 28/05/13 for Rs 5L | 23/EE/13-14 dtd. 06.09.13 Sajimon.E.B | 497208 7.2% below 459660 | Nil | 3 Months up to |  | Alappuzha | Agreement executed. Fund not deposited by the concerned department. Not started. |  | spl
84 | Renovation works to the buildings situated in Andhakaranazhy Beech Pattanakkad Panchayath. | Order No.P5/17605/2012 dt 22/10/12 for Rs 7.67 L | 16/EE/13-14 dt 28/05/13 for Rs 7.67L | 20/EE/13-14 dt 23/08/13 Sri Naufal PM | 766960 9.3% below 704361 | Nil | 3 Months upto | Nil | Cherthala | Work stand still, because the roof work not done by the party who took the restaurant on lease as agreed. | 50 | ctl
85 | KMSCL-Renovation - work of Karunya Community Pharmcy outlet at Taluk Head Quarters Hospital, Haripad | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Estimate for Rs. 862007 forwarded to MD, KMSCL, TVM for AS. |  | hpd
86 | SWTD Alappuzha construction office cum workshp building at Ponjikkara, Alappuzha | Order No. A1-1306/13 dtd 15.04.13 of Director SWTD, Alappuzha for Rs. 100L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | AS obtained. Detailed estimate to be prepared. Architectural drawing outsourced, directed A EE to cancel the the work order and to tender the same |  | alp
87 | Construction of Way side Aminity Centre at Kayamkulam, Alappuzha | Order No. APAKL/015/2013 dtd. 31.03.2014 for 30 L | 1/EE/14-15 dtd. 2.4.2014 for 30 L | 16/EE/14-15 dtd. 12/8/14 Sri. C. Vinod Kumar | 2998518 0.1% below 2995520 | Nil | 6 months upto | Nil | Kayamkulam | Agreement executed. Work not started. |  | hpd
DIVISION WORK
88 | Special repairs to AEO Office Mavelikkara | CE/BLDGS/Alpy/1930/2013 dt 22/03/13 for Rs 8.35L | 6/EE/13-14 dt 27/04/13 for Rs 8.35 L | 15/EE/13-14 dt 27/05/13 P Unnikrishnan | 833837 3.76% below 808342 |  | 3 months upto | Nil | Mavelikkara | Completed | 100 | hpd
89 | Urgent Special repairs to Mini Civil Station Building at Kayamkulam | Order No.CE/BLDGS/ALPY/8689/2013 dt 30/10/2013 for Rs 10 Lacs. | 30/EE/13-14 dt 30/11/13 for Rs 10 Lacs. | 36/EE/13-14 dtd. 06.01.2014 Sunil Kumar.K.C | 996259 5.72% below 941169 | Nil | 3 months | Nil | Kayamkulam | Work in progress |  | hpd
90 | Strengthening Trauma Care unit in General Hospital Alappuzha | GO(Rt.) No. 41/87/13/H&FWD dtd. 18/12/2013 for Rs. 10L | 48/EE/13-14 dtd. 10.03.14 for Rs. 10L | 17/EE/14-15 dtd. 21.08.14 Sri. Saji. J | 699979 13.37% above 797066 | Nil | 3 months upto | Nil | Ambalappuzha | Agreement executed. Work started. |  | spl
91 | Special repair works to District TB Centre Alappuzha | Order No.CE/BL/ALPY /6535/2013 dt 30/12/13 for Rs 7 Lacs. | 49/EE/13-14 dtd. 10.03.14 for Rs. 7L | 22/EE/14-15 dtd. 25/10/14 Sri.Shaji.V | 699445 9.89% above 768620 | Nil | 3 months upto | Nil | Ambalappuzha | Nearing completion |  | spl
92 | Maintenance and repair of Poly technic college, Cherthala. | Order No. CE/BL/ALPY/440/20135 dt 09.02.2015 for Rs 999800/- | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Work tendered. No response. Retenderd on24.04.2015. Single tender received on Royees John at 25% above estimate rate. Approveal got from S E |  | ctl
93 | Urgent repairs to PWD Dock workshop Alappuzha | GO(Rt.) No. 541/2015/PWD dtd. 16.04.2015 for Rs. 27.70 L | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | A.S.obtained. Detailed estimate under preparation.
94 | Land development Land scaping and boundary wall raising at RDO Quarters, Alappuzha | OrderNo. CE/BL/ALPY/2193/15 dtd. 26.03.15 for Rs. 9.5L | 1/EE/15-16 dtd. 20.04.2015 for Rs. 9.5L | 10/EE/15-16 dtd. 04/08/15 Sri. P.T.Sebastian | 922511 8.22% above 998341/- | Nil | 3 months upto | Nil | Alappuzha | Complted
95 | Providing partition work of N.H.Division, Office at Civil Station Annex , 3rd floor, Alappuzha | OrderNo. CE/BL/ALPY/2194/15 dtd. 27.03.15 for Rs. 7.08L | 3/EE/15-16 dtd. 20.04.2015 for Rs. 7.08L | 11/EE/15-16 dtd. 04/08/15 Sri. P.T.Sebastian | 707717/- 4.47% 739352 | Nil | 3 months upto | Nil | Alappuzha | Complted
96 | Inaguration work providing partitiion , Cabin work etc in new subtreasury, Minicivil station, Cherthala. | OrderNo. A1/13732/2011 dtd. 09.01.15f of the Director of Treaslury for Rs. 8.5L | 44/EE/15-16 dtd. 25/02/15 for Rs. 8.5L | 16/EE/15-16 dtd. 23.09.2015 Sri.Royees John | 723129/- 15% above 831598 | Nil | 3 months upto | Nil | cherthala | Civil work completed, Electrical work pending
97 | Registration ofice complex, Alapupzha -Construction of vehicle shed and ,levelling the yard | OrderNo. CE/BL/ALPY/ 2674/ 2015/ td.31.03.15 for Rs. 6.52L | 5/EE/15-16 dtd. 20.04.2015 for Rs. 6.52L | 23/EE/15-16 dtd. 23.11.2015 Sri.D.Abraham | 642463 7.58% above 691162 | Nil | 3 months upto | Nil | Alappuzha | Agreement Executed
NABARD
98 | 4210-01-110-75 (RIDF XVI) Construction of New building for L.S. Noornad | G.O (Rt) No.1767/11/ H&FWD dt.6-5-11for Rs.392 L | 48/CE/BL/ 12-13 Dt: 23/6/12 for Rs: 392 Lakhs | 97/SEBSC/12-13 dt 01/01/13. N Vijayan | 37086671/6.9% above/ 39645651 | 41610 | 24 months upto 11/02/15 | Nil | Mavelikara | O.P.Block completed Male ward and Female ward not done due to disputed arised by the inmates of L.S.Nooranadu. Closure proposed | 20 | hpd
99 | 4210-03-110-75 (RIDF - XVII) Construction of Gallery type Lecture Theatre in Medical College , Alappuzha. | G.O (Rt) No.922/12/ H&FWD dt.19-3-12 for Rs.840 L | 83/CE/BL/ 2012-13 Dt: 29/9/12 for Rs: 840 Lakhs | 54/SEBSC/12-14 dtd.20.1.14 KSCC Ltd. | 70980436 27.75% above 90677507 | 10.03.2014 | 15 months upto 09.06.2015 | Nil | Ambalapuzha | Work upto Ist floor completed and Pillars for the Ist floor casted.Truss work in progress. Electrical work to be Completed. | 30 | spl
100 | 4210-03-110-75 (RIDF - XVII) Construction of Gallery type Auditorium in Medical College, Alappuzha. | G.O (Rt) No.922/12/ H&FWD dt.19-3-12 for Rs.700 L | 49/CE/Bldg/ 2012-13 Dt: 26/6/12 for Rs: 700L | 93/SEBSC/12-13 dt 24/12/12.J Abdul Vahid | 60678199 7.9% above/ 65465078 | 41277 | 18 Months upto 31/08/14 | Nil | Ambalapuzha | Structure completed. Roof work completed. Acustics works in progress. Finishing work in progress. | 30 | spl
101 | Construction of departmental block in IHRD Eng: college, Pallipuram, Cherthala.Phase-I | GO(Rt) No.1694/2012/H/Edn dt 07/08/12 for Rs 443L |  | 56/SEBSC/13-14 dt 23/01/14. Nasrudeen | 36759937 1.11% below 36351902 | 30.01.2014 | 15 months upto 29.04.2015 | Nil | Cherthala | Structure work completed. Work in progress. R E submitted for approval | 50 | ctl
102 | (RIDF XX) Construction of building for Govt. Model Boys Higher Secondary School, Haripad , Alappuzha. | GO(Rt) No.1014/2015/Gl.Edn dt 16.03.2015 for Rs 81.6L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | A.S. Obtained. Detailed estimate under scrutiny, to be tendered | 50 | ctl
103 | (RIDF XX) Construction of Hospital building, Haripad, Alappuzha | GO(Rt) No.856/2015/ H&FWD dt 12.03.2015 for Rs 8952L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | 3 Nos. Achitect qualified. Directed to submit conceptual design.
4105
10
LAC-ADF PROJECTS 2012-13
1.Aroor L.A Constituency - Sri.A.M.Areef MLA
104 | Construction of new building for GVVHSS, Kodamthuruthu, Cherthala | GO(Rt)No730/2013/G.Edn dated 15.02.13 for Rs60 Lakhs. | 43/EE/12-13 dt.25/3/13 for Rs.60 L | 32/EE/13-14 dt.02/12/13 Sri.George.E. Varghese | 5599927 18% above E/R 6310023 | 16.12.2013 | 15.09.2014 | Nil | Aroor | Work completed. | 100 | ctl
105 | Construction of a building for Laboratory and class room for T.H.S.S, Pallippuram, Cherthala | GO(Rt)No429/2013/G.Edn dated 21.03.13 for Rs60 Lakhs. | 8/EE/13-14 dt.29/4/13 for Rs.60 L | 46/EE/13-14 dt 17.03.2014 Sri. I.C. Tomychen | 5598765 41.54% above 7285264 | 27.03.14 | 9 months upto 26.09.2014 | Nil | Aroor | Work completed. | 100 | ctl
106 | Construction of class room for HSS Chandiroor, Cherthala | GO(Rt)No961/2013/G.Edn dated 27.02.13 for Rs60 Lakhs. | 44/EE/12-13 dt.25/3/13 for Rs.60 L | 11/EE/13-14 dt 18/05/13 Sri. George E Varghese | 5748979/ ER/ 5748979 | 27.08.2013 | 9 Months upto 26.05.2014 | Nil | Aroor | Work completed. | 100 | ctl
107 | Construction of adminstrative block including landscape in CHC Arookutty | GO(Rt)No881/2013/H &FWD dated 16.03.13 for Rs118 Lakhs. | 8/SEBSC/2013-14 dt 30/05/13 for Rs 118L | 55/SEBSE/2013-14 Sri.Geogre E. Varghese | 9594151 17.5% above 10870727 | 28.03.2014 | 9 Months upto 27.12.2014 | Nil | Aroor | Structure and masonry work completed.Finishing work in progress | 50 | ctl
II.Alappuzha Constituency (Sri.Dr.T.M.Thomas Issac MLA)
108 | Construction of new building for G S M M G H S S Kanjikuzhy | GO(Rt)No.746/2013/G.Edn dated 15.02.13 for Rs50 Lakhs. | 4/EE/13-14 dt.15/4/13 for Rs.50 L | 40/EE/13-14 dt 04.03.2014 K.K. Antony | 4674773 19% above estimate rate 5306339 | 30.10.2013 | 9 Months upto 29.07.2014 | Nil | Alappuzha | Work completed. | 100 | ctl
109 | Construction of new building for SDVJB School, Alappuzha | G.O (Rt) No.1060/2013/G.Edn. Dt.4/3/13 for Rs.50 L | 3/EE/13-14 dt.15/4/13 for Rs.50 L | 37/EE/13-14 dtd. 06.02.02014 T.A. Rafel | 4729546 30% above 5669604 | 25.02.2014 | 9 months upto 24.11.2014 | Nil | Alappuzha | Completed | 40 | alp
110 | Construction of new building for Govt. L.P School, Mararikulam | G.O (Rt) No.639/2013/G.Edn. Dt.12/2/13 for Rs.50 L | 5/EE/13-14 dt.15/4/13 for Rs.50 L | Nil | Nil | Nil | Nil | Nil | Alappuzha | SN issued. Agreement to be executed.School authority did not remove the foundation of the demolished building from the proposed site and hence the site couldnot be handed over to the contractor. Now the contractor has applied to release his EMD. Quotation invited on 04.02.2015. No response. Requotation invited on 26.02.15. No response. |  | ctl
111 | Construction of a building for Govt. H.S. Pollathai,Alappuzha | G.O (Rt) No.1113/2013/G.Edn. Dt.7/3/13 for Rs.50 L | 2/EE/13-14 dt.15/4/13 for Rs.50 L | 12/EE/13-14 dt 21/05/13 . Shahul Hameed Naina | 4727002/0.91% below /4697911 | 27.11.2013 | 9 Months upto 22.02.2014 | Nil | Alappuzha | Work completed. | 100 | alp
112 | Construction of stage and Open Air Auditorium for Govt HS. Kalavoor. | G.O (Rt) No.881/2013/G.Edn. Dt.22/2/13for Rs.30 L | 1/EE/13-14 dt.15/4/13 for Rs.30 L | 13/EE/13-14 dt 22/05/13 T.A. Abdul Latheef | 2698052/ 8.5% below /2533950 | Nil | 6 Months upto | Nil | Alappuzha | Work completed. Inagurated on 25.02.2014. | 100 | alp
III. Ambalappuzha L.A Constituency- Sri.G.Sudhakaran MLA
113 | Construction of building for Govt. Muhammadens Boys HSS Alappuzha | GO(Rt)No 644/2013/G.Edn dated 12.02.2013 for Rs 100 Lakhs. | 41/EE/12-13 dt.25/3/13 for Rs.100 L | 30/EE/13-14 dt 12.11.2013 P.T. Sebastian | 9619355 33.34% above 11711155 | 25.11.2013 | 12 Months upto 24.11.2014 | Nil | Ambalapuzha | Work completed. Inagurated | 100 | alp
114 | Construction of building for Govt.GHSS Alappuzha | GO(Rt)No 847/2013/G.Edn dated 21.02.2013 for Rs 100 Lakhs. | 42/EE/12-13 dt.25/3/13 for Rs.100 L | 31/EE/13-14 dt 12.11.2013 P.T. Sebastian | 9615572 27.9% above 11417714 | 25.11.2013 | 12 months up to 24.11.2014 | Nil | Ambalapuzha | Work completed. Inagurated | 100 | alp
115 | Constuction of new building for Govt. H.S. Paravoor | G.O.(Rt) No.1736/ 2013/G.Edn.dt 18/04/13 for Rs 100 L | 18/EE/13-14 dt. 10.6.13 for Rs. 100L | 25/EE/13-14 dtd. 10.9.13 P.Mohan das | 9548983 1.9% below 9422219 | 19.09.2013 | 12 months up to 18.09.2014 | Nil | Ambalapuzha | Work completed. Inagurated | 100 | alp
IV.Haripad L.A Constituency - Sri.Ramesh Chennithala MLA
116 | Construction of building for Govt. Boys HSS, Haripad | G.O (Rt) No.945/2013/G.Edn dt.27/2/13 for Rs.100 L | 39/EE/12-13 dt.25/3/13 for Rs.100 L | 3/EE/14-15 dt. 11.07.14 M. Ismail Kutty | 9144321 41% above1 1862033 | Nil | 12 months up to | Nil | Haripad | Finishing work in progress. |  | hpd
117 | Construction of building for Govt. CHC Muthukulam | G.O (Rt) No.715/2013/H&FWD dt.4/3/13 for Rs.100 L | 40/EE/12-13 dt.25/3/13 for Rs.100 L | 29/EE/13-14 dtd. 23/9/13 K.R.Harikumar | 9016133 18.25% above 10198030 | 03.10.2013 | 12 months up to 02.10.2014 | Nil | Haripad | Work completed. | 100 | hpd
118 | Construction of building for Govt. CHC Thrikkunnappuzha | G.O (Rt) No.980/2013/H&FWD dt.22/3/13 for Rs.75 L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Soil investigation report obtained. For 35 m pile. BSNL deposited 1 Crore to CHC and the work is started. Requested to wait after their completion. |  | hpd
119 | Construction of new building of Muthukulam Village office | G.O.(Rt) No.2054/13/RD dt 10/04/13 for Rs 25 L | 17/EE/13-14 dt 10/06/13 for Rs 29.5L | 38/EE/13-14 dtd. 18.02.14 P.S. Mathew | 2768575 19.32% above 3172215 | Nil | Nil | Nil | Haripad | Completed |  | hpd
120 | Construction of building for Govt. Polytechnic Haripad | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | Estimate for 125L. MLA sanction for 100L. Balance amount of Rs.25 L to be requested for getting
(V) .Kayamkulam L.A Constituency - Sri.C.K.Sadasivan MLA
121 | Construction of new block for Primary Health Centre Chettikulangara | G.O (Rt)No.900/2013/H&FWD dt.18/3/2013 for Rs.100 L | 10/EE/13-14 dt.29/4/13 for Rs.100 L | 09/EE/13-14 dt 10/05/13 N.Vijayan | 9616615/ ER /9616615 | 19.07.2013 | 12 Months upto 18.07.2014 | Nil | Kayamkulam | Structure completed. Finishing work in progress. | 85 | hpd
122 | Construction of Artificial Lake and providing additional facilities to museum cultural complex, Krishnapuram. | G.O (Rt)No.68/2013/CAD dt.20/2/2013 for Rs.300 L | 11/CE/BL/2013-14 dt 18/06/13 for Rs 300 L | Nil | Nil | Nil | Nil | Nil | Kayamkulam | Agreement executed |  | hpd
(VI) Mavelikkara L.A Constituency - Sri.R.Rajesh MLA
123 | Construction of new building for Community Health Centre Kurathikad. | G.O (Rt)No.937/2013/H&FWD dt.20/3/2013 for Rs.100 L | 11/EE/13-14 dt.29/4/13 for Rs.100 L | 14/EE/13-14 dt 24/05/13 M.R Chandrangathan | 9299830/ 0.5% below 9264058 | 03.07.13 | 12 Months upto 02.07.2014 | Nil | Mavelikkara | Finishing work in progress | 60 | hpd
(VII).Chengannur L.A.Constituency - Sri.P.C.Vishnunath MLA
124 | Construction of building for Govt. H.S.S Mulakkuzha, Chengannur. | G.O (Rt)No.1059/2013/G.Edn dt.4/3/2013 for Rs.100 L | 9/EE/13-14 dt.29/4/13 for Rs.100 L | 41/EE/13-14 dt 04.03.2014 Sri. Hameed Kunju | 9195327 44.22% above 11892971 | 23.07.2014 | 12 month upto 22.07.2015 | Nil | Chengannur | Site handedover. Termination proposal without risk &Cost. Submitted to Govt. |  | chr
125 | Construction of building for Govt. Higher Secondary School , Thiruvanvandoor | GO (Rt) No.1248/2013/G.Edn dt 16/03/13 for Rs 100 L | 7/EE/14-15 dtd. 19.05.2014 for Rs. 100 L | 31/EE/14-15 dtd.27.02.15 Sri.J. Manzoor | 9614692 13.9% above 10951134 | Nil | 12 month upto | Nil | Chengannur | Finishing work in progress |  | chr
126 | Construction of building for OP block CHC, Mannar | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | Estimate submitted to CE for Rs. 51 L on 20.11.2012 for AS., No scope for this work |  | chr
LAC-ADF PROJECTS-13-14
I.Aroor L.A Constituency - Sri.A.M.Areef MLA
127 | Construction of building for Govt UPS Arookutty. | GO(Rt) No. 1181/2014/G. Edn. Dtd. 04.03.14 for Rs. 54 L | 14/EE/14-15 dtd. 30.06.14 for Rs. 4890704/- | 14/EE/15-16 dtd.04.09.2015 Sri. P.N. Gopalakrishnan | 4890702 14.4% above 5594963/- |  | 6 months upto | Nil | Aroor | Work started |  | ctl
128 | Construction of new building for G.H.S.S Thirunelloor | G.O(Rt) No. 1136/2014/G.Edn dt. 03.03.2014 for Rs. 84.73L | 16/EE/14-15 dtd. 30.06.14 for Rs. 84.73 L | Nil | Nil | Nil | Nil | Nil | Aroor | S.N. Issued agreement to be executed |  | ctl
129 | Construction of new building for Anganavadi ( 5 Nos) - Anganavady (No.90) in Kuthiyathode Pt., Anganavady (No. 120, 130, 135) in Thuravoor Panchayath, Anganavady (No.21) in Pallippuram Panchayath | GO(Rt.) No.163/2014/SJD dtd. 05.03.2014 for Rs. 45L for 5 Anganvady | 15/EE/14-15 dtd. 30.06.14 for Rs. 45 L | Nil | Nil | Nil | Nil | Nil | Aroor | Tender received from Sri. Binnikuttan at 31.83% above E/R approved by Govt Tender Committee . But Contractor is not willing to execute the agreement at the approved rate. So retendered. But no response. Quotation invited. No response. Re -quotation to be invited. with date as 3/12/2015 |  | ctl
II.Cherthala L.A Constituency - Sri.P. Thilothaman MLA
130 | Construciton of Building for Govt, PHC Vettakkal | GO(Rt.) No.2276/2014/H&FWD dtd. 05.07.2014 for Rs. 40 L | 27/EE/14-15 dtd. 19.09.14 for Rs. 40 L | Nil | Nil | Nil | Nil | Nil | Cherthala | Tender received from Sri. Binnikuttan at 29.94% above E/R approved by Govt Tender Committee . But Contractor is not willing to execute the agreement at the approved rate. Dispute regarding Land. |  | ctl
131 | Construction of building for library cum reading room in Pattanackad Panchayath office compound | GO(Rt.) No.1468/2014/LSGD dtd. 10.06.2014 for Rs. 25 L. | 319/2015-16/26/6/15/ 25 L | Nil | Nil | Nil | Nil | Nil | Cherthala | AS obtained. Amount deposited by LSGD. Work tendered. No response.Retendered. No response. Quotation to be invited. No response. Re-quotation invited. As on 3/12/2015 |  | ctl
132 | Construction of administrative block for community heath centre Muhamma | GO(Rt.) No.1307/2013/H&FWD dtd. 10.04.2013 for Rs. 58.3 L. | 41/EE/14-15/28/1/15/ 58.3 L | Nil | Nil | Nil | Nil | Nil | Cherthala | Work tendered twice. No response. Quotation received from Sri. V.S.Sreekumar at 26.56% above E/R approved by Govt. Tender Committee. But firm period of the Quotation expired addressed to Contractor to extend the firm Period on 15.07.15. But no response. Quotation recieved from V S sreekumar cancelled. Requotation invited as on 8/12/15 |  | ctl
III.Alappuzha L.A Constituency - Sri..Dr. T.M. Thomas Issac MLA
133 | Construction of a new IP block at PHC Kalavoor | GO(Rt.) 3125/2014/H&FWD dtd. 22.09.14 for Rs. 32L | 34/EE/14-15 dtd. 31/10/14 for Rs. 35 L | Nil | Nil | Nil | Nil | Nil | Alappuzha | AS obtained. Tendered with date as 03.12.2014 No response. Retendered on 21.12.14 No response. Quotation invited two times. No response. The fact reported to CE for further direction. |  | alp
134 | Construction of a building for Govt. HS Mannanchery Alappuzha | GO(Rt) No. 1738/2014 G.Edn. Dtd. 06.05.2014 for Rs. 90 L | 25/EE/14-15 dtd. 18.08.2015 for Rs. 90 L | Nil | Nil | Nil | Nil | Nil | Alappuzha | AS obtained. Tendered on 12.11.2014. No Response. Retendered on 26.11.2014. No response. Quotation invited. No response. Requotation invited with date as 30/12/2014. No response. 3 rd quotation invited. No responseThe fact reported to CE for further direction. |  | alp
135 | Construction of class room for Govt. PJ LPS Kalavoor, Valavanadu | GO(Rt) No. 2602/ 2014/ G.Edn. Dtd. 02.07.2014 for Rs. 42 L | 28/EE/14-15 dtd. 26.09.14 for Rs. 42L | Nil | Nil | Nil | Nil | Nil | Alappuzha | AS obtained. Tendered on 12.11.2014. No Response. Retendered on 26.11.2014. No response. Quotation invited. No response. Requotation invited with date as 30/12/2014. No response. 3 rd quotation invited. No response. The fact reported to CE for further direction. Again requotation invited with dtd. as 04.08.15 as requested from MLA's Office. No response. |  | alp
136 | Construction of toilet block & private bus stand at Alappuzha | GO(Rt.)No. 2165/2014/ LSGD dtd. 21.08.2014 for Rs. 31.5L | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | AS obtained. Transmitted to LSGD as per the direction of CE. |  | alp
137 | Construciton of new Building for Buds School at Mararikulam | GO(Rt) No. 2603/ 2014/ G.Edn. Dtd. 02.07.2014 for Rs. 30 L | 29/EE/14-15 dtd.08.10.14 For Rs.30L | 09/EE/15-16 dtd. 25.07.15 Sri.V.Radhakrishanan | 2830177 41.02% above 3991116 | Nil | 6 months upto | Nil | Alappuzha | Work in progress |  | ctl
IV. Amabalapuzha L.A Constituency - Sri.G.Sudhakaran MLA
138 | Construction of stage and open air auditorium for Govt HS. Ambalappuzha | GO(Rt) No. 1323/ 2015/ G.Edn. Dtd. 31.02.2015 for Rs. 120 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalappuzha | Work tendered bt S E L M R submitted |  | alp
V. Kuttanadu L.A Constituency - Sri.Thomas Chandy MLA
139 | Construction of building for new block for KSRTC Bus stand Edathua | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kuttanad | Plan not yet approved by the client |  | alp
140 | Construction of building for Rest House, Pulinkunnu | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Kuttanad | Estimate prepared. But letter from MLA for the estimate amount not yet received. |  | alp
VI. Kayamkulam L.A Constituency - Sri. C.K. Sadasivan MLA
141 | Construction of a new building for Govt. B.H.S.S Kayamkulam | GO(Rt) 4707/13/Gedn dtd 06.11.2013 for Rs. 75 lakh | 44/EE/13-14 dt.04/2/14 for Rs.75 L | 21/EE/14-15 dtd. 15.10.14, Sri.Abdul Aziz | 7041815 35.46% above | Nil | 9 month upto | Nil | Kayamkulam | Agreement Executed. Work started. |  | hpd
142 | Construction of a new building for Govt. .H.S.S Ramapuram | G.O(Rt)No.4769/2013/G.Edn dt.06/11/2013 for Rs.75 L | 41/EE/13-14 dt.27.01.2014 for Rs.75 L | 24/EE/14-15 dtd. 13.11.14, Sri. C.Vinod kumar | 7041815 17% above | Nil | 9 month upto | Nil | Kayamkulam | Agreement Executed. Work started. Work in progress. Plinth beam completed. Column work started |  | hpd
VII. Mavelikkara L.A Constituency - Sri. R. Rajesh MLA
143 | Construction Office & Shopping Complex at Chunakkara Grama panchayath | G.O(Rt)No.593/2014/LSGD dt.28/02/2014 for Rs. 100 L | 2/EE/14-15 dtd. 05.04.14 for Rs. 100 L | Nil | Nil | Nil | Nil | Nil | Mavelikkara | AS obtained. Tendered on 08.07.2014. But no response. Retendered with date as 02.08.2014. No respose. Transmitted to LSGD as per the direction of CE. |  | hpd
144 | Construction Office & Shopping Complex at Padanilam Market in Noornadu Grama Panchayath | G.O(Rt)No.593/2014/LSGD dt.28/02/2014 for Rs. 100 L | 3/EE/14-15 dtd. 05.04.14 for Rs. 100 L | Nil | Nil | Nil | Nil | Nil | Mavelikkara | AS obtained. Tendered on 08.07.2014. But no response. Retendered with date as 02.08.2014. No response. Transmitted to LSGD as per the direction of CE. |  | hpd
145 | Construction of a new building for Ayurveda Clinic at Thamarakulam Grama Panchayath | G.O(Rt)No.2150/2014/LSGD dt.20/08/2014 for Rs. 25 L | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikkara | A.S obtained. Transmitted to LSGD as per the direction of CE. |  | hpd
146 | Construction of a new building for PHC Vallikunnam | G.O(Rt)No.1931/2014/H&FWD dt.11/06/2014 for Rs. 30 L | 31/EE/14-15 dtd. 8.10.14 Rs. 30L | 13/EE/15-16 dtd. 01.09.2015 Sri. C.Vinod kumar | 2784022 25.29% above 3488101 | Nil |  | Nil | Mavelikkara | work started, column footing completed |  | hpd
147 | Construction of a new building for Gramapanchayath Office, Thekkekara | G.O(Rt)No.1784/2014/LSGD dt.10/07/2014 for Rs. 70 L | 14/EE/15-16 dtd. 29.05.15 for Rs. 70L | 06/EE/15-16 dtd. 15.07.15 Sri. Liju.P.Rajan | 6866055 5.1% below E/R. 6515886/- | Nil | 15 months upto | Nil | Mavelikkara | work started, column work started |  | hpd
148 | Construction of a new building for Khadi Servodaya Sangam, Thekkekara Grama Panchayath | G.O (Rt)No.1226/2014/ID dt.1/11/2014 for Rs.25 L | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikkara | AS obtained. Requested to Industries department for depositing the amount of Rs. 25L to EE, Buildings, Alappuzha by CE vide Lr. No. CE/BL/PL1/LAC-ADS/ALPY/40/14 dtd. 13.02.15. Amount not deposited.T S to be issued |  | hpd
149 | Construction of a new building for Canteen & doormetry block at Govt. Hospital Mavelikara | GO(Rt.) No. 27/45/2014 H& F WD dtd. 12.8.14 for Rs. 67L | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikkara | As obtained. Work tendered twice. No response. Quotation invited. No response. Fact reported to MLA on 21.07.15. Re-quotation invited. No response. Quotation received from Sri. Liju.P.Rajan submitted to SE for approval. |  | hpd
150 | Construction of a new building for Panchakarma Centre at Thazhakkara Grama Pancayath | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Mavelikkara | Estimate submitted to CE on 02.01.2014 for Rs. 25 L |  | hpd
VIII. Chengannur L.A Constituency - Sri. P.C. Vishnunath MLA
151 | Construction of a building for Govt. H.S.S Budhanoor | G.O(Rt)No.2298/2014/G.Edn dt.11/06/2014 for Rs. 100 L | 33/EE/14-15 dtd.21.10.2014 for Rs. 100L | 04/EE/15-16 dtd. 02/06/15 Sri. M.A.Rajan | 9364506/- 17.5% above 11003295/- | Nil | 12 months upto | Nil | Chengannur | Work in progress. Nearing completion |  | chr
152 | Construction of a builidng for University Institute of Technology, Mannar | GO(Rt) No. 824/2014/H.Edn. Dtd. 26.04.2014 for Rs. 100 L | 22/EE/14-15 dtd. 21.07.14 for Rs. 100 L | 12/EE/15-16 dtd. 02/08/15 Sri. B. Sreekumar | 9599635 19.5% above 11476364/- | Nil | Nil | Nil | Chengannur | structure completed, masonry in progress |  | chr
153 | Construction of a builidng for Technical Higher Secondary School Puliyoor under IHRD | GO(Rt) No. 987/2014/H.Edn. Dtd. 22.05.2014 for Rs. 100 L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur | AS obtainedWork tendered on 17.06.15. No response.Retender on 02.07.15.Single tender received from M/s. .Aiswarya Constructions at 29% above E/R. Submitted to SE for approval. |  | chr
LAC-ADF PROJECTS-14-15
154 | Providing Aswas Public Aminities along the National Highway near the Kodamthuruthu Panchayath office, Cherthala | GO(Rt) No. 1505//2014/PWD. Dtd. 29.10.2014 for Rs. 100 L | 37/EE/14-15 dtd. 31.12.14 for Rs. 100L | 05/EE/15-16 dtd. 10.07.15 Sri. M.E. Abdul Salam | 9016120/- 27.13% above 11462193/- | Nil | 9 months upto | Nil | Aroor | Upto lintel level complted, fencing work in progress |  | ctl
155 | Costruction of class room, Auditorium and compound wall for GHS Aroor | GO(Rt) No. 1096/2015/G.Edn Dtd. 20.03.2015 for Rs. 117 L | Nil | Nil | Nil | Nil | Nil | Nil | Aroor | AS obtained.Estimate submitted to S E for T S on 30/11/2015 |  | ctl
II. Alappuzha Constituency (Sri.Dr.T.M.Thomas Issac MLA)
156 | Construction of a building for Sri. Chitra Maharaja Vilasam GUPS Poomkavu | G.O (Rt) No.5302/2014/G.Edn. Dt.28.11.2014 for Rs.50 L | 50/EE/14-15 dtd. 30.03.2015 for Rs. 50L | Nil | Nil | Nil | Nil | Nil | Alappuzha | A.S.Obtained. No response. Quotation invited on 26.06.15. Single quotation at 50% above E/R received from Sri. T.A Raphel. Submitted to SE for approval |  | alp
III. Ambalapuzha Constituency (Sri.G.Sudhakaran MLA)
157 | Construction of new building for GHSS Kakkazham, Alappuzha | G.O (Rt) No.5476/2014/G.Edn. Dt.08.12.2014 for Rs.153 L | Nil | Nil | Nil | Nil | Nil | Nil | Alappuzha | Tendered by S E |  | alp
IV. Haripad L.A Constituency - (Sri. Ramesh Chennithala MLA)
158 | Construction of New building for UIT, Karuvatta | GO(Rt) No. 2299/2015/ H.Edn Dtd. 04.09.2015 for Rs. 70 L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | A.S.Obtained. To be tendered.
LAC -ADS - 2015-16
I.Aroor L.A Constituency - Sri.A.M.Areef MLA
159 | Construction of Jomon Memorial Open air Stadium (Phase -I) in the campus of the college of Engineering, Cherthala under IHRD | GO(Rt) No. 1682/2015/ H&FWD . Dtd. 02.07.2015for Rs. 150 L | Nil | Nil | Nil | Nil | Nil | Nil | Aroor | A.S.Obtained. Detailed submitted to SE for T.S. on 06/08/2015 through PRICE.To be tendered. Returned the estimate by SE for correction. Forwarded to AEE for re-submission
II. Ambalapuzha Constituency (Sri.G.Sudhakaran MLA)
160 | Construction of new building for Govt. new L.P.School, Karoor Ambalapuzha | GO(Rt) No. 5361/2015/ G.Edn Dtd.16/11/15for Rs. 27 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate for T S TO BE SUBMITTED
161 | Construction of a new building for KKKPMHSS, Ambalapuzha | GO(Rt) No. 5360/2015/ G.Edn Dtd.16/11/15for Rs. 56.75 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate for T S TO BE SUBMITTED
162 | Construction of new building for Naluchira H.S. Thottappally. | GO(Rt) No. 4650/2015/G.Edn Dtd. 03.10.2015 for Rs. 96.5 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | A.S.Obtained. To be tendered.
163 | Construction of new building for Govt L.P.School Tottappally (Anandeswaram School) | GO(Rt) No. 3534/2015/G.Edn Dtd. 21.08.2015 for Rs. 27 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | A.S.Obtained. To be tendered.
164 | Construction of a new building for Govt. L.P.School Karoor Ambalappuzha | GO(Rt) No. 5361//15/G.Edn Dtd. 16.11.2015 for Rs. 27 L | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | A.S.Obtained. To be tendered.
165 | Construction of a new Buildg for SDV UPS Neerkunnam Amblappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate for Rs. 49.50L shmitted to CE Buildingd, Tvpm. Vide Lr. No. A5/1175/15 dtd.18/06/2015 for A.S
166 | Construction of Toilet block for Muhammedans Girls H.S.S Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate for Rs. 26.5L to be submitted to SE for A.S thorugh PRICE.
167 | Construction of toiilet block for fire and rescue station Alappuzha | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Ambalapuzha | Estimate for Rs. 15L to be submitted to SE for A.S thorugh PRICE.
III. Chengannur L.A Constituency - Sri. P.C. Vishnunath MLA
168 | Providing Public Amenity Center beside M.C Road at Hospital Jn. In chengannur Town in Alappuzha | GO(Rt) No. 1124/15/PWD Dtd. 31.07.2015 for Rs. 35 L | Nil | Nil | Nil | Nil | Nil | Nil | Chengannur
MP LADS
169 | Sri. VAYALAR RAVI, MP (RS) Construction of new building for Maternity Ward in Taluk Govt. Hospital Cherthala | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Cherthala | Amount alloted is not sufficient to meet the minimum requirement of Materinity Ward. Requested for additional funds to District Collector, Alappuzha vide Lr. No. A11/394/14 dtd. 26/03/2015 |  | ctl
170 | Sri. K.C VENUGOPAL MP Construction of Girls Friendly Toilet and Watch man room in ST Premetric Ladies Hostel, Maithara in Cherthala South Panchayath | Order No. 522/ 2014-15/ DPO/ALP/ MPLADS/KCV dtd. 24.11.2015 for Rs. 26 L | 1852/2015-16 dtd. 03/12/15 for Rs. 26 L through PRICE | Nil | Nil | Nil | 6 months upto | Nil | Cherthala | A.S obtained. T.S issued. Work Tendered with date as 14/12/15 and will be opened on 18/12/15
171 | Consruction of Thuravoor Thaluk Hospital buildings, Kuthiyathode Panchayat | Order No. 566/ 2015-16/ DPO/ALP/ MPLADS/KCV dtd. 02/12/15 for Rs. 53 L | Nil | Nil | Nil | Nil | 9 months | Nil | Cherthala | A.S.recevied on 04/12/15 will be Tendered on 08/12/15
172 | Dr. T.N. Seema MP (RS) Construction of waiting area with fixed chain infront of Mortuary at Govt. Hospital, Kayamkulam | No. 1123/2015-16/DPO/ALP/MPLADS/TN dtd. 02.09.2015 of District Collector, Alappuzha for 4 L | Nil | Nil | Nil | Nil | Nil | Nil | Haripad | A.S.obtained and forwarded to AEE, Haripad , WORK TENDERED
SDF MLA'S
173 | SDF FOR MLA'S Sri. LUDY LUIZ, MLA (Nominated LAC) Construction of new building for UIT Study Centre under Kerala University in Haripad | Order No. 26960/14/F4 dtd. 14.11.2014 of District Collector, Alappuzha for Rs. 30L | 35/EE/14-15 dtd. 12.11.14 for Rs. 30L | 29/EE/14-15 dtd. 17.01.15. Sri. P. Ravindran. | 2929113 1.26% below 289226 | Nil | Before 30.04.15. | Nil | Haripad | Work Completed | 100 | hpd
EXECUTIVE ENGINEER

## COURT COMPLEX (hidden)
KERALA PUBLIC WORKS DEPARTMENT
BUILDINGS DIVISION, ALAPPUZHA
9. Constructio and renovation of Court Complex -Present Status
Sl.No | Budget Page no.& item no | Budget Provisions in lakhs | LA Constituency | Division | Department | Name of Project | Head of Account | Estimate Amount | A.S No. Date & Amount | T.S No. Date & Amount | Date of Tender | Agt.No & Date | Name of Contractor | Tender Percentage | Est. PAC/Qtd Rate/ | Agreed. PAC | Period of Completion in months | SHO Date | Date of completion as per agreement | Date of extended completion, if any | Actual DOC | Present Stage | Physical Progress (%) | Stage of Electrification | Exp. Up to Current month | Amount requird up to this financial year | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | 35/19 |  | Haripad | Alappuzha | Home | Construction of Court Complex, Haripad Phase II | 4059-01-051-71 | 234L | G.O (Rt.) 3740/2013 Home dtd. 9/12/2013 for Rs. 234L | 4/SEJ/EKM/ 14-15 dt. 26.09.14 for Rs. 249L |  | 4/SEJ/EKM/ 15-16 dtd. 25.06.15 | Sri. Lalji. | 23.69% above | 22798042 | 28198898/- | 15 months | 3.102 | 02.03.17 |  |  | Column work in progress |  |  | 28696481
2 | 34/17 |  | Chengannur | Alappuzha | Home | Construction of five story building for court complex at Chengannur | 4059-60-051-98 | 51500000 | GO(Rt)No. 565/12/PWD dt.31.03.12 for Rs.515 L | 87(a)/CE/BL/ 2012-13 dt 26/03/13 for Rs 592L |  | 4/SEJ/EKM 2014-15 dtd. 01.08.14 | General Manager KSCC Ltd. TVM | 19% above E/R | 40973675 | 48758673 |  | 20.08.14 | 19.02.16 | Nil |  | 3rd Floor Roof completed. Column work of 4th floor in progress | 30 |  | 4616225 | 1383500000
3 | 34/18 |  | Kayamkulam | Alappuzha | Home | Construction of Court Complex, Kayamkulam | 4059-60-051-98 |  | Nil | Nil |  | Nil |  |  | Nil | Nil |  |  | Nil | Nil |  | Soil investigation report received. Architectural Drawing received. Structural Design received estimate under preparation.
EXECUTIVE ENGINEER

## PPP (hidden)
KERALA PUBLIC WORKS DEPARTMENT
BUILDINGS DIVISION, ALAPPUZHA
Review of Ashwas Public Amenities Kerala Limited (MD -APAKL)
Sl.No | Budget Page no.& item no | Budget Provisions in lakhs | LA Constituency | Division | Department | Name of Project | Head of Account | Estimate Amount | A.S No. Date & Amount | T.S No. Date & Amount | Date of Tender | Agt.No & Date | Name of Contractor | Tender Percentage | Est. PAC/Qtd Rate/ | Agreed. PAC | Period of Completion in months | SHO Date | Date of completion as per agreement | Date of extended completion, if any | Actual DOC | Present Stage | Physical Progress (%) | Stage of Electrification | Exp. Up to Current month | Amount requird up to this financial year | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 |  |  | Kayamkulam | Alappuzha | PPP | Construction of Way side Aminity Centre at Kayamkulam, Alappuzha |  | 3000000 | Order No. APAKL/015/2013 dtd. 31.03.2014 for 30 L | 1/EE/14-15 dtd. 2.4.2014 for 30 L |  | 16/EE/14-15 dtd. 12/8/14 | Sri. C. Vinod Kumar | 0.1% below | 2998518 | 2995520 | 6 months |  |  |  |  | Agreement executed. Work not started. Fund not yet received
2 |  |  | Aroor | Alappuzha | ppp | Providing Aswas Public Aminities along the National Highway near the Kodamthuruthu Panchayath office, Cherthala | 4849-60-051-77 | 9016120 | GO(Rt) No. 1505//2014/PWD. Dtd. 29.10.2014 for Rs. 100 L | 37/EE/14-15 dtd. 31.12.14 for Rs. 100L |  | 05/EE/15-16 dtd. 10.07.15 | Sri. M.E. Abdul Salam | 27.13% above | 9016120/- | 11462193/- | 9 months | 22/05/15 | 21/02/16 |  |  | Upto lintel level complted, fencing work in progress | 25 |  | 225268
3 |  |  | Chengannur | Alappuzha | ppp | Providing Public Amenity Center beside M.C Road at Hospital Jn. In chengannur Town in Alappuzha |  | 3500000 | GO(Rt) No. 1124/15/PWD Dtd. 31.07.2015 for Rs. 35 L | Nil |  | Nil |  |  | Nil | [6 empty] | Tendered Lowest tender received from M.A.Vijayan @4% above E/R. To be submitted to SE for approval
EXECUTIVE ENGINEER

## Sheet3 (hidden)
Sl.No | Budget Page no.& item no | Budget Provisions in lakhs | LA Constituency | Division | Department | Name of Project | Head of Account | Estimate Amount | A.S No. Date & Amount | T.S No. Date & Amount | Date of Tender | Agt.No & Date | Name of Contractor | Tender Percentage | Est. PAC/Qtd Rate/ | Agreed. PAC | Period of Completion in months | SHO Date | Date of completion as per agreement | Date of extended completion, if any | Actual DOC | Present Stage | Physical Progress (%) | Stage of Electrification | Exp. Up to Current month | Amount requird up to this financial year | Remarks

## Sheet4 (hidden)
Sl.No | Name of work | Budget Page no.& item no | A.S No. Date & Amount | T.S No. Date & Amount | Agt.No & Date Name of Contractor | Est. PAC/Qtd Rate/ Agreed. PAC | Date of commencement | Date of completion as per agreement | Date of extended completion, if any | Name of Constituency | Present Stage | Physical Progress (%)

## CSSA (hidden)
KERALA PUBLIC WORKS DEPARTMENT
BUILDINGS DIVISION, ALAPPUZHA
PROGRESS REPORT CSSA WORKS AS ON 15.04.2016
Sl.No | Budget Page no.& item no | Budget Provisions in lakhs | LA Constituency | Division | Department | Name of Project | Head of Account | Estimate Amount | A.S No. Date & Amount | T.S No. Date & Amount | Date of Tender | Agt.No & Date | Name of Contractor | Tender Percentage | Est. PAC/Qtd Rate/ | Agreed. PAC | Period of Completion in months | SHO Date | Date of completion as per agreement | Date of extended completion, if any | Actual DOC | Present Stage | Physical Progress (%) | Stage of Electrification | Exp. Up to Current month | Amount requird up to this financial year | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
1 | 34/17 | Nil | Chengannur | Alappuzha | Home | Construction of five story building for court complex at Chengannur | 4059-60-051-98 | 51500000 | GO(Rt)No. 565/12/PWD dt.31.03.12 for Rs.515 L | 87(a)/CE/BL/ 2012-13 dt 26/03/13 for Rs 592L | 25.07.2013 | 4/SEJ/EKM 2014-15 dtd. 01.08.14 | General Manager KSCC Ltd. TVM | 19% above E/R | 40973675 | 48758673 | 18 month | 20.08.14 | 19.02.16 | Nil | Not completed | Finishing work in progress. | 85 | Detailed Estimate submitted to CEE. RS 150 L No space for Electric room, fire sump, Alteration in Lift shaft is required for providing 13 passenger Lift | 18492914 | 15000000 | On going
2 | Nil | Nil | Alappuzha | Alappuzha | Judiciary | ADMINISTRATION OF JUSTICE Construction of compound wall forAblock building in Court complex Alappuzha | 4059-60-051-98 | 287 L | GO(Rt)No.1243/08/Home dt. 18-4-08 for Rs.250 L of Home (24.00 L) | 40/CE/BLW/09/10 dt 24/07/09 for Rs 287 L(Part T/S) |  | 6/SEJ/EKM/11-12 dt. 02.12.11 | B Harikrishnan | 23.4% above | 2627360/ | 3163437 | 15 months upto | 09.12.2011 | 6 months upto 08.06.12 | 31.05.15 |  | Work completed | 100 |  | 3537157
EXECUTIVE ENGINEER

## NBD
KERALA PUBLIC WORKS DEPARTMENT
ROADS DIVISION KASARAGOD
PROGRESS FOR THE MONTH OF OCTOBER 2017
Sl.No | Budget Page no.& item no | Budget Provisions in lakhs | LA Constituency | Name of Project | Estimate Amount | A.S No. Date & Amount | T.S No. Date & Amount | Agt.No & Date | Name of Contractor | Estimate PAC | Agreed. PAC | Period of Completion in months | Date of site handing over | Date of completion as per agreement | Extended date of completion | Actual DOC | Present Status of works | Physical Progress (%) | Exp. Up to Current month | Amount requird up to this financial year | Remarks
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 22 | 23 | 24
I | BUDGET WORKS
2015-16
1 |  |  |  | Improvements to Edathodu - Neeleshwaram Road Km 15/500 to 8/300 | 300 | G.O. (Rt) No. 1930/2015/PWD dated, 22/12/2015 | [10 empty] | Estimate submitted for TS.Nomenclature of work(Chainage) to be changed
2 |  |  |  | Thekkil - Alatty Road 1st Phase | 400 | G.O. (Rt) No. 1930/2015/PWD dated, 22/12/2015 | 170/2015-16 dtd.15/02/2016 | SE(K)371/15-16 dtd.4/3/2016 | Sri.K.Moideenkutty Haji, PWD contractor, Pattuvathil , P.O.Thekkil |  | 35058353 |  | 2016-03-04 | 2017-03-03 |  |  | Completed | 100%
3 |  |  |  | Improvements to Hosdurg-Panathur road(SH)Km 15/000 to 44/175(Ist reach) | 1500 | G.O. (Rt) No. 183/2016/PWD dated, 28/01/2016 | 444/16-17 Dtd :23/07/2016 | SE(K)11/17-18 dtd.25/5/2017 | M/s Kudroli Construction company |  | 116659938 |  | 2017-05-25 | 2018-01-24 |  |  | Initial level taken
2016-17
1 |  |  | Kanhangad | Improvements to Kanhangad Guruvanam Mekkatta Road b/w km 0/000 to 1/900 | 194 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 3709/2016-2017 dtd:25/03/2017 | SE(K)131/17-18 dtd.29/07/2017 | Sri.Rajes varkey PWD Contractor Karimpanakal(h) Plachikkara(P.O) | 19216540 | 17659999 |  | 2017-08-01 |  |  |  | Work in progress
2 |  |  | Kasaragod | Improvements to Neerchal - Kottakani Madhur Road km 0/000 to 5/500(excluding kottakani bridge approach road) | 95 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 4296/2016-2017 dtd:31/3/2017 | SE(K)174/17-18 dtd.24/08/2017 | Sri.Azeez.P.K Pallikkandam(H) Peradala (PO) Badiyaduka | 9498892 | 9395619 | 9 | 2017-08-24 | 2018-05-23 |  |  | Agmt executed
3 |  |  | Thrikkaripur | Improvements to Chittarikkal Kunnumkai Road 1st phase b/w km 0/000 to 1/600 | 130 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 3726/2016-2017 dtd:25/03/2017 | SE(K)130/17-18 dtd.29/07/2017 | Sri.Rajes varkey PWD Contractor Karimpanakal(h) Plachikkara(P.O) |  | 11491961 | [5 empty] | Agmt executed
4 |  |  | Udma | Improvements to Bevinja Aloor Eriyanni Road(last reach)from km 13/900 to 18/200 | 48 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 |  |  | M.S.Mohammed Rafeeq Masthikundu P.O.Muliyar | 4799959 | 5063748.02 | [5 empty] | Agmt to be executed
5 |  |  | Udma | Improvements to Bandadukka Charnakochi Payaradukka Road km 0/000 to 3/000 | 48 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 2826/2016-2017 dtd:28/02/2017 | EE/KSD/15/17-18 dtd.29/05/2017 | M.S.Mohammed Rafeeq Masthikundu P.O.Muliyar |  | 3844887 | 9 | 2017-05-29 | 208/02/2018 |  |  | work in progress
6 |  |  | Udma | Providing BM & BC to Udma Thekkil Road from km 0/000 to 3/500 | 280 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 3781/2016-2017 dtd:27/03/2017 | SE(K)132/17-18 dtd.29/07/2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 27944071 | 23496874 | [5 empty] | work in progress
7 |  |  | Udma | Improvements to Pallathur-Adoor-Pandi road km 0/000 to 9/350 1st phase (0/000 to 3/600) | 283 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4271/2016-2017dtd:31/03/2017 | SE(K)128/17-18 dtd.29/07/2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 28171737 | 22940573 | 9 Months | 2017-08-03 | 2018-05-02 |  |  | Initial Level Reported
8 |  |  | Kasaragod | Providing BM & BC to Madhur-Patla-Kolangana road km 0/000 to 3/000 | 95 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 3781/2016-2017 dtd:27/03/2017 | [9 empty] | Initial Level Reported
9 |  |  | Kasaragod | Providing BM & BC to Perumbalakadavu-Nayanmarmoola-Erappakatta road km (1st reach) | 188 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [10 empty] | TS Approved
10 |  |  | Kasaragod | Provding BM & BC to Pannikkunnu-Shiribagilu road km 0/000 to 3/000 | 188 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [10 empty] | Submitted to ce for tender approval
11 |  |  | Kasaragod | Improvements to Kasaragod-Madhur road km 3/000 to 6/450 (BM &BC) | 188 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 185/2017-2018 dtd:29/04/2017 | SE(K) 80/17-18 Dtd:04/07/17 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 18794799 | 15331462 | [5 empty] | Agmt executed
12 |  |  | Manjeshwar | BM & BC to Permuda Dharmathaduka Bayarpadavu road 1st reach km 0/000 to 3/450 | 228 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 992/2017-18 Dtd:21/05/2017 | SE(K) 154/17-18 Dtd:11/08/17 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 22676268 | 22636598 | 6 Months | 2017-08-16 | 2018-02-15 |  |  | Initial Level Reported
13 |  |  | Manjeshwar | BM & BC to Dharmathadka-Kaniyala-Beloor-Beripadavu road km 0/000 to 7/400 | 350 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4274/16-17 Dtd:31/3/17 | SE(K) 47/17-18 Dtd:24/06/17 | M.A.Ameer Munabath Cengala | 34811953 | 34270450 | 9 Months | 2017-03-05 | 2018-04-04 |  |  | Initial level Taken
14 |  |  | Kanhangad | Improvements to Nedumbu-Mavinakadayagayam roa din Kinanoor-Karinthalam GP | 95 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4294/16-17 Dtd:31/3/17 | SE(K) 22/17-18 Dtd:03/06/17 | Noufal P M Puthiyadukkam Chattanchal P O Thekkil |  |  |  | 17-06-17 |  |  |  | Initial levels reported
15 |  |  | Uduma | Improvements to Kottikulan Thachamgad road between 1/200 to 3/200 | 192 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [10 empty] | Submitted for TS
16 |  |  | Trikripur | Improvements to Chimeni Kunnumkai road by providing BM BC 0/000 to 1/100 | 132 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4254/2016-2017 dtd:31/03/2017 | SE(K) 129/17-18 Dtd:29/07/17 | Sri.Rajes varkey PWD Contractor Karimpanakal(h) Plachikkara(P.O) |  | 11376528 | [5 empty] | Initial levels reported
17 |  |  | Trikripur | 2016/8761-Improvements to Parakole-Kinavoor-Kanyala-Palayi-Chathamath-Kariyamkode road km 7/000 to 12/000 | 176 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 993/2017-2018 Dtd:21/05/2017 | [9 empty] | RetenderedSelection notice to be issued .
18 |  |  | Trikripur | Improvements to Kakadavu Badoor-Kambaloor-Cherupuzha road - West eleri & East Eleri GP | 126 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [10 empty] | MLA reguested for substitution
2017-18
1 |  |  | Manjeswaram | Surface renewal to Ubbathody-Cheppinadukka-Naikap Road from km 4/000 to 5/000 | 13.5 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
2 |  |  | Manjeswaram | Improvements to Majirpalla-Boddodi-Koottathaje Road from km 2/200 to 3/200 | 30 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
3 |  |  | Manjeswaram | Improvements to Majirpalla-Boddodi-Koottathaje Road from km 1/200 to 2/200 | 30 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
4 |  |  | Manjeswaram | Improvements to Kallije Komangala Kurudapadavu Road from 1/800 to 3/500 | 50 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
5 |  |  | Kasaragod | Surface renewal to Nekrampara-Arladka-Pundoor-Nerampady-Yethadka Road km 5/800 to 9/000 | 40 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
6 |  |  | Thrikkaripur | Improvements to Pothamkandam-Anapettipoyil-Padiyottchal Road | 75 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
7 |  |  | Udma | Improvements to Thekkil-Seezhoor road at km 4/000 to 6/200 (From Delijunction to Melparamba town) | 180 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017 | [10 empty] | DPR Under Preparation
II | NABARD
1 |  |  |  | RIDF XXI - Reconstruction of Kottekanni bridge at (Korathikundu) including approach road on Neerchal-Kottakanni-Madhur road in Kasaragod District | R 715.00 | G.O. (Rt) No. 1962/15 /PWD dt. 30-12-2015 Item No. 6 (Bridges) | 244/2016-17 Dtd:03/06/2016 | SE(K)154/2016-17 Dtd:20/09/201625/05/2017 | Sri.M.A.Ameer, PWD contractor, Munambath House | 71499022 | 53356353 |  | 24.9.2014 | 18 |  |  | Approach Road work in progress | 94%
2 |  |  |  | Providing BM&BC to old MCC road km from 16/800 to 23/200, Bengara-Manjeshwar -Kuloor road 0/000 to 8/020 and Meeyapadavu-Chigurpade road km 0/000 to 1/5000 in Kasaragod District | R 900.00 | G.O. (Rt) No. 1962/15 /PWD dt. 30-12-2015 Item No. 10 (Bridges) | 416/2016-17 Dtd:15/07/2016 | SE(K)12/2017-18 Dtd:25/05/2017 | KUDROLI CONSTRUCTIONS CO. (P) LTD., 16A KURTARKAR COMMERCIAL, ARCADE 2ND FLR., KAZIWADA PONDA,GOA | 87247818 | 72923966 |  | 3.6.2017 | 6 |  |  | Concrete work in progress. Part initial levels reported to CTE. | 10%
3 |  |  |  | RIDF-XXII Improvments to Pallathinkal-AnjankukkodKottodi bridge road | R 300.00 | /G.O.(Rt.) No.1608/2016/PWD dt.23/11/2016 Item No.29 - | 3940/2016-17 Dtd:29/03/2017 | SE(K)133/2017-18 Dtd:29/07/2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 28953425 | 21903470 |  | 02-08-17 | 01-04-2018 |  |  | TS issued. Work to be tendered
4 |  |  |  | Construction Mullacheri bridge in Uduma-Mullachery road | R 300.00 | /G.O.(Rt.) No.1608/2016/PWD dt.23/11/2016 Item No.33 - |  |  | Sri. M.S. Abdul Hakeem, Civil work Contractor, Quodriya Manzil, Chengala P.O. |  | 22117755 |  | 11.10.2017 | 10.09.2018 | 12 |  | Work tendered
III | KIIF-B
2016-17
Road work
1 | Sl. No. 20-Budget Speech |  |  | Improvements to Hosdurg-Panathur road by providing BM and BC from Km 24/000 to 42/00 in Kasaragod District |  | Go(Rt) No 1192/2016/PWD dated 20.08.2016 | [10 empty] | Govt. directed to kept in abeyance
2 | Sl. No. 39-Budget speech |  |  | Improvements to Kayyur-Chembranganam-Palakkunnu road Km 0/000 to 10/900 and Link road 1.135 Km (Total 12.035 Km) in Kasaragod district |  | Go(Rt) No 1192/2016/PWD dated 20.08.2016 | 2388/16-17 dtd 17.12.2016 Rs. 6,00,000 | EE/KSD/122/16-17 dtd 14.3.17 | Smt. Ruby Soft tech, Tvm. | 551170 | 551170 | 2 | 15.3.2017 | 14.5.2017 |  | 13.5.2017 | Investigation work Completed. DPR under preparation
3 | (Sl. No. 21-Budget Speech |  |  | Improvements to Nileshwar-Edathodu road Km 0/000 to 13/000 in Kasaragod district |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | 2387 /16-17 dtd 17.12.2016 | EE/KSD/123/16-17 dtd 14.3.17 | Smt. Ruby Soft tech, Tvm. | 589819 | 589819 | 2 | 15.3.2017 | 14.5.2017 |  | 14.5.2017 | Investigation work Completed. DPR under preparation
4 | (Sl. No 13-Budget Speech |  |  | Improvements to Thekkil-alatty road Km 0/000 to 34/700 in Kasaragod District ) |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [10 empty] | DPR Submitted
5 | Sl.No. 3-Reply Speech |  |  | Improvements to Kiliyalam-Varanhoor road |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [10 empty] | Investigation work Completed. DPR under preparation
6 | (Sl. No. 34-Reply Speech |  |  | Improvements to Kalladka-Perla-Ukkinadka road Km 23/227 to 33/000 in Kasaragod District ) |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [10 empty] | DPR Submitted
7 | Sl. No. 35-Reply Speech |  |  | Improvements to Kalladka-Cherkala road Km 33/000 to 52/194 in Kasaragod district |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [10 empty] | Investigation work Completed. DPR under preparation
8 | Sl. No. 36-Reply Speech |  |  | Improvements to Cheruvathur – Cheemeni – IT Park – Palavayal – Bheemanady – Mukkada Road Km 0/000 to 54/000 in Kasaragod Dist. |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [10 empty] | Investigation work Completed. DPR under preparation
Bridge Work
9 | (Sl. NO. 61-Budget speech |  |  | Odankallu Bridge ) |  | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | [10 empty] | DPRsubmitted for TS
10 | Sl. No. 62- Budget speech |  |  | Puligochal-Kiltakayam Bridge | 10 | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | 2362/16-17 Dtd:16/12/2016 Rs/-7.10 | EE/KSD/109/16-17 Dtd:24/01/17 | Safe matrix Architectural&Engineering Consultant India Private Lmtd |  | 526027 |  | 02-02-2017 | 01-04-2017 | 20-04-2017 | 18-04-2017 | Investigation work Completed
11 | (Sl. No. 63- Budget speech |  |  | Klayikode-Ramanchira Bridge(InvestigationWork) | 1000 | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | [10 empty] | Investigation work Completed
12 | Sl. No. 7- Replyt speech |  |  | Bheemanady Kalikadavu Bridge(InvestigationWork) | 1000 | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | 2386/16-17 Dtd:17/12/2016 Rs/-6.60 | EE/KSD/110/16-17 Dtd:24/01/17 | Safe matrix Architectural&Engineering Consultant India Private Lmtd |  | 484434 |  | 02-02-2017 | 01-04-2017 | 20-04-2017 | 18-04-2017 | Investigation work Completed
2017-18
Road work
1 | Para 156 (Sl.No 9) |  | Trikaripur | Nileshwaram NH- Kacheriradav- Town- Byepass Road and bridge- Raja road improvement | 4000 | [11 empty] | Investigation submitted
2 | SL no 13 Of GO(Rt) 942/2017/PWD dated 10.07.2017 (not in budget speech) |  | Uduma | Bovikkanam - Kanathoor - Kuttikole Road | 1500 | [11 empty] | Investigation Estimate Tendered for Rs. 4.7 Lakhs
3 | Para 156 (Sl.No 35) |  | Kanhangad | Padnnakkad over bridge- Vellarikundu road ( including bridges) | 6000 | [11 empty] | Investigation submitted
4 | Sl no . 37 |  | Kasaragod | Badiadka - Yathadka - Soolyapadhavu Road km 0/000 to 20/000 | 2800 | Go(Rt) No 942/2017/PWD dated 10-07-2017 | 2440/17-18 Dtd:28-09-2017 Rs/-818000 |  | Sri.D.M Ahammed Deshamangalam(H) Badiradka(PO) Kudlu | 816930 | 858594.03 | 1 |  |  |  |  | Investigation Submitted
5 | Sl no . 53 |  | Manjeswaram | Maskumari- Kurudapadavu Road | 1000 | [11 empty] | Investigation Submitted
6 | Sl No: 98 |  | Manjeswaram | Construction of Valaiyapalam & rennovation of Kuloor Chinnala Road | 1500 | [11 empty] | Investigation Submitted
7 | Sl no 132 |  | Kasaragod | Nekrampara -Arladka - Pundoor -Narampady - Yathadka road km 0/000 to 11/600 | 1500 | Go(Rt) No 942/2017/PWD dated 10-07-2017 | 2433/17-18 Dtd:28-09-2017 Rs/-561000 |  | Sri.D.M Ahammed Deshamangalam (H) Badiradka (PO) Kudlu | 560517 | 569877.67 | 1 |  |  |  |  | Investigation Submitted
8 | Para 156 (Sl.No 171) |  | Kanhangad | Rakkole- Ennappara road | 2000 | [11 empty] | Investigation tender date 02-11-17
9 | Para 156 (Sl.No 172) |  | Kanhangad | Mekkatt- Errikkulam road. | 1500 | [11 empty] | Investigation tender date 02-11-17
10 | Para 156 (Sl.No 35) |  | Kanhangad | Padnnakkad over bridge- Vellarikundu road ( including bridges) | 6000 | [11 empty] | Investigation Submitted
Bridge Work
11 | Para 157,Sl No 23 |  | Udma | Construction of Chotta Bridge across Payaswini river in Muliyar Panchayath | 1500
12 | Para 157 (Sl.No 30) |  | Kanhangad | Kanhangad Fly Over | 4000
13 | PARA 157,Sl No 33 |  | Kasargode | Construction of Bajpekadavu (Kubanoor) Bridge in manjeswar LAC | 1000
4 | MLA ADS
1 |  |  | Trikkaripur | LAC- Asset Development Sceme - 2014-15 Trikaripur LAC - Improvements to Mayicha-Kuttivayal-Poraik road km 0/000 to 0/500 in Kasaragod District | 15 | G.O. (Rt) No. 1847/2015/LSGD dated 20/06/15 Rs. 15 akhs | 371/16-17 dt.24/06/2016 Rs-15 | EE/KSD/23/16 dt.18/08/2016 | Muhammed Hazeem, Mangad Udma |  | 1242242 |  | 2016-08-18 | 2016-12-17 |  |  | Earth work , side protection in progress | 30%
2 |  |  | Kanhangad | Improvements to Thayelenkurunhi - Kappithottam Road KM 0/130 to 0/630 | 20 | G.O. (Rt) No. 3348/2015/LSGD dated 13/11/15 20 Lakhs | 1925/16-17 Dtd: 18/10/2016 | EE/KSD/104/16-17 Dtd:16/01/2017 | sri.Reji Joseph Kollamparambil House Malakkallu P O |  | 1553427 |  | 2017-01-16 | 2017-04-15 |  |  | Initial level approved
3 |  |  | Kanhangad | Improvements to Vetradi - Koliampara Road Km 0/000 to 1/200 | 25 | G.O. (Rt) No. 3348/2015/LSGD dated 13/11/15 25 Lakhs | 2121/16-17 Dtd: 04/11/2016 | EE/KSD/105/16-17 dtd.17/01/2017 | sri.M S Mohammed Rafique PWD Contractor Muliyar PO | 2261753 | 1874634 | 3 | 2017-01-17 | 2017-04-16 |  |  | Earth work completed, GSb Work in progress | 45
4 |  |  | Trikkaripur | Improvements to Veethukunnu-Ring road Km 0/000 to 0/650 in Pilicode Grama Panchayath | 25 | G.O. (Rt) No. 439/2016/LSGD dated 3/2/2016 25 Lakhs | 2138/16-17 dt.5/11/2016 | EE/KSD/84/16-17 dtd.26/12/2016 | Sri.E.Raveendran, PWD Contractor, Onakkunnu, Karivellur P.O, Kannur | 2315993 | 1848309 | 6 | 2016-12-26 | 2017-06-25 |  |  | Earth work completed, GSb Work in progress | 20%
5 |  |  | Kasaragod | Improvements to Churipallam-Mavinakkatta road Km 1/700 to 3/200 | 50 | G.O. (Rt) No. 399/2016/PWD/Tvm dated 18/2/2016 50 Lakhs | [10 empty] | Revised estimate submitted for 32.28 lakh from km 0/000 to 0/500
6 |  |  | Kanhangad | Improvements to Kakkod-Kondapadi-Chimmathode road Km 0/000 to 2/750 in Kinanoor-Karindalam Grama panchayath | 25 | G.O. (Rt) No. 817/2016/LSGD dated 25/02/16 25 Lakhs | 1201/17-18 Dtd:23/06/2017 | EE/KSD/35/17-18dt.10/08/2017 | V V Manojan PWD Contractor Nileshwaram |  | 2212458 | 6 | 2017-08-10 | 2018-01-09 |  |  | Initial levels reported
7 |  |  | Kanhangad | Improvements to Chamundikunnu-Kizhakkethumbodi road Km 0/518 to 1/33o in Panathadi Grama Panchayath | 30 | G.O. (Rt) No. 817/2016/LSGD dated 25/02/16 30 Lakhs | 572/2017-18 Dtd:9/05/2017 | EE/KSD/30/17-18dt. | Mohammed Sakkeer PWD Contractor Bevinja |  | 2407601 | 6 |  |  |  |  | Initial levels taken
8 |  |  | Kanhangad | Ottakolly-ManchuchalKani road Km 3/500 to 3/850 in Balal Grama Panchayat | 15 | G.O. (Rt) No. 817/2016/LSGD dated 25/02/16 15 Lakhs |  |  | Shaiby Sebastian PWD Contractor | [7 empty] | Intial Level Taken
9 |  |  | Trikaripur | LAC-ADS 2015-16 Trikaripur Constituency - Construction of 6m span culvert and approach road at Kariyamkod-Podothuruthi-Chathamath road in Nileshwaram Muncipality. | 45 | GO(Rt.)No.1085/2016/PWD dtd.20/07/2016. | 2570/2016-2017 dated; 07/01/2017 | EE/KSD/12016-1718dt.07/03/2017 | sri.M S Mohammed Rafique PWD Contractor Muliyar PO | 4209868.57 | 3157756 | 6 | 2017-03-07 | 2017-09-06 |  |  | Culvert completed. Approach road work in progress | 80%
10 |  |  | Trikkaripur | Improvements to Muttuchirathattu- kinathady road Km 0/190to 0/840 in Trikkaripur LAC |  |  | 2066/2016-17 dated; 27/10/2016 | EE/KSD/100/16-17 dt.09/01/2017 |  |  |  |  | 2017-01-09 | 2017-04-08 |  |  | Initial level taken and reported to CTE
5 | DEPOSIT WORKS
Kasaragod Package
1 |  |  |  | Construction Kannankai Bridge in Trikaripur LAC | 360 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.1 | 238/15-16 dtd 20/02/16 for Rs.290 L |  | U.Muhammed Kunhi, PWD Contractor, Panalam House Cheroor |  |  |  | 2016-06-17 | 2017-12-07 |  |  | Piling Work completed and abutment pile cap completed work in progress | 60%
2 |  |  |  | Construction of Ayamkadavu Bridge in Periya-Ayampara-Perladukkam road | 1400 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.7 | G.O.Rt.No. 1493/2015/PWD dtd.1/10/2015 | [5 empty] | 2016-12-31 | 2018-06-30 |  |  | substructure completed. Work in progress. | 65%
3 |  |  | Trikaripur | Construction of Vanhangad Bridge | 500 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.10 | 243/15-16 dtd.20/02/16 for Rs.480 L |  | M/s Chattanchal Engineering Company (P) Ltd. |  |  |  | 2016-07-15 | 2018-06-10 |  |  | Piling Work in progress out of 24 piles 21 pile completed.out of 3 spans 2 span girder & Deck slab completed | 75%
4 |  |  | Kasaragod | Construction of Vidyagiri Bridge | 250 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.15 | 244/15-16 dtd 20/02/2016 for Rs.250 L |  | Mohammed Asharaf, PWD Contractor, Etthirthodu, P.O.Edneer, Kasaragod |  |  |  | 2016-06-20 | 2017-06-14 |  |  | Completed | 100%
5 |  |  | Kanhangad | Improvments to Korathipathi-Ranipuram road | 150 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.20 | 4/CE/R/15-16 /4 dtd.18/4/ 2015 |  | Sei.M.A.Usman, PWD Contractor, Masthikundu House, P.O.Muliyar |  |  |  | 2015-11-09 | 2016-05-08 |  |  | Work Completed | 100%
6 |  |  | Manjeshwar | Improvments to Hill highway from Purushangadi to Idiyadukka ( 2nd reach) km 4/700 to 6/500 and 9/200 to 17/200 | 650 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.21 | [10 empty] | In view of NATPAC report decide to obtain clarification from Govt. in this regard
7 |  |  |  | Kasaragod Develoment Package - 2015-16 Reconstruction of Painikkara Bridge at km 24/600 of Hosdurg -Panathur road in Kasaragod District | 20 | G.O.(ms)No.3/2016/Plg Tvm dtd 14/01/2016, Sl.No.49 for Rs. 250L | 242/15-16 dtd.20/02/2016 for Rs. 240 L |  | U.Mohammed Kunhi, PWD contractor, Panalam House |  |  |  | 2016-06-17 | 2017-06-07 |  |  | Piling Work & deck slab work completed. Approach road work in progress | 90%
8 |  |  |  | Kasaragod Develoment Package - 2015-16 Improvements to Olavara Udumbumthala-Vellappu road in between 0/000 to 6/500 in Kasaragod District | 200 | G.O.(ms)No.3/2016/Plg Tvm dtd 14/01/2016, Sl.No.48 for Rs. 200L | 10/16-17 dtd.15/04/2016 for Rs.200 L |  | U.Mohammed Kunhi, PWD contractor, Panalam House |  |  |  | 2016-08-16 | 2017-02-15 |  |  | GSB &WMM completed Balance work in progress | 50%
9 |  |  |  | Kasaragod Development Package 2015-16 - Improvements to Hosdurg-Panathur(SH) road (Chemberi to Kolichal) working chainage between km 42/00 to 44/175) in Kasaragod District | 500 | G.O.(ms)No.3/2016/Plg Tvm dtd 14/01/2016, Sl.No.47 for Rs. 500L | 138/15-16 dtd.11/02/2016 for Rs.500 L |  | Sri.K.Moideen kutty Haji, PWD Contractor, Pattuvathil House, P.O.Thekkil |  |  |  | 2016-03-04 | 2016-11-03 |  |  | GSB completed.WMM Completed from 42/700 to 44/175 | 50%
10 |  |  |  | Cherupuzha-Chittarikkal road (2nd phase) | 350 | G.O.(Rt.) No.77/2016/Plg.Tvm dated 20/02/2016 | 11/16-17 dt.15/4/2016 Rs.350 L |  | Sri.Hunifa Meethal, PWD contractor | [7 empty] | GSB work completed. Balance work in progress | 50%
11 |  |  |  | Strengthening of Quality Control Sub division District Lab functioning under PWD by Purchasing equipments | 25 | GO(Rt.)No.544/2015/Plg./ dtd.22/12/2015 | [10 empty] | Revised estimate submitted for approval.
12 |  |  |  | Improvements to Nileshwar-Kottappuram -Thuruthi-Cheruvathur road km 0/000 to 11/000 | 800 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Estimate submitted for TS
13 |  |  |  | Improvements to Periya-Odayanchal road km 0/000 to 1/000 | 200 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Investigation Work in Progress
14 |  |  |  | Improvments to Mavila Kadappuram-Udinur Kadappuram-Ezhimala road km 0/000 to 12/000 | 200 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Estimate for TS under preparation
15 |  |  |  | Improvements to Ukkinadka-Elakana road km 0/000 to 4/000 | 910 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | TS Issued work to be tendered
16 |  |  |  | Improvements to Chowki-Uliyathadka SP Nagar Koppa road km 0/000 to 1/100 | 125 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 1027/17-18 | [9 empty] | Work Started
17 |  |  |  | Improvements to Bheemanadi-Mukkada road km 3/800 to 4/200 | 100 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 3998/16-17 | SE(K)127/17-18 dtd 29.7.2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 9532424 | 9099530 | 6 | 29.7.2017 | 28.1.2018 |  |  | work in progess
18 |  |  |  | Improvements to Panathur-Kallappalli road km 3/000 to 5/200 | 200 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Estimate submitted for TS
19 |  |  |  | Construction of Thadiyan vallappu bridge at Periya Odayanchal road | 275 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Agmt.Executed
20 |  |  |  | Construction of Bridge at Perumbatta across Thejaswini river in Cheemeni-Palavayal-Odakkolli road | 990 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Estimate submitted for TS
21 |  |  |  | Improvements to Thekkil Kizhoor road (0/000 to 3/500) | 300 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 232/17-18 | [9 empty] | Work Started
22 |  |  |  | Improvments to Edathila valappur-Channadukkam-Mangod road in between km 3/800 to 5/500 | 100 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 3853/16-17 | [9 empty] | TS issued work to be tendered
23 |  |  |  | Construction of Pallathur Bridge in Pallathumpara in Adoor Pandi road in Udma LAC in Kasaragod District | 758 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [10 empty] | Estimate for TS under preparation
24 |  |  |  | 2017/3548-Construction of Palathera Bridge across maicha river in cheruvathur vengat maicha Road | 700 | G.O.(Ms)No.174/2017/Plg. dtd.27/ 03/ 2017 | 418/2017-18 Dtd:5/05/2017 Rs/-530000 | EE/KSD/43/2016-17 Dtd:02/09/2017 | Safe matrix Architectural&Engineering Consultant India Private Lmtd | 529035 | 516603 | [5 empty] | Investigation work under tendering process
One Time Maintanance
1 |  |  |  | One time maintenance of village roads/ODR's IV-Part-III 2015-16-various roads in Chemmanadu and Chengala Grama panchayath and Puthiyaparappa in Kasaragod District- Package No.1 | 65 | GO(MS)No.109/2015-16/PWD,, TVM dated 21/12/2015 | CR/340/15-16 dtd.27/02/2016 | SE(K)150/16-17Dt:09/06/16 | Noufal | 6347989 | 6906377 |  | 2016-09-09 | 2017-01-08 | 2017-10-30 |  | work in progress
2 |  |  |  | One time maintenance of village roads/ODR's 2015-16 in Kasaragod Distriect mangalpady grama panchayath Package-1 | 88 | GO(MS)No.59/2015/PWD,, TVM dated 03/07/2015 | CR/47/2015-16 Dtd:9/7/15 | SE(K)405/15-16Dt:04/03/16 | V.P.Abdul khader |  | 9675162 |  | 2016-03-04 | 2016-07-03 |  |  | Work in progress
3 |  |  |  | One time maintenance of village roads/ODR's -III-2015-16 in various roads in Kasaragod municipality | 132 | GMS)No.76/2015/PWD,TVM dated 18/09/2015 | CR/243/2015-16 Dtd:9/12/15 | SE(K)404/15-16Dt:04/03/16 | V.P.Abdul khader |  | 9626423 |  | 2016-03-04 | 2016-07-03 |  |  | Work in progress
4 |  |  |  | One time maintenance of village roads ODR's-2015-16- in Kasaragod Distriect Vorkady grama panchayath package-2 | 60 | GO(MS)No.59/2015/PWD, TVM dated 03/07/2015 | CR/44/2015-16 Dtd:9/7/15 | SE(K)72/15-16Dt:01/09/16 | K.Abdul Rahiman |  | 5656794 |  | 2015-09-01 | 2015-12-31 |  |  | Work completed
5 |  |  |  | One time maintenance of vilalge roadsODR's 2015-16-Various roads in Bedadukka-Kuttikole and Chemmanadu grama oanbchayath in Kasaragod District-Package-2 | 130 | GO(MS)No.107/2015/PWD, TVM dated 21/12/2015 | CR/341/2015-16 Dtd:29/2/16 | SE(K)107/16-17Dt:19/7/16 | B.A.Shereef |  | 12530567 |  | 2016-07-19 | 2016-11-18 |  |  | Work in progress
6 |  |  |  | One time maintenance of village roads ODR's-III-2015-16- in Kasaragod Distriect in Kumbadaje-Badiadka-Bellur and Karadka-package-2 | 150 | GMS)No.76/2015/PWD, dated 18/09/2015 | CR/246/2015-16 Dtd:9/12/15 | SE(K)56/16-17 Dt:08/6/16 | K.V.Yoosaf |  | 16887916 |  | 2016-06-08 | 2016-09-07 |  |  | Work in progress
7 |  |  |  | One time maintenance of village roads ODRs-2015-16 in Kasaragod Distriect Manjeshwar grama panchayath Package-3 | 60 | GO(MS)No.59/2015/PWD, TVM dated 03/07/2015 | CR/49/2015-16 Dtd:10/7/15 | SE(K)344/15-16 Dt:01/03/16 | K.Abdul Rahiman |  | 6259728 |  | 2016-03-02 | 2016-07-01 |  |  | Work completed
8 |  |  |  | One time maintenance of village roads ODRs-III 2015-16-Various roads under Mogral Puthur grama panchayath-Package-3 | 119 | GO(MS)No.76/2015/PWD, TVM dated 18/09/2015 | CR/245/2015-16 Dtd:9/12/15 | SE(K)62/16-17 Dt:09/06/16 | M.A.Iqbal |  | 12520033 |  | 2016-06-09 | 2016-10-08 |  |  | Work in progress
9 |  |  |  | One time maintenance of village roads ODRs 2015-16 in Kasaragod District-Paivalike and Puthige grama panchayath-Package-4 | 74 | GO(MS)No.59/2015/PWD, TVM dated 03/07/2015 | CR/43/2015-16 Dtd:10/7/15 | SE(K)71/15-16 Dt:01/08/16 | K.Abdul Rahiman |  | 7317431 |  | 2015-09-01 | 2015-12-31 |  |  | Work in progress
10 |  |  |  | One time maintenance of village roads ODRs-III- 2015-16 in Kasaragod District-Changala grama panchayath-Package-4 | 132 | GO(MS)No.2015/PWD, dated18/09/2015 | CR/244/2015-16 Dtd:9/12/15 | SE(K)63/16-17 Dt:08/06/16 | M.A.Iqbal |  | 13883253 |  | 2016-06-09 | 2016-10-08 |  |  | Work in progress
11 |  |  |  | Pme time maintenance of village roads ODRs 2015-16 in Kasaragod District- Kumbala grama panchayath-Package-5 | 54 | GO(MS)No.59/2015/PPWD, dated 03/07/2015 | CR/48/2015-16 Dtd:10/7/15 | SE(K)230/15-16 Dt:13/11/15 | A.K.Thouseef |  | 5835381 |  | 2015-11-16 | 2016-03-15 |  |  | Work in progress
12 |  |  |  | One time maintenance of village roads OdRs 2015-16 -Part-I in Kasaragod district- Puthige gramma pabchayath-Package-6 | 90 | GO(MS)No.59/2015/PPWD, dated 03/07/2015 | CR/45/2015-16 Dtd:10/7/15 | SE(K)406/15-16 Dt:04/03/16 | V.P.Abdul khader |  | 9711134 |  | 2016-03-04 | 2016-11-03 |  |  | Work in progress
13 |  |  |  | One time maintenance of village roads ODRs 2015-16 in Kasaragod District Enmakaje gramma panchayath-Package-7 | 74 |  | CR/46/2015-16 Dtd:10/7/15 | SE(K)343/15-16 Dt:01/03/16 | C.H.Abdul Nizar |  | 8131582 |  | 2016-03-01 | 2016-06-30 |  |  | Work in progress
14 |  |  |  | One time maintenance of villages Roads ODRs Phase IV Part -I in various roads in kanhangad,madian-Ajanoor,kodom belur,madikai-pullur-periya,pallikkara &badaduka Grama Panchayath in kasaragod district |  | GO(MS)No.107/2015/PPWD, dated 21/12/2015 |  | SE(K)149/16-17 Dt:01/03/16 | V.V.Manojan |  | 15354670 |  | 2016-03-01 | 2016-08-31 |  |  | One number tobe started
15 |  |  |  | One time maintenance of village and ODRs Phase IV-Part -I (Kanhangad and TKR LAC)in various panchayath under PWD Roads section west eleri in kasaragod district Pakage 3 | 110 | GO(MS)No.109/2015/PPWD, dated 21/12/2015 | CR/16/2016-17 Dtd:3.06.2016 | SE(K)143/16-17 Dt:19/08/16 | Simson Vincent |  | 9887875 |  | 2016-08-19 | 2016-11-18 |  |  | One number tobe started
16 |  |  |  | One time maintenance of villages Roads ODRs Phase IV Part -I in various roads in karindalam,kayyur cheemeni-pilicode,cheruvathur,Trikaripur,nileshwar,padanna&valiyaparamba Grama Panchayath in kasaragod districtOne time maintenance of village and ODRs under Roads Section Nileshwar | 190 | GO(MS)No.109/2015/PPWD, dated 21/12/2015 | CR/13/2016-17 Dtd:5.08.2016 | SE(K)153/16-17 Dt:19/08/16 | M.V.Kunhikoran |  | 16495338 |  | 2016-08-19 | 18/11/22016 |  |  | Work completed
6 | SLTF
Pre monsoon 2016-17
1 |  |  |  | Urgent potholes filling to Eriya Kanhiradukkam road Km. 0/000 to 3/100. |  |  | AEE/TS/368/16-17 Dt. 22.06.2017 | AEE/H/05/ 2016-17 Dt. 25.07.2016 | Sri, AV Sreedharan | 300000 | 298364/- | [5 empty] | in progress ( work pending due to vigilance enquiry )
Post Monsoon 2016-17
1 |  |  | Kanhangad | Alamipally Areekadavu road km.0/000 to 2/100 | 14 | SLTF Dt. 05.09.2016 ( CE/R&B/TF/KSGD/03//2016-17 | EE/TS/1308/2016-17 Dtd.02.10.16 | EE/KSD/113/2016-17 Dtd:7/02/2017 | Udma LCCS | 1500000 | 1217334 | 3 | 2017-02-07 | 2017-05-06 |  |  | This work is proposed for cancellation and new work arranged
1 |  |  | Kasaragod | Kundamkuzhi Moonamkadavu Periya road km.1/200 to 2/700 | 15 | SLTF Dt. 05.09.2016 ( CE/R&B/TF/KSGD/03//2016-17 | EE/TS/1310/2016-17 Dtd.02.10.16 | EE/KSD/80/2016-17 Dtd:21/12/2016 | M.S. Mohammed Rafeeque. Muliyar | 2500000 | 1136017 | 3 | 2016-10-02 | 2017-01-01 |  |  | bitumen issued
1 |  |  | Trikaripur | OR 2016-17 - BT surface rectification works on Athudra-Kooliyadu-Peringara Road | 20 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [10 empty] | work tendered
2 |  |  | Trikaripur | OR 2016-17 - BT surface rectification works on Mavilakadappuram-Valiyaparamba Road (Swa,mi madam portion) | 20 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [10 empty] | Letter submitted for name of work correction. ( Major work in KDP )
3 |  |  | Trikaripur | OR 2016-17 - BT surface rectification works on Trikaripur-Payyannur road from Thattarkkadavu Palam to Annoor | 10 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [10 empty] | Quotation submitted for approval
4 |  |  | Trikaripur | OR 2016-17 - BT surface rectification works on Cheruvathur-Cheemeni-Thaliyaramada Road from km 0/000 to 2/500 road | 15 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3259/2016-17 dated 14/3/17 | EE/KSD/39/2017-18 Dated: 22-08-2017 | Sri. A.K. vinod Karyamkode | 1498400 | 1483495 | 2 | 2017-08-22 | 2017-10-21 |  |  | Agmt.Executed
5 |  |  | Trikaripur | OR 2016-17 - BT surface rectification works on Cheemeni-Palavayal-Odakkolli Road on km 25/000 to 30/000 | 20 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [10 empty] | Quotation invited
6 |  |  | Udma | OR 2016-17 - BT surface rectification works on Bandadukka-Manadukka-Kolichal road from km 0/300 to 3/000 | 15 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 2942/2016-17 Dated: 07/03/2017 | EE/KSD/16/2017-18 Dated: 01-06-2017 | N. Haridasan | 1498934/- | 1530615/- | 2 | 2017-04-20 | 2017-06-19 | Nil | 2017-05-11 | Completed | 100%
7 |  |  | Udma | OR 2016-17 - BT surface rectification works on Bandadukka-Manadukka-Kolichal road from km 5/000 to 7/500 | 15 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 2940/2016-17 Dated: 07/03/2017 | EE/KSD/17/2017-18 Dated: 01-06-2017 | N. Haridasan | 1498299/- | 1514546/- | 2 | 2017-04-20 | 2017-06-19 | Nil | 2017-05-11 | Time extension Granded up to 31/12/2017
8 |  |  | Udma | OR 2016-17 - BT surface rectification works on Bekal-Panayal Road from 0/000 to 1/600 | 25 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3304/16-17 Dt 23/3/17 | EE/KSD/32/2017-18 Dated: 18/07/2017 | Majeed Bendichal |  | 2615372 | 6 | 2017-07-18 | 2018-01-17 |  |  | Not started due to rain
9 |  |  | Udma | OR 2016-17 - BT surface rectification works on Bekal-Panayal Road from 1/900 to 3/500 | 25 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3606/16-17 Dt 23/3/17 | EE/KSD/33/2017-18 Dated:18/07//2017 | Majeed Bendichal |  | 2586500 | 6 | 2017-07-18 | 2018-01-17 |  |  | Not started due to rain
10 |  |  | Udma | OR 2016-17 - BT surface rectification works on Adoor-Pandy road from km 0/000 to 5/750 | 10 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3053/206-17 Dated: 10/03/2017 | EE/KSD/26/2017-18 Dated: 28-06-2017 | N. Haridasan | 998920/- | 1047623/- | 5 | 2017-06-28 | 2017-11-27 | Nil |  | Work in Progress
1 |  |  | Kanhangad | BT patches and strip BT to Hosdurg-Panathur road Km 24/000 to 26/000 | 15 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2964/16-17 Dt 7/3/17 | EE/KSD/05/17-18 Dt 02/5/17 | Anil Jose, Padimaruth |  | 1488532/- | [5 empty] | Bitumen issued
2 |  |  | Kanhangad | Surface Rectification by BT patches and strip BT to Odayanchal-Cherupuzha road Km 3/000 to 5/000 | 15 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2973/16-17 Dt 7/3/17 | EE/KSD/04/17-18 Dt 02/5/17 | Anil Jose, Padimaruth |  | 1430387/- | [5 empty] | Collection in progress
3 |  |  | Kanhangad | Providing BT patches and strip BT to Hosdurg-panathur road Km 32/000 to 33/500 | 12 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2962/16-17 Dt 7/3/17 | EE/KSD/02/17-18 Dt 17/4/17 | TJ Joseph Joy Kallar |  | 1195551/- | [5 empty] | in progress 50% completed
4 |  |  | Kanhangad | Providing BT patches and strip BT to Hosdurg-panathur road Km 38/000 to 39/000 | 8 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2951/16-17 Dt 7/3/17 | EE/KSD/03/17-18 Dt 17/4/17 | TJ Joseph Joy, Kallar |  | 796115/- | [5 empty] | Collection in progress
5 |  |  | Kasaragod | Surface rectification to Pernadka - Ramdas nager Road at Km 0/000 to 4/000 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/01/17-18 Dated: 12/04/2017 | Abdul Sherif.M | 999153/- | 931360/- | 2 | 2017-04-12 | 2017-06-11 |  |  | Work in Progress
6 |  |  | Kasaragod | Providing strip Bt to the Narampady-Ajjimoola-Vodamkallu-Vidyagiri road between Km 0/000 to 5/000 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3422/16-17 Dated:20-03-2017 | EE/KSD/13/17-18 Dated: 22/05/2017 | BA Abdul Khader | 999740/- | 1025985/- | 2 | 2017-05-22 | 2017-07-21 |  |  | Work in Progress
7 |  |  | Kasaragod | Providing stip BT to the Mulleria-Nattakkal-Ariapadavu road betweeen Km 2/000 and 8/000 | 5 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2999/16-17 Dated: 09/03/2017 | AEE/KSD/15/2016-17 Dated: 17/08/2017 | B.A Shareef | 452282/- | 477427/- | 2 | 2017-04-28 | 2017-06-27 |  |  | Work in Progress
8 |  |  | Kasaragod | Providing strip BT to the Nekrampara - Arladka - Pundoor - Narampady - Yethadka Road between Km 9/000 and11/600 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 81/17-18 Dated: 25/04/2017 | EE/KSD/14/2017-18 Dated: 22/05/2017 | B. A Abdul Khader | 999838/- | 1034541/- | 2 | 2017-05-22 | 2017-07-21 |  |  | Work Compled
9 |  |  | Kasaragod | Surface rectification to Bovikanan - Bevinje Road at Km 3/000 to 4/400 | 8 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/08/17-18 Dated: 08/05/2017 | Araf. P.B | 799520 | 766487/- | 2 | 2017-05-08 | 2017-07-07 |  |  | Work in Progress
10 |  |  | Kasaragod | Surface Rectification to Bevinje-Aloor-Iriyanni road Km 0/000 to 1/000 | 7 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/09/17-18 Dated: 08/05/2017 | Araf. P.B | 699712/- | 676860/- | 2 | 2017-05-08 | 2017-07-07
11 |  |  | Manjeshwar | Re- Construction of collapsed RCC Culver (6m span) at Km 0/900 of Durgipalla - Bejja - Munnipady Road | 20 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/20/16-17 Dated: 14/06/2017 | Iddin Kunhi. |  | 1498340/- | [5 empty] | Work in Progress
12 |  |  | Manjeshwar | Surface Rectification to Majeerpalla - Kolyoor Temple Donikallu - Pollakaje - Meeyapadavu Road Km from 0/000 to 1/500 | 15 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3444/16-17 Dated: 20-03-2017 | EE/KSD/6/2017-18 Dated: 04-05-2017 | K Abdul Rahiman | 1499212 | 1416670 | 2 | 2017-05-04 | 2017-07-03 |  |  | Work in Progress
13 |  |  | Manjeshwar | Providing Strip B-T to Kunjathoor-Kedumbadi-Nandarapadavu Road km from 1/000 to 2/600,4/300 to 6/700 and 8/800 to 9/100 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3445/16-17 Dated: 20-03-2017 | EE/KSD/9/2017-18 Dated: 04-05-2017 | K Abdul Rahiman |  | 944015/- | 2 | 2017-05-04 | 2017-07-03 |  |  | Work in Progress
14 |  |  | Manjeshwar | providing Strip B-T to Majeerpalla-Agra road Km 0/000 to 1/000 | 5 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3019/16-17 Dated: 19-03-2017 | AEE/KSD/01/17-18 Dated: 21/04/2017 | K Abdul Rahiman | 471636/- | 471636/- | 2 | 2017-05-04 | 2017-07-03 |  |  | Work in Progress
1 |  |  | Kasaragod | Surface renewal to Perumbalakadavu-Nayammarmoola-Erappakkatta Road km 1/000 to 3/000 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [10 empty] | Substituted Order Dated on 29-03-2017
2 |  |  | Kasaragod | Surface renewal to Badiadka-Barla-vidyagiri-Muniyoor Road km 2/000 to 3/000 | 18 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1149/17-18 Dated: 09-06-2017 | [9 empty] | Work in Re Tendering Process
3 |  |  | Kasaragod | Surface renewal to Ramdas Nagar-Parakatta Road km 0/000 to 2/250 (balance portion) | 7 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 4194/16-17 Dated: 30/03/2017 | EE/KSD/23/17-18 Dated: 17-06-2017 | V.P.Abdulkhader V.P(H) P.O.Mogral |  | 753484 | 5 | 2017-06-17 | 2017-11-16 |  |  | Work in Progress
4 |  |  | Udma | Surface renewal to Periya-Odayamchal road between km 8/500 to 9/500 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1166/17-18 Dt. 14/6/17 | [9 empty] | Tendered
5 |  |  | Udma | Surface renewal to Kundamkuzhi-Moonamkadavu-Periya road km 5/000 to 7/000 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1167/17-18 Dt.14/6/17 | [9 empty] | Tendered
6 |  |  | Udma | Surface renewal to Bovikanam-Kanthur Road km 5/000 to 6/800 | 18 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 4443/16-17 Dated: 30/03/2017 | EE/KSD/41/17-18 Dated: 02-09-2017 | Udayapuram LCS | 1795718 | 1797003 | 6 | 2017-09-02 | 2017-02-01 |  |  | Work in Progress
7 |  |  | Udma | Surface renewal to Koliyadukam-Perumbalakadavu road km 0/000 to 2/000 | 24 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 4176/16-17 Dated: 30/03/2017 | EE/KSD/24/17-18 Dated: 17-06-2017 | Mohammed Sunaif.C.M MAH Compound Chengala(PO) |  | 149854 | 6 | 2017-06-17 | 2017-12-16 |  |  | Work in Progress
8 |  |  | Udma | Surface renewl to delampady Panjikal road 3/500 to 4/500 | 15 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1148/2017-18 Dtd:09/06/2017 |  | Sri,Berka Abdul KhaderBerka(HO) Nellikkatta Edneer(PO) | 1498537 | 1608541 | 2 |  |  |  |  | Selection Notice Issued
9 |  |  | Manjeshwar | Surface renewal to Bakery Junction Kavisubramnya Temple thoudugoli road from km 2/230 to 3/000 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 113/17-18 Dated: 27/04/2017 | EE/KSD/22/17-18 Dated: 14-06-2017 | Mohammed Sakeer, Bevinje, Thekkil Ferry | 2497650/- | 2209963/- | 2 |  |  |  |  | Work in Progress
10 |  |  | Manjeshwar | Surface renewal to Kuloor-Chinala Road km 0/000 to 1/500 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 571/17-18 | EE/KSD/27/17-18 Dated: 04/07/2017 | V.P. Abdul Khader | 2498324 | 2183835 | 6 | 2017-07-04 | 2018-01-03 |  |  | Work in Progress
11 |  |  | Kanhangad | Surface renewal to Anakallu-Pookayam-Malakallu(Extension)km 1/200 to 4/500 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 574/17-18 Dt.9/5/17 |  | Sebastian MD, Malakkallu | [7 empty] | Tendered
12 |  |  | Kanhangad | Surface renewal to Periya-Odayamchal road between km 8/500 to 9/500 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1166/17-18 Dt.14/06//17 | EE/KSD/42/17-18 Dated: 02/09/2017 | Udayapuram LCS | 1249134 | 1241122 | [5 empty] | Agmt.Executed
13 |  |  | Kanhangad | Surface renewal to Chamattamvayal-Kalichanadukam road km 3/000 to 4/000 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1151/17-18 Dt.9/6/17 | EE/KSD/40/17-18 Dated: 24/08/2017 | E V Krishna Pothuval | 1297545 | 1227322 | 3 |  |  |  |  | Agmt.Executed
14 |  |  | Kanhangad | surface renewal to Chullikkara-Kuttikole road km 5/000 to 6/500 | 12 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1006/2017-18 dated 22/5/17 |  | G.S. Rajeev Malakkallu | [7 empty] | Tendered
15 |  |  | Kanhangad | Surface renewal to Chullikkara-Kuttikole road km 7/500 to 9/000 | 16 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 573/2017-18 dated 9/5/17 |  | G.S. Rajeev Malakkallu | [7 empty] | Tendered
16 |  |  | Trikaripur | Surface renewal to Odayanchal Cherupuzha road km 20/400 to 22/000 | 17 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [10 empty] | Tendered
17 |  |  | Trikaripur | Surface renewal to Chittarikkal-Kunnumkai road km 9/000 to 10/500 | 17 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 575/2017-2018 dt :09/05/2017 Rs/-12L |  | Joseph joy Kallar PO Rajapuram | [7 empty] | Tendered
18 |  |  | Trikaripur | Surface renewal to Cheemeni-Palavayal-Odakolli road km 21/500 to 23/000 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [10 empty] | Tendered
19 |  |  | Trikaripur | surface renewal to Peralam-Kamballur road km 0/000 to 1/000 | 8 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [10 empty] | Tendered
|  |  | Kanhangad | Rectification of surface damages to Chemmattamvayal-Kalichanadukkam road km 10/000 to 14/250 | 10 | CE/R&B/TF/KSGD/11/2016-17 DT. 28/03/2017 | 43 /17-18 Dt.22/4/17 | EE/KSD/19/17-18 Dated: 01/07/2017 | Pradyumna.B.K Bekal Fort Kasaragod | 998557 | 1082830 | 2 | 2017-06-01 | 2017-07-31 | 2017-10-30 |  | GSB in progress
|  |  | Kanhangad | Rectification of surface damages to Chemmattamvayal-Kalichanadukkam road km 14/300 to 18/600 | 10 | CE/R&B/TF/KSGD/11/2016-17 DT. 28/03/2017 | 42 /17-18 Dt.22/4/17 | EE/KSD/18/17-18 Dated: 31/06/2017 | M. Abdul Basheer ,P.O.Bekal Fort | 999016 | 1080995 | 2 | 2017-06-01 | 2017-07-31 | 2017-10-30 |  | GSB in progress
|  |  | Kasaragod | RP 2016-17-Surface renewal to approach road Tb Kasaragod | 15 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [10 empty] | Work in Re Tendering Process
|  |  | Kasaragod | RP 2016-17-Surface renewal to Collectors Bengalow-Thamarakkuzhi link road km 0/000 to 0/165 | 5 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 78/17-18 Dated: 25/04/2017 | AEE/KSD/2/17-18 Dated: 11/05/2017 | D.M. Ahamad |  | 499084/- | [5 empty] | Work in Progress
|  |  | Manjeshwar | RP 2016-17 -Surface renewal to NH Nayabazar-Kuthkodi-Sonkal-Prathap Nagar -Ambedkar road km 1/200 to 1/800 | 20 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 112/2017-18 Dtd:27/04/17 | AEE/KSD/34/17-18 Dated: 02/08//2017 | Abdul Saleem |  | 1790573 | 3 | 2017-08-02 | 2017-11-01 |  |  | Work in Progress
|  |  | Kanhangad | RP 2016-17-Surface renewal to Thulasseri-Nileshwaram Azhithala(via) Ajanur Kadappuram road km 4/500 to 6/800 | 20 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 1146 /17-18 Dt.22/4/17 | [9 empty] | Tendered
|  |  | Trikaripur | RP 2016-17 -Surface renewal to Chittarikkal-Kunnumkai road km 6/500 to 7/500 | 12 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 1007/17-18 Dt.22/05/17Rs/-12L |  | Joseph joy Kallar PO Rajapuram |  | 1199971 | 6 |  |  |  |  | Tendered
|  |  | Trikaripur | RP 2016-17 -Surface renewal to Chittarikkal-Kunnumkai road km 7/500 to 9/000 | 15 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 883/17-18 Dt.17/05/17Rs/-15L |  | Joseph joy Kallar PO Rajapuram |  | 1499970 | 6 |  |  |  |  | Tendered
|  |  | Trikaripur | RP 2016-17-Surface renewal to Trikaripur-Vellappu Ayitti road km 0/300 to 0/900 | 7 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [10 empty] | Tendered
|  |  | Trikaripur | RP 2016-17-Surface renewal to Pothamkandam-Anepettypoil-Padiyottuchal road km 1/600 to 2/500 | 10 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [10 empty] | To be cancelled duo to new work in KDP
|  |  | Trikaripur | RP 2016-17-Surface renewal to Cheruvathur-Cheemeni-Thaliyammada road km 11/000 to 11/500 | 6 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [10 empty] | Tendered
|  |  | Kasaragod | Surface renewal to Perumbalakadavu-Nayammarmoola-Erappakkatta road km 3/000 to 5/000 | 25 | CE/R&B/TF/KSGD-SUB-1/2016-17 DT. 29/03/2017 | 730/17-18 Dated: 12/05/2017 | [9 empty] | Under Tender
|  |  | Kanhangad | RP 2016-17-Surface renewal to Thulasseri-Nileshwaram Azhithala(via) Ajanur Kadappuram road km 3/500 to 4/500 | 13 | CE/R&B/TF/KSGD-SUB-1/2016-17 DT. 29/03/2017 | 1147 /17-18 Dt.09/6/17
|  |  | Trikaripur | Resurfacing on Kayyur-Chembrakanam-Palakunnu Road | 20 | CE/R&B/TF/KSGD-S&S-1/2016-17 DT. 29/03/2017 | 918/2017-18 dated 18/5/2017 | EE/KSD/36/17-18 Dated: 11-08-2017 | Udayapuram labour contract Co-op society Ltd., | 1998100 | 1986423 | 3 | 2017-08-11 | 2017-11-10 |  |  | Agmt.Executed
|  |  | Trikaripur | Resurfacing on Thaikadappuram-Azhithala Road | 20 | CE/R&B/TF/KSGD-S&S-1/2016-17 DT. 29/03/2017
|  |  | Trikaripur | Resurfacing on Nadakkavu-Udhinur-Machikkadu Road | 12 | CE/R&B/TF/KSGD-S&S-1/2016-17 DT. 29/03/2017 | [10 empty] | ODR
|  |  | Manjeshwar | Urgent rectification works between km 23/227 and 33/000 of Kalladuka-Cherkala road | 23.1 | CE/R&B/TF/KSGD-S&S-2/2016-17 DT. 31/03/2017 | 45/17-18 Dated: 22/04/2017 | EE/KSD/11/17-18 Dated: 16-05-2017 | B Abdul Khader | 23085090 | 2307934 | 2 | 2017-05-16 | 2017-07-15 |  |  | Completed
|  |  | Kasaragod | Urgent rectification works between km 33/000 and 50/500 of Kalladuka-Cherkala road | 24.45 | CE/R&B/TF/KSGD-S&S-2/2016-17 DT. 31/03/2017 | 44/17-18 Dated: 22/04/2017 | EE/KSD/29/2017-18 Dated: 04/07/2017 | Muhammad Kunhi. K., Kettumkal | 2444917/- | 2557300/- |  | 2017-07-04 |  |  |  | Work in Progress
|  |  | Kasaragod | Urgent rectification works between km 2/000 and 20/000 of Badiadka-Yethaduka-Soolapadavu raod | 8.85 | CE/R&B/TF/KSGD-S&S-2/2016-17 DT. 31/03/2017 | 81/17-18 Dated: 25/04/2017 | EE/KSD/10/2017-18 Dated: 16/05/2017 | B. A. Shreef | 884741 | 957016 | 2 | 2017-05-16 | 2017-07-15 |  |  | Completed
|  |  | Kasaragod | Road Safety Works - Providing metal Crush barrier at various accident spots uinder PWD roads Section, Kasaragod | 14.6 | KSD/2017/668 Dated: 20/03/2017 | 4143/16-17 Dated: 30/03/2017 | EE/KSD/21/2017-18 Dated: 14/06/2017 | Majeed Bendichal |  | 1311824 | 3 | 2017-06-14 | 2017-09-13 |  |  | Completed
PRE MONSOON WORKS 2017-18 ( Other Than SLTF Works)
1 |  |  | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Muligadde - Beripadavu Road Km 2/750 to 4/100 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 148/17-18 Dated: 28/04/2017 | AEE/KSD/10/17-18 Dated: 02/08/2017 | K. Abdul Rahiman | 198457/- | 213506/- | 3 | 2017-05-23 | 2017-08-22 |  |  | Work in Progress
2 |  |  | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Perla - Soorambail Road between Km 3/900 and 5/800 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 156/17-18 Dated: 28/04/2017 | AEE/KSD/14/17-18 Dated: 21/06/2017 | A.K. Badsha | 249164/- | 265837/- | 1 | 2017-06-21 |  |  |  | Work in Progress
3 |  |  | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Morthana - Miyapadavu Road Km 0/000 to 0/700, 1/400 to 2/400 and 3/500 to 3/800 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 149/17-18 Dated: 28/04/2017 | AEE/KSD/04/17-18 Dated: 01/06/2017 | A.K. Thouseef | 245490/- | 248501/- | 3 | 2017-06-01 | 2017-06-30 |  |  | Work in Progress
4 |  |  | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Baikatta - Meeyapadavu Road Km 0/000 to 1/300 and 1/700 to 2/800 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 150/17-18 Dated: 28/04/2017 | AEE/KSD/05/17-18 Dated: 01/06/2017 | A.K. Thouseef | 999237/- | 944015/- | 3 | 2017-05-23 | 2017-08-22 |  |  | Work in Progress
5 |  |  | Uduma | Pre Monsoon works 2017-18 BT Patches to Kanhirathinkal - Vavadukkam Road between Km 0/000 to 5/000 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 152/17-18 Dated: 28/04/2017 | AEE/KSD/07/17-18 Dated: 22/06/2017 | A.R Abdul Rahiman | 249743/- | 266443/- | 3 | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
6 |  |  | Uduma | Pre Monsoon works 2017-18 BT Patches and potholes filling of Delampady - Panjikkal Road Km 0/000 to 3/500 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 154/17-18 Dated: 28/04/2017 | AEE/KSD/12/17-18Dated: 16/08/2017 | A.K. Badsha | 199569/- | 244263/- | 1 | 2017-06-21 |  |  |  | Work in Progress
7 |  |  | Uduma | Pre Monsoon works 2017-18 BT Patches and potholes filling of Bovikanam - Kanathur Road between Km 0/000 to 5/000 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 151/17-18 Dated: 28/04/2017 | AEE/KSD/08/17-18 Dated:22/06/2017 | A.R Abdul Rahiman | 249778/- | 266577/- | 3 | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
|  |  | Udma | Urgent Special Repairs works to Uduma Mullassery road Km. 3/700 to 4/700 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  |  | K.Muhammed Kunhi Zubair Munzil Mangad(PO)vUdma |  | 299966 | [5 empty] | Quatation submitted for approval
9 |  |  | Kasaragod | Pre Monsoon Works 2017-18 BT Patches to Kasaragod - Kanhangad Old SH | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 179/17-18 Dated: 29/04/2017 | AEE/KSD/06/17-18 Dated:22/06/2017 | A.R Abdul Rahiman | 299360/- | 321859/- | 3 | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
10 |  |  | Kasaragod | Pre Monsoon works 2017-18 BT Patches and potholes filling of Nellikkatta - Karmamthody Road Km 10/000 to 11/000 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 155/17-18 Dated: 28/04/2017 | AEE/KSD/11/17-18Dated: 16/08/2017 | A.K. Badsha | 299273/- | 320010/- | 1 | 2017-06-21 |  |  |  | Work in Progress
11 |  |  | Kasaragod | Pre Monsoon Works 2017-18 BT Patches to Madhur - Patla - Kolloangana Road between Km 3/000 to 8/020 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 147/17-18 Dated: 28/04/2017 | AEE/KSD/09/17-18Dated: 22/06/2017 | A.R Abdul Rahiman | 199826/- | 212919/- | 3 | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
12 |  |  | Kasaragod | Pre Monsoon Works 2017-18 BT Patches and Pot holes filling of Nakrampara - Arladkka - Pundoor - Narampady Road between Km 0/000 to 6/010 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 153/17-18 Dated: 28/04/2017 | AEE/KSD/13/17-18Dated: 16/08/2017 | A.K. Badsha | 199826/- | 214587/- | 1 | 2017-06-21 |  |  |  | Work in Progress
13 |  |  | Trikkaripur | Urgent Surface rectification to Payyanur -Kara Thalichalam road Km. 3/700 to 4/500 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  | AEE/H/01/17-18 Dt. 26-10-17 | MV BALAKRISHNAN | [7 empty] | Agmt.Executed
14 |  |  | Trikkaripur | Urgent Surface rectification to Cheemeni - Chanadukkam - Kakkadavu road Km. 3/000 to 4/000 | 4 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  | AEE/H/02/17-18 Dt. 26-10-17 | MV BALAKRISHNAN | [7 empty] | Agmt.Executed
15 |  |  | Trikkaripur | Urgent Surface rectification to Cheemeni - Chanadukkam - Kakkadavu road Km. 4/000 to 5/000 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  | AEE/H/03/17-18 Dt. 26-10-17 | MV BALAKRISHNAN | [7 empty] | AGT. EXECUTED
16 |  |  | Kanhangad | Urgent Special Repairs works to Chemmattamvayal - Kalichanadukkam road Km. 4/000 to 5/000 | 5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  |  | M.A.Haris Mustikundu Muliyar |  | 499413 | [5 empty] | Quatation submitted for approval
17 |  |  | Kanhangad | Urgent Special Repairs works to Thuillissery - Nileswaram - Azhithala (via. ) Ajanur kadappuram road Km. 0/000 to 0/500 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  |  | M.Muhammed Kunhi Athinjal |  | 299668 | [5 empty] | Quatation submitted for approval
18 |  |  | Kanhangad | Urgent Special Repairs works to T.B Savaparamba - Kotrachal road Km. 3/000 to 4/000 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 |  |  | M.Muhammed Anandasramam |  | 199054 | [5 empty] | Quatation submitted for approval
1 |  |  | Manjeshwar | Strip BT of Sungathakatta - Nandarapadavu Road Km 0/000 to 1/500 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3761/17-18 Dated: 12/10/2017 | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
2 |  |  | Manjeshwar | Strip BT of Morthana - Miyapadavu Road Km 0/700 to 1/400, 2/410 to 3/500 and 3/800 to 6/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3754/17-18 Dated: 12/10/2017 | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
3 |  |  | Manjeshwar | Strip BT and Pot holes filling to Meeyapadavu - Baikatta Road Km 0/000 to 3/000 | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3893/17-18 Dated: 13/10/2017 | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
4 |  |  | Manjeshwar | Strip BT and Pot holes filling to Chevar - paivalike Road from Km 0/000 to 3/600 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4133/17-18 Dated: 16/10/2017 | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
5 |  |  | Manjeshwar | Strip BT to Kadambar Arimala Mazjid Road from Km 0/000 to 2/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4137/17-18 Dated: 16/10/2017 | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
6 |  |  | Manjeshwar | Water Logged Portion Concrete Road pavement and CC Drain for Manjeshwaram - Ukkada Road from Km 11/600 to 11/700 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3647/17-18 Dtd:12/10/17 |  | P.Ahammed Sherief Perla(H0) Perla(PO) | 2499051 | 2085263 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
7 |  |  | Manjeshwar | Strip BT and Pot holes filling to Durgipalla Bejja Munnipady Road from Km 0/000 to 2/500 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3771/17-18 Dated: | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
8 |  |  | Manjeshwar | surface rectification between km 0/000 and 4/000 of Mundyathadukka-Mugu-Puthige Road | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3999/17-18 Dated: 14/10/17 | [9 empty] | Work under Tendering Process
9 |  |  | Manjeshwar | Strip BT and Pot holes filling to Durgipalla Bejja Munnipady Road from Km 2/500 to 5/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4140/17-18 Dated: 16/10/2017 | [9 empty] | Tenderd on 27-10-17 No Response - Re- Tendered
10 |  |  | Manjeshwar | Surface Renewal to Kumbla-Kanchikatta-kottekar-Naikapu Road km 3/700 to 4/400 | 12 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3799/17-18 Dated: 12/10/17 | [9 empty] | Work under Tendering Process
11 |  |  | Manjeshwar | Construction of CC culvert and CC Drain at Km 8/300 of Permuda - Bayarpadavu Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4095/17-18 Dated: 15/10/17 |  | Subin Antony Manathoor(H) Kumbadaje(PO) | 1498234 | 1437236.64 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
12 |  |  | Manjeshwar | Surface Renewal to Soorambail-Vaninagar-Kinningar Road km 1/000 to 2/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4089/17-18 Dated: 15/10/17 |  | Berka AbdulKhader berka(H) Edneer Nellikkatta | 1441042 | 1437236.64 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
13 |  |  | Manjeshwar | Strip BT and Pot holes filling at Km 3/900 to 4/400 of Muligadde - Beripadavu Rod | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
14 |  |  | Manjeshwar | Surface Renewal to Perla-Soorambail- Road km 3/900 to 5/800 | 24 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3807/17-18 Dated: 12/10/17 | [9 empty] | Work under Tendering Process
15 |  |  | Manjeshwar | Strip BT and Pot holes filling at Km 4/000 to 6/000 of Ubbathodi - Cheppinadukka - Naikap Road | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
16 |  |  | Manjeshwar | Surface Renewal to Adkasthala-Odia- Road km 2/500 to 4/500 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4073/17-18 Dated: 15/10/17 |  | M Ahammed Asharaf Ethirithode(H) Edneer(PO) | 2496772 | 2427366.81 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
17 |  |  | Manjeshwar | SR to Hidayath Nagar NH Pachilampara Bagavathi Temple Raod 0/000 to 3/000 | 16 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4228/2017-18 Dated: 17/10/2017 | [9 empty] | Work under Tendering Process
18 |  |  | Kasaragod | Construction of C C drain between km 22/200 and 22/700 of Cherkala - Jalsoor Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4193/17-18 Dated: 16/10/2017 |  | C.H Ahammed Asharaf Managing Partner C H Construction Cherikkode Thekkil(PO) | 1497191 | 1269442.5 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
19 |  |  | Kasaragod | Construction of slab culvert and providing covering slab at km19/050 of Cherkala - Jalsoor Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
20 |  |  | Kasaragod | Construction of slab culvert and CC drain at km3/510 of A P Circle - Gosada- Bolinja Road | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 4094/17-18 Dated: 15/10/2017 | [9 empty] | Work under Tendering Process
21 |  |  | Kasaragod | Construction of C C drain between km 21/100 and 21/800 of Cherkala - Jalsoor Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
22 |  |  | Kasaragod | Widening and construction of protection wall between km 16/000 and 16/200 Cherkala - Jalsoor Road | 18 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
23 |  |  | Kasaragod | surface rectification between km 16/000 and 39/000 of Cherkala - Jalsoor Road | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
24 |  |  | Kasaragod | Surface Renewal to Nellikatta-Karmanthody Road km 10/000 to 11/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3767/17-18 Dtd:12/10/17 |  | Subin Antony Manathoor(H) Kumbadaje(PO) | 1499732 | 1398697.46 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
25 |  |  | Kasaragod | Providing BM & BC bet Km 3/000 to 4/500 at Madhur- Patla Kollamgana road | 50 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
26 |  |  | Kasaragod | Surface Renewal to Nekrampara-Arladuka-Kodimoole-Pundoor-Narampady-Yethadka Road km 10/000 to 11/600 | 21 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3760/17-18 Dtd:12/10/17 |  | Subin Antony Manathoor(H) Kumbadaje(PO) | 2099581 | 1950522.12 | 2 |  |  |  |  | Selection Notice Issued.Agmtto be executed
27 |  |  | Kasaragod | Improvements to Karantakkadu Junction at KM 0/000 to 0/400 of Kasaragod -Madhur road | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
28 |  |  | Kasaragod | Surface Renewal to Nekrampara-Arladuka-Kodimoole-Pundoor-Narampady-Yethadka Road km 9/000 to 10/000 | 11 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
29 |  |  | Udma | Providing strip BT to Thekkil-Alatty road bet KM 30/400 to 34/555 (MSS) | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
30 |  |  | Udma | Surface renewal to Paduppu - Bandadukka Karivedakam road att Km0/000 to 1/800 and 2/210 to 3/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
31 |  |  | Udma | Surface rectification to Paduppu Bandamkai Karivedakam Road (km 2/210 to 3/000) | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work substituted
32 |  |  | Udma | Ammangod Kallukandam Chathappady road (km 5/000 to 0/000) | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
33 |  |  | Udma | Surface rectification to Chaligal-Meengoth-ambalathara road km 3/500 to 4/900 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2888/17-18 Dtd:5/10/2017 |  | Sri.K.M.Ahammed Kainoth(H) Melparamba(PO) Kalanad | 1480203 | 1398639 | 2 |  |  |  |  | Selection notice Issued
34 |  |  | Udma | Surface providing strip BT to Thekkil-Alatty road km 16/000 to 17/300 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 |  |  |  | 1480203 | [6 empty] | Work under Tendering Process
35 |  |  | Udma | OR 2017-2018 BC surface rectification works on bekal-panayal road between 3/500to 4/000. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
36 |  |  | Udma | OR 2017-2018 BC surface rectification works on bekal-panayal road between 4/000 to 5/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
37 |  |  | Udma | OR 2017-2018 BC surface rectification works on bekal-panayal road between 5/000 to 6/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
38 |  |  | Udma | Surface rectification to Eriya Kanhiradukka, road km 0/000 to 3/000 | 18 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
39 |  |  | Udma | Providing covering slab overdrain to Udma Mullacherry road between km 0/000 to 1/000 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Substituted
40 |  |  | Udma | Widening the carriage way and surface renewal to Bovikanam Bevinje road km 0/000 to 3/000 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3862/2017-18 Dated: 13/10/2017 | [9 empty] | Work under Tendering Process
41 |  |  | Udma | Widening the carriage way and surface renewal to Bovikanam Bevinje road km 0/000 to 3/000 | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
42 |  |  | Udma | Providing strip BT to Koliyadukkam Perumbalakkadavu road km 0/000 to 5/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3862/2017-18 Dated: 13/10/2017 | [9 empty] | Work under Tendering Process
43 |  |  | Udma | Providing strip BT to Thekkil-Alatty road bet KM 0/000 to 16/000 | 12 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 3362/17-18 Dated: 09/10/17 | [9 empty] | Work under Tendering Process
44 |  |  | Kanhangad | OR 2017-2018 Supplying and Laying Shelmac on various roads under road section kanhangad . | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 |  |  | M/S Bitu tech | [7 empty] | Work Tendered
45 |  |  | Kanhangad | OR 2017-2018 Clearing side drain, jungle clearance, clearing choked culverts and wood cutting in various roads under roads section kanhangad . | 2 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 |  |  | M Mohammed | [7 empty] | Work Tendered
46 |  |  | Kanhangad | Providing strip B.T to Hosdurg Panathur road K.M 26/000 to 28/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2698/2017-18 Dtd:04/10/2017 Rs/-1489000 |  |  | 1488153 | [6 empty] | Work under Tendering Process
47 |  |  | Kanhangad | Providing strip B.T to Odayanchal Cherupuzha road K.M 5/000 to 6/500. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
48 |  |  | Kanhangad | Providing strip B.T to Anakkal Pookayam Malakkallu Road K.M 0/000to 1/200. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
49 |  |  | Kanhangad | Providing strip B.T to Odayanchal Cherupuzha Road K.M 0/000to 3/000. | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2693/2017-18 Dtd:04/10/2017 Rs/-1983700 |  |  | 1983653 | [6 empty] | Work under Tendering Process
50 |  |  | Kanhangad | Providing strip B.T to Chullikkara Kuttikkole Road K.M 6/500 to 7/500. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
51 |  |  | Kanhangad | Providing strip B.T to Hosdurg Panathur road K.M 33/500 to 34/500 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
52 |  |  | Kanhangad | Urgent surface rectification to Nileswar Edathode road KM.3/000 to 5/000. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
53 |  |  | Kanhangad | Urgent surface rectification to Nileswar Edathode road KM.12/000 to 13/000. | 6 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2445/2017-18 Dtd:28/09/2017 Rs/-6 L |  |  | 594042 | [6 empty] | Work under Tendering Process
54 |  |  | Kanhangad | Urgent surface rectification to Bangalam Thekkan Bangalam Nileswar block office road KM.0/000 to 2/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
55 |  |  | Kanhangad | Urgent surface rectification to Choyyamkode Mukkada office road KM.6/000 to 8/500. | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
56 |  |  | Kanhangad | OR 2017-2018 Raising water logged portion and surface rectification between Km 1/000 to 2/000 Thullichery-Nileswar-Azhithala (via) Ajanoor kadappuram road. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
57 |  |  | Kanhangad | OR 2017-2018 Raising water logged portion and surface rectification at Nhanikadavu between Km 5/000 to 6/000 T.B Shavaparamba- Kottrachal road. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
58 |  |  | Kanhangad | OR 2017-2018 Surface rectification and raising water logged portion between km 7/000 to 8/400 of T.B shavaparamba-kottrachal road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
59 |  |  | Kanhangad | OR 2017-2018 Surface rectification to T.B shavaparamba-kottrachal road between km 1/000 to 2/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
60 |  |  | Trikaripur | Supplying and laying shelmac on various roads under Roads Section, West Eleri. | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 |  |  | M/S Bitu tech | [7 empty] | Work Tendered
61 |  |  | Trikaripur | Removal of slipped earth cleaning chalked culverts and removal of fallen trees and wood cutting for various roads under Roads section west eleri. | 2 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
62 |  |  | Trikaripur | Supplying and laying shelmac on various roads under Roads Section, Nileswar. | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 |  |  | M/S Bitu tech | [7 empty] | Work Tendered
63 |  |  | Trikaripur | Removal of slipped earth cleaning chalked culverts and removal of fallen trees and wood cutting for various roads under Roads section Nileswar. | 2 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
64 |  |  | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha road K.M 26/400 to 28/000 . | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
65 |  |  | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha road K.M 28/00 to 29/500 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2661/17-18 Dtd:02/10/17 Rs/-15L |  |  | 1499349 | [6 empty] | Work under Tendering Process
66 |  |  | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha road K.M 29/500 to 31/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2662/17-18 Dtd:02/10/17 Rs/-15L |  |  | 1498533 | [6 empty] | Work under Tendering Process
67 |  |  | Trikaripur | Providing strip B.T to Varakkad-Elerithattu Paramba Road K.M 0/000 to 2/600. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2694/17-18 Dtd:04/10/17 Rs/-1496000 |  |  | 1495147 | [6 empty] | Work under Tendering Process
68 |  |  | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha Road K.M 23/500to 25/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2653/17-18 Dtd:04/10/17 Rs/-15L |  |  | 1498524 | [6 empty] | Work under Tendering Process
69 |  |  | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha Road K.M 22/000to 23/500 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2696/17-18 Dtd:04/10/17 Rs/-1497000 |  |  | 1496987 | [6 empty] | Work under Tendering Process
70 |  |  | Trikaripur | Providing strip B.T to Cheemeni-Palavayal-Odakkolli Road K.M 26/500 to 28/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 519/17-18 Dtd:24/09/17 Rs/-1488000 |  |  | 1487825 | [6 empty] | Work under Tendering Process
71 |  |  | Trikaripur | Providing strip B.T to Beemanadi-Mukkada Road K.M 6/000 to 8/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2692/17-18 Dtd:04/10/17 Rs/-1481000 |  |  | 1480439 | [6 empty] | Work under Tendering Process
72 |  |  | Trikaripur | Providing strip B.T to Cheemeni-Palavayal-Odakkolli Road K.M 25/000 to 26/500. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2692/17-18 Dtd:04/10/17 Rs/-15L |  |  | 1499725 | [6 empty] | Work under Tendering Process
73 |  |  | Trikaripur | Providing covering slab and repairs existing drain of cheruvathur padna edachakai road K.M 3/000 to 5/000 | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
74 |  |  | Trikaripur | Urgent surface rectification to Thrikkaripur Payyannur Byepass road KM.0/000 to 0/500. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
75 |  |  | Trikaripur | Urgent surface rectification to Cheemeni Kakkadavu road KM.7/900 to 8/000 and 9/000 to 11/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [10 empty] | Work under Tendering Process
1 |  |  | Manjeshwar | OR - 2017-18 - Supplying and laying shelmac under Roads Section Manjeswar Rs. 5.00 Lakhs - H/A : 3054-03-337-99 | 5 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 3890/2017-18 Dated: 13/10/2017 |  | Sarda Agencies | [7 empty] | Supplying Shelmac. Work Order Issued For laying Re - Tendered
2 |  |  | Manjeshwar | OR - 2017-18 - Construction of culvert and CC drain at Km 2/650 of Durgipalla Bejje Munnipady road - Rs. 10.00 Lakhs H/A : 3054-03-337-99 | 10 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 4303/17-18 Dated: 18/10/17
3 |  |  | Kasaragod | SR - 2017 -18 - Surface renewal to Mulleria - Nattakkal - Aripadavu road Km 0/000 to 1/000, Rs. 18.00 Lakhs H/A: 3054-03-337-97 | 18 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 4191/17-18 Dated: 16/10/17 |  | Subin Antony Manathoor(H) Kumbadaje(PO) | 1799448 | 1658776.53 | 2
4 |  |  | Kasaragod | SR - 2017 -18 - Surface renewal to Mulleria - Nattakkal - Aripadavu road Km 1/000 to 2/000, Rs. 18.00 Lakhs H/A: 3054-03-337-97 | 18 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 3956/17-18 Dated: 14/10/17
5 |  |  | Kasaragod | SR - 2017-18 - Surface renewal to Mullerial Nattakkal - Aripadavu road km 11/000 to 12/000 Rs. 12.00 Lakhs H/A; 3054-03-337-97 | 12 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 3998/17-18 Dated: 14/10/17
6 |  |  | Kasaragod | 1) RP - 2017-18 - Providing MSS between Km 6/000 to 10/310 at Madhur Patla - Kollangana road. Rs. 47.00 Lakhs H/A : 3054-03-337-98 | 47 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017
7 |  |  | Kasaragod | 2) RP -2017-18 - Supplying and laying shelmac under Roads Section Kasaragod Rs. 3.00 Lakhs H/A: 3054-03-337-98 | 3 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 3857/17-18 Dated: 17/10/17 & 3858/17-18 Dated: 13/10/17 |  | Sarda Agencies | [7 empty] | Supplying Shelmac. Work Order Issued For laying Re Tendered
8 |  |  | Uduma | OR - 2017-18 Surface rectification to Paduppu - Bandankai - Karivedakam road Km 0/000 to 1/750 Rs. 15.00 Lakhs H/A: 3054-03-337-99 | 15 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 3640/17-18 Dated: 12/10/17
9 |  |  | Uduma | OR - 2017-18 Surface rectification to Paduppu - Bandankai - Karivedakam road Km 1/800 to 3/000 Rs. 20.00 Lakhs H/A: 3054-03-337-99 | 20 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | 3641/17-18 Dated: 12/10/17
1 |  |  | Uduma | Providing covering slab overdrain to Udma Mullacherry road between km 0/000 to 1/000 | 25 | CE/R&B/KSD/Substitution/3/17-18. Dated 26/10/2017 | [10 empty] | Work under tendering progress
1 |  |  | Kasaragod | Providing Resurfacing bet Km 6/000 to 8/500 at Madhur- Patla Kollamgana road | 22 | CE/R&B/KSD/Substitution/2/17-18. Dated 20/10/2017 | [10 empty] | Work under tendering progress
2 |  |  | Kasaragod | ProvidingResurfacing bet Km 8/500 to 10/830 at Madhur- Patla Kollamgana road | 25 | CE/R&B/KSD/Substitution/2/17-18. Dated 20/10/2017 | [10 empty] | Work under tendering progress
Hill highway
1 |  |  |  | Investigation Estimate from Nandarapadavu to Chevar from 0/000 to 23/290 | 9.91 | GO (Rt) No. 942/2017 PWD Dated: 10-07-2017 | 1469/17-18 ` 9,91,000/- | EE/KSD/49/17-18 dated 14/09/2017 | Sri. K V Yoosuf, KV House, Bombrana PO, Kumbla | 990912 | 941450.61 | 15 days | 2017-08-25 |  |  |  | Work Completed
2 |  |  |  | Infrastructure Development works as part of Special Investment Scheme KIIFB - Investigation Estimate for preparing detailed project report for the work of Hill Highway Investigation Edaoparamba to Cevar ( 49.635 Km) | 21.00 | GO (Rt) No. 942/2017 PWD Dated: 10-07-2017 | 1471/17-18 `21,00,000/- | EE/KSD/46/17-18 dated 14/09/2017 | Sri. N. Haridasan, Kottakkal (H), Bandadka PO | 4209465 | 2050075.62 | 15 days | 2017-08-25 |  |  |  | Work Completed
3 |  |  |  | Investigation Estimate from Kolichal to Edaparamba from 0/000 to 24/400 | 14 | GO (Rt) No. 942/2017 PWD Dated: 10-07-2017 | 1471/17-18 `14,42,000/- | EE/KSD/48/17-18 dated 14/09/2017 | Sri. D M Ahammed, Deshamangalam (H), Badiradka PO, Kudlu | 4825043 | 1369804.07 | 30days | 2017-08-25 |  |  |  | Work in Progress
4 |  |  |  | Kolichal to Cherupuzha |  | GO (Rt) No. 942/2017 PWD Dated: 10-07-2017 | 1468/17-18 ` 12,60,000/- | EE/KSD/47/17-18 dated 14/09/2017 | Sri. D M Ahammed, Deshamangalam (H), Badiradka PO, Kudlu | 1449068 | 1196957 | 15 days | 2017-08-25 |  |  |  | Work in Progress
Stimulus Package
|  |  |  | Construction of bridge at Kottapuram across Thejaswini river connecting Cheruvathur & Nileshwar Grama Panchayaths(Trikaripur) | R 2330 L | G.O.(Rt) No. 1044/09 dt.14-7-09 | 278/CE/R/ 2009-10/302 | SE(K)74/10-11 dt.01-07-2010 | M/S Kerala State Construction Corporation Ltd, P.B.No.1944 , Kochi. |  | R 227443660 |  | 15-07-2010 | 14-01-2013 | extension applied upto 31/08/2017 |  | Approch road Work in Progress | 95%

## Sheet5 (hidden)
KERALA PUBLIC WORKS DEPARTMENT
ROADS DIVISION KASARAGOD
PROGRESS FOR THE MONTH OF SEPTEMBER 2017
Sl.No | LA Constituency | Name of Project | Estimate Amount | A.S No. Date & Amount | T.S No. Date & Amount | Agt.No & Date | Name of Contractor | Agreed. PAC | Date of site handing over | Date of completion as per agreement | Extended date of completion | Actual DOC | Present Status of works | Physical Progress (%) | Exp. Up to Current month | Remarks
1 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 15 | 16 | 17 | 18 | 19 | 20 | 22 | 24
I
2015-16
1 |  | Improvements to Edathodu - Neeleshwaram Road Km 15/500 to 8/300 | 300 | G.O. (Rt) No. 1930/2015/PWD dated, 22/12/2015 | [8 empty] | Estimate submitted for TS.Nomenclature of work(Chainage) to be changed
2 |  | Thekkil - Alatty Road 1st Phase | 400 | G.O. (Rt) No. 1930/2015/PWD dated, 22/12/2015 | 170/2015-16 dtd.15/02/2016 | SE(K)371/15-16 dtd.4/3/2016 | Sri.K.Moideenkutty Haji, PWD contractor, Pattuvathil , P.O.Thekkil | 35058353 | 2016-03-04 | 2017-03-03 |  |  | BT Work completed. Balance work in progress | 95%
3 |  | Improvements to Hosdurg-Panathur road(SH)Km 15/000 to 44/175(Ist reach) | 1500 | G.O. (Rt) No. 183/2016/PWD dated, 28/01/2016 | 444/16-17 Dtd :23/07/2016 | SE(K)11/17-18 dtd.25/5/2017 | M/s Kudroli Construction company | 116659938 | 2017-05-25 | 2018-01-24 |  |  | Initial level taken
2016-17
1 | Kanhangad | Improvements to Kanhangad Guruvanam Mekkatta Road b/w km 0/000 to 1/900 | 194 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 3709/2016-2017 dtd:25/03/2017 | SE(K)131/17-18 dtd.29/07/2017 | Sri.Rajes varkey PWD Contractor Karimpanakal(h) Plachikkara(P.O) | 17659999 |  |  |  |  | Work in progress
2 | Kasaragod | Improvements to Neerchal - Kottakani Madhur Road km 0/000 to 5/500(excluding kottakani bridge approach road) | 95 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 4296/2016-2017 dtd:31/3/2017 | [7 empty] | Agmt executed
3 | Thrikkaripur | Improvements to Chittarikkal Kunnumkai Road 1st phase b/w km 0/000 to 1/600 | 130 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 3726/2016-2017 dtd:25/03/2017 | SE(K)130/17-18 dtd.29/07/2017 | Sri.Rajes varkey PWD Contractor Karimpanakal(h) Plachikkara(P.O) | 11491961 |  |  |  |  | Agmt executed
4 | Udma | Improvements to Bevinja Aloor Eriyanni Road(last reach)from km 13/900 to 18/200 | 48 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | [8 empty] | work under Retender in process
5 | Udma | Improvements to Bandadukka Charnakochi Payaradukka Road km 0/000 to 3/000 | 48 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 2826/2016-2017 dtd:28/02/2017 | EE/KSD/15/17-18 dtd.29/05/2017 | M.S.Mohammed Rafeeq Masthikundu P.O.Muliyar | 3844887 | 2017-05-29 | 208/02/2018 |  |  | work in progress
6 | Udma | Providing BM & BC to Udma Thekkil Road from km 0/000 to 3/500 | 280 | G.O. (Rt) No. 179/2017/PWD dated, 14/02/2017 | 3781/2016-2017 dtd:27/03/2017 | SE(K)132/17-18 dtd.29/07/2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 23496874 |  |  |  |  | TS issued work to be tendered
7 | Udma | Improvements to Pallathur-Adoor-Pandi road km 0/000 to 9/350 1st phase (0/000 to 3/600) | 283 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4271/2016-2017dtd:31/03/2017 | SE(K)128/17-18 dtd.29/07/2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 22940573 |  |  |  |  | Selectio n notice issued . Agmt. to be executed
8 | Kasaragod | Providing BM & BC to Madhur-Patla-Kolangana road km 0/000 to 3/000 | 95 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 3781/2016-2017 dtd:27/03/2017 | [7 empty] | Submitted to ce for tender approval
9 | Kasaragod | Providing BM & BC to Perumbalakadavu-Nayanmarmoola-Erappakatta road km (1st reach) | 188 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [8 empty] | Submitted for TS
10 | Kasaragod | Provding BM & BC to Pannikkunnu-Shiribagilu road km 0/000 to 3/000 | 188 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [8 empty] | Submitted to ce for tender approval
11 | Kasaragod | Improvements to Kasaragod-Madhur road km 3/000 to 6/450 (BM &BC) | 188 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 185/2017-2018 dtd:29/04/2017 | SE(K) 80/17-18 Dtd:04/07/17 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 15331462 |  |  |  |  | Agmt executed
12 | Manjeshwar | BM & BC to Permuda Dharmathaduka Bayarpadavu road 1st reach km 0/000 to 3/450 | 228 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 992/2017-18 Dtd:21/05/2017 | SE(K) 154/17-18 Dtd:11/08/17 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 22636598 |  |  |  |  | Selection notice issued
13 | Manjeshwar | BM & BC to Dharmathadka-Kaniyala-Beloor-Beripadavu road km 0/000 to 7/400 | 350 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4274/16-17 Dtd:31/3/17 | SE(K) 47/17-18 Dtd:24/06/17 | M.A.Ameer Munabath Cengala | 34270450 |  |  |  |  | Agmt executed
14 | Kanhangad | Improvements to Nedumbu-Mavinakadayagayam roa din Kinanoor-Karinthalam GP | 95 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4294/16-17 Dtd:31/3/17 | SE(K) 22/17-18 Dtd:03/06/17 | Noufal P M Puthiyadukkam Chattanchal P O Thekkil | [5 empty] | Agmt executed
15 | Uduma | Improvements to Kottikulan Thachamgad road between 1/200 to 3/200 | 192 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [8 empty] | Submitted for TS
16 | Trikripur | Improvements to Chimeni Kunnumkai road by providing BM BC 0/000 to 1/100 | 132 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 4254/2016-2017 dtd:31/03/2017 | SE(K) 129/17-18 Dtd:29/07/17 | Sri.Rajes varkey PWD Contractor Karimpanakal(h) Plachikkara(P.O) | 11376528 |  |  |  |  | Agmt executed
17 | Trikripur | 2016/8761-Improvements to Parakole-Kinavoor-Kanyala-Palayi-Chathamath-Kariyamkode road km 7/000 to 12/000 | 176 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | 993/2017-2018 Dtd:21/05/2017 | [7 empty] | RetenderedSelection notice to be issued .
18 | Trikripur | Improvements to Kakadavu Badoor-Kambaloor-Cherupuzha road - West eleri & East Eleri GP | 126 | G.O(Ms)No.18/2017/PWD dtd.16/03/2017 | [8 empty] | MLA reguested for substitution
2017-18
1 | Manjeswaram | Surface renewal to Ubbathody-Cheppinadukka-Naikap Road from km 4/000 to 5/000 | 13.5 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
2 | Manjeswaram | Improvements to Majirpalla-Boddodi-Koottathaje Road from km 2/200 to 3/200 | 30 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
3 | Manjeswaram | Improvements to Majirpalla-Boddodi-Koottathaje Road from km 1/200 to 2/200 | 30 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
4 | Manjeswaram | Improvements to Kallije Komangala Kurudapadavu Road from 1/800 to 3/500 | 50 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
5 | Kasaragod | Surface renewal to Nekrampara-Arladka-Pundoor-Nerampady-Yethadka Road km 5/800 to 9/000 | 40 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
6 | Thrikkaripur | Improvements to Pothamkandam-Anapettipoyil-Padiyottchal Road | 75 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
7 | Udma | Improvements to Thekkil-Seezhoor road at km 4/000 to 6/200 (From Delijunction to Melparamba town) | 180 | G.O(Rt)No.1386/2017/PWD dated 15/09/2017
II
1 |  | RIDF XXI - Reconstruction of Kottekanni bridge at (Korathikundu) including approach road on Neerchal-Kottakanni-Madhur road in Kasaragod District | R 715.00 | G.O. (Rt) No. 1962/15 /PWD dt. 30-12-2015 Item No. 6 (Bridges) |  |  | Sri.M.A.Ameer, PWD contractor, Munambath House | [5 empty] | Approach Road work in progress | 93%
2 |  | Providing BM&BC to old MCC road km from 16/800 to 23/200, Bengara-Manjeshwar -Kuloor road 0/000 to 8/020 and Meeyapadavu-Chigurpade road km 0/000 to 1/5000 in Kasaragod District | R 900.00 | G.O. (Rt) No. 1962/15 /PWD dt. 30-12-2015 Item No. 10 (Bridges) | 416/2016-17 Dtd:15/07/2016 | SE(K)12/2017-18 Dtd:25/05/2017 | KUDROLI CONSTRUCTIONS CO. (P) LTD., 16A KURTARKAR COMMERCIAL, ARCADE 2ND FLR., KAZIWADA PONDA,GOA | 72923966 |  |  |  |  | Initial level taken
3 |  | RIDF-XXII Improvments to Pallathinkal-AnjankukkodKottodi bridge road | R 300.00 | /G.O.(Rt.) No.1608/2016/PWD dt.23/11/2016 Item No.29 - | 3940/2016-17 Dtd:29/03/2017 | SE(K)133/2017-18 Dtd:29/07/2017 | Sri. B.A. Shereef, PWD Contractor, Berka House, Kasaragod | 21903470 |  |  |  |  | TS issued. Work to be tendered
4 |  | Construction Mullacheri bridge in Uduma-Mullachery road | R 300.00 | /G.O.(Rt.) No.1608/2016/PWD dt.23/11/2016 Item No.33 - | [8 empty] | Work tendered
III
2016-17
Road work
1 |  | Improvements to Hosdurg-Panathur road by providing BM and BC from Km 24/000 to 42/00 in Kasaragod District |  | Go(Rt) No 1192/2016/PWD dated 20.08.2016 | [8 empty] | Govt. directed to kept in abeyance
2 |  | Improvements to Kayyur-Chembranganam-Palakkunnu road Km 0/000 to 10/900 and Link road 1.135 Km (Total 12.035 Km) in Kasaragod district |  | Go(Rt) No 1192/2016/PWD dated 20.08.2016 | [8 empty] | Investigation work Completed. DPR under preparation
3 |  | Improvements to Nileshwar-Edathodu road Km 0/000 to 13/000 in Kasaragod district |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [8 empty] | Investigation work Completed. DPR under preparation
4 |  | Improvements to Thekkil-alatty road Km 0/000 to 34/700 in Kasaragod District ) |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [8 empty] | Investigation work Completed. DPR under preparation
5 |  | Improvements to Kiliyalam-Varanhoor road |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [8 empty] | Investigation work Completed. DPR under preparation
6 |  | Improvements to Kalladka-Perla-Ukkinadka road Km 23/227 to 33/000 in Kasaragod District ) |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [8 empty] | Investigation work Completed. DPR under preparation
7 |  | Improvements to Kalladka-Cherkala road Km 33/000 to 52/194 in Kasaragod district |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [8 empty] | Investigation work Completed. DPR under preparation
8 |  | Improvements to Cheruvathur – Cheemeni – IT Park – Palavayal – Bheemanady – Mukkada Road Km 0/000 to 54/000 in Kasaragod Dist. |  | Go(Rt)No 1052/2016/PWD dated 01.11.2016 | [8 empty] | Investigation work Completed. DPR under preparation
Bridge Work
9 |  | Odankallu Bridge ) |  | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | [8 empty] | . DPRsubmitted for TS
10 |  | Puligochal-Kiltakayam Bridge |  | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | [8 empty] | Investigation work Completed
11 |  | Klayikode-Ramanchira Bridge |  | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | [8 empty] | Investigation work Completed
12 |  | Bheemanady Kalikadavu Bridge |  | Go(Rt) No 1496/2016/PWD dated 31.10.2016 | [8 empty] | Investigation work Completed
2017-18
Road work
1 | Trikaripur | Nileshwaram NH- Kacheriradav- Town- Byepass Road and bridge- Raja road improvement | 4000
2 | Uduma | Bovikkanam - Kanathoor - Kuttikole Road | 1500
3 | Kanhangad | Padnnakkad over bridge- Vellarikundu road ( including bridges) | 6000
4 | Kasaragod | Badiadka - Yathadka - Soolyapadhavu Road km 0/000 to 20/000 | 2800
5 | Manjeswaram | Maskumari- Kurudapadavu Road | 1000
6 | Manjeswaram | Construction of Valaiyapalam & rennovation of Kuloor Chinnala Road | 1500
7 | Kasaragod | Nekrampara -Arladka - Pundoor -Narampady - Yathadka road km 0/000 to 11/600 | 1500
8 | Kanhangad | Rakkole- Ennappara road | 2000
9 | Kanhangad | Mekkatt- Errikkulam road. | 1500
10 | Kanhangad | Padnnakkad over bridge- Vellarikundu road ( including bridges) | 6000
Bridge Work
11 | Udma | Construction of Chotta Bridge across Payaswini river in Muliyar Panchayath | 1500
12 | Kanhangad | Kanhangad Fly Over | 4000
13 | Kasargode | Construction of Bajpekadavu (Kubanoor) Bridge in manjeswar LAC | 1000
4
1 | Trikkaripur | LAC- Asset Development Sceme - 2014-15 Trikaripur LAC - Improvements to Mayicha-Kuttivayal-Poraik road km 0/000 to 0/500 in Kasaragod District | 15 | G.O. (Rt) No. 1847/2015/LSGD dated 20/06/15 Rs. 15 akhs | 371/16-17 dt.24/06/2016 Rs-15 | EE/KSD/23/16 dt.18/08/2016 | Muhammed Hazeem, Mangad Udma | 1242242 | 2016-08-18 | 2016-12-17 |  |  | Earth work , side protection in progress | 30%
2 | Kanhangad | Improvements to Thayelenkurunhi - Kappithottam Road KM 0/130 to 0/630 | 20 | G.O. (Rt) No. 3348/2015/LSGD dated 13/11/15 20 Lakhs | 1925/16-17 Dtd: 18/10/2016 | EE/KSD/104/16-17 Dtd:16/01/2017 | sri.Reji Joseph Kollamparambil House Malakkallu P O | 1553427 | 2017-01-16 | 2017-04-15 |  |  | Initial level submitted for approval
3 | Kanhangad | Improvements to Vetradi - Koliampara Road Km 0/000 to 1/200 | 25 | G.O. (Rt) No. 3348/2015/LSGD dated 13/11/15 25 Lakhs | 2121/16-17 Dtd: 04/11/2016 | EE/KSD/105/16-17 dtd.17/01/2017 | sri.M S Mohammed Rafique PWD Contractor Muliyar PO | 1874634 | 2017-01-17 | 2017-04-16 |  |  | Earth work completed, GSb Work in progress | 45
4 | Trikkaripur | Improvements to Veethukunnu-Ring road Km 0/000 to 0/650 in Pilicode Grama Panchayath | 25 | G.O. (Rt) No. 439/2016/LSGD dated 3/2/2016 25 Lakhs | 2138/16-17 dt.5/11/2016 | EE/KSD/84/16-17 dtd.26/12/2016 | Sri.E.Raveendran, PWD Contractor, Onakkunnu, Karivellur P.O, Kannur | 1848309 | 2016-12-26 | 2017-06-25 |  |  | Earth work completed, GSb Work in progress | 20%
5 | Kasaragod | Improvements to Churipallam-Mavinakkatta road Km 1/700 to 3/200 | 50 | G.O. (Rt) No. 399/2016/PWD/Tvm dated 18/2/2016 50 Lakhs | [8 empty] | Revised estimate submitted for 32.28 lakh from km 0/000 to 0/500
6 | Kanhangad | Improvements to Kakkod-Kondapadi-Chimmathode road Km 0/000 to 2/750 in Kinanoor-Karindalam Grama panchayath | 25 | G.O. (Rt) No. 817/2016/LSGD dated 25/02/16 25 Lakhs | 1201/17-18 Dtd:23/06/2017 | EE/KSD/35/17-18dt.10/08/2017 | V V Manojan PWD Contractor Nileshwaram | 2212458 | 2017-08-10 | 2018-01-09 |  |  | Agmt. Executed
7 | Kanhangad | Improvements to Chamundikunnu-Kizhakkethumbodi road Km 0/518 to 1/33o in Panathadi Grama Panchayath | 30 | G.O. (Rt) No. 817/2016/LSGD dated 25/02/16 30 Lakhs | 572/2017-18 Dtd:9/05/2017 | EE/KSD/30/17-18dt. | Mohammed Sakkeer PWD Contractor Bevinja | 2407601 |  |  |  |  | Agmt. Executed
8 | Kanhangad | Ottakolly-ManchuchalKani road Km 3/500 to 3/850 in Balal Grama Panchayat | 15 | G.O. (Rt) No. 817/2016/LSGD dated 25/02/16 15 Lakhs |  |  | Shaiby Sebastian PWD Contractor | [5 empty] | Agmt. Executed
9 | Trikaripur | LAC-ADS 2015-16 Trikaripur Constituency - Construction of 6m span culvert and approach road at Kariyamkod-Podothuruthi-Chathamath road in Nileshwaram Muncipality. | 45 | GO(Rt.)No.1085/2016/PWD dtd.20/07/2016. | 2570/2016-2017 dated; 07/01/2017 |  | sri.M S Mohammed Rafique PWD Contractor Muliyar PO | [5 empty] | Culvert completed. Approach road work in progress(80%)
10 | Trikkaripur | Improvements to Muttuchirathattu- kinathady road Km 0/190to 0/840 in Trikkaripur LAC |  |  | 2066/2016-17 dated; 27/10/2016 | EE/KSD/100/16-17 dt.09/01/2017 |  |  | 2017-01-09 | 2017-04-08 |  |  | Initial level taken and reported to ce
5
Kasaragod Package
1 |  | Construction Kannankai Bridge in Trikaripur LAC | 360 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.1 | 238/15-16 dtd 20/02/16 for Rs.290 L |  | U.Muhammed Kunhi, PWD Contractor, Panalam House Cheroor |  | 2016-06-17 | 2017-12-07 |  |  | Piling Work completed
2 |  | Construction of Ayamkadavu Bridge in Periya-Ayampara-Perladukkam road | 1400 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.7 | G.O.Rt.No. 1493/2015/PWD dtd.1/10/2015 |  |  |  | 2016-12-31 | 2018-06-30 |  |  | Piling Work completed & Pile cap completed Pier& pier cap completed
3 | Trikaripur | Construction of Vanhangad Bridge | 500 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.10 | 243/15-16 dtd.20/02/16 for Rs.480 L |  | M/s Chattanchal Engineering Company (P) Ltd. |  | 2016-07-15 | 2018-06-10 |  |  | Piling Work in progress out of 24 piles 21 pile completed.out of3 spans 1 span girder & Deck slab completed | 60%
4 | Kasaragod | Construction of Vidyagiri Bridge | 250 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.15 | 244/15-16 dtd 20/02/2016 for Rs.250 L |  | Mohammed Asharaf, PWD Contractor, Etthirthodu, P.O.Edneer, Kasaragod |  | 2016-06-20 | 2017-06-14 |  |  | Completed | 100%
5 | Kanhangad | Improvments to Korathipathi-Ranipuram road | 150 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.20 | 4/CE/R/15-16 /4 dtd.18/4/ 2015 |  | Sei.M.A.Usman, PWD Contractor, Masthikundu House, P.O.Muliyar |  | 2015-11-09 | 2016-05-08 |  |  | Work Completed | 100%
6 | Manjeshwar | Improvments to Hill highway from Purushangadi to Idiyadukka ( 2nd reach) km 4/700 to 6/500 and 9/200 to 17/200 | 650 | G.O.(Rt)No.16/2015/Plg TVM dtd 08/01/2015, Sl.No.21 | [8 empty] | In view of NATPAC report decide to obtain clarification from Govt. in this regard
7 |  | Kasaragod Develoment Package - 2015-16 Reconstruction of Painikkara Bridge at km 24/600 of Hosdurg -Panathur road in Kasaragod District | 20 | G.O.(ms)No.3/2016/Plg Tvm dtd 14/01/2016, Sl.No.49 for Rs. 250L | 242/15-16 dtd.20/02/2016 for Rs. 240 L |  | U.Mohammed Kunhi, PWD contractor, Panalam House |  | 2016-06-17 | 2017-06-07 |  |  | Piling Work & deck slab work completed | 70%
8 |  | Kasaragod Develoment Package - 2015-16 Improvements to Olavara Udumbumthala-Vellappu road in between 0/000 to 6/500 in Kasaragod District | 200 | G.O.(ms)No.3/2016/Plg Tvm dtd 14/01/2016, Sl.No.48 for Rs. 200L | 10/16-17 dtd.15/04/2016 for Rs.200 L |  | U.Mohammed Kunhi, PWD contractor, Panalam House |  | 2016-08-16 | 2017-02-15 |  |  | GSB &WMM completed Balance work in progress | 50%
9 |  | Kasaragod Development Package 2015-16 - Improvements to Hosdurg-Panathur(SH) road (Chemberi to Kolichal) working chainage between km 42/00 to 44/175) in Kasaragod District | 500 | G.O.(ms)No.3/2016/Plg Tvm dtd 14/01/2016, Sl.No.47 for Rs. 500L | 138/15-16 dtd.11/02/2016 for Rs.500 L |  | Sri.K.Moideen kutty Haji, PWD Contractor, Pattuvathil House, P.O.Thekkil |  | 2016-03-04 | 2016-11-03 |  |  | GSB completed.WMM Completed from 42/700 to 44/175 | 50%
10 |  | Cherupuzha-Chittarikkal road (2nd phase) | 350 | G.O.(Rt.) No.77/2016/Plg.Tvm dated 20/02/2016 | 11/16-17 dt.15/4/2016 Rs.350 L |  | Sri.Hunifa Meethal, PWD contractor | [5 empty] | GSB work completed. Balance work in progress | 50%
11 |  | Strengthening of Quality Control Sub division District Lab functioning under PWD by Purchasing equipments | 25 | GO(Rt.)No.544/2015/Plg./ dtd.22/12/2015 | [8 empty] | Revised estimate submitted for approval.
12 |  | Improvements to Nileshwar-Kottappuram -Thuruthi-Cheruvathur road km 0/000 to 11/000 | 800 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Estimate submitted for TS
13 |  | Improvements to Periya-Odayanchal road km 0/000 to 1/000 | 200 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Investigation Work in Progress
14 |  | Improvments to Mavila Kadappuram-Udinur Kadappuram-Ezhimala road km 0/000 to 12/000 | 200 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Estimate for TS under preparation
15 |  | Improvements to Ukkinadka-Elakana road km 0/000 to 4/000 | 910 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Estimate for TS under preparation
16 |  | Improvements to Chowki-Uliyathadka SP Nagar Koppa road km 0/000 to 1/100 | 125 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 1027/17-18 | [7 empty] | TS issued work to be tendered
17 |  | Improvements to Bheemanadi-Mukkada road km 3/800 to 4/200 | 100 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 3998/16-17 | [7 empty] | TS issued work to be tendered
18 |  | Improvements to Panathur-Kallappalli road km 3/000 to 5/200 | 200 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Estimate submitted for TS
19 |  | Construction of Thadiyan vallappu bridge at Periya Odayanchal road | 275 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Agmt.Executed
20 |  | Construction of Bridge at Perumbatta across Thejaswini river in Cheemeni-Palavayal-Odakkolli road | 990 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Estimate submitted for TS
21 |  | Improvements to Thekkil Kizhoor road (0/000 to 3/500) | 300 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 232/17-18 | [7 empty] | Agmt.Executed
22 |  | Improvments to Edathila valappur-Channadukkam-Mangod road in between km 3/800 to 5/500 | 100 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | 3853/16-17 | [7 empty] | TS issued work to be tendered
23 |  | Construction of Pallathur Bridge in Pallathumpara in Adoor Pandi road in Udma LAC in Kasaragod District | 758 | G.O.(Ms)No.8/2017/Plg. dtd.17/02/ 2017 | [8 empty] | Estimate for TS under preparation
24 |  | Construction of Palathera Bridge across maicha river in cheruvathur vengat maicha Road | 700 | G.O.(Ms)No.174/2017/Plg. dtd.27/ 03/ 2017 | [8 empty] | Investigation work under tendering process
One Time Maintanance
1 |  | One time maintenance of village roads/ODR's IV-Part-III 2015-16-various roads in Chemmanadu and Chengala Grama panchayath and Puthiyaparappa in Kasaragod District- Package No.1 | 65 | GO(MS)No.109/2015-16/PWD,, TVM dated 21/12/2015 | CR/340/15-16 dtd.27/02/2016 | SE(K)150/16-17Dt:09/06/16 | Noufal | 6906377 | 2016-09-09 | 2017-01-08 |  |  | work in progress
2 |  | One time maintenance of village roads/ODR's 2015-16 in Kasaragod Distriect mangalpady grama panchayath Package-1 | 88 | GO(MS)No.59/2015/PWD,, TVM dated 03/07/2015 | CR/47/2015-16 Dtd:9/7/15 | SE(K)405/15-16Dt:04/03/16 | V.P.Abdul khader | 9675162 | 2016-03-04 | 2016-07-03 |  |  | Work in progress
3 |  | One time maintenance of village roads/ODR's -III-2015-16 in various roads in Kasaragod municipality | 132 | GMS)No.76/2015/PWD,TVM dated 18/09/2015 | CR/243/2015-16 Dtd:9/12/15 | SE(K)404/15-16Dt:04/03/16 | V.P.Abdul khader | 9626423 | 2016-03-04 | 2016-07-03 |  |  | Work in progress
4 |  | One time maintenance of village roads ODR's-2015-16- in Kasaragod Distriect Vorkady grama panchayath package-2 | 60 | GO(MS)No.59/2015/PWD, TVM dated 03/07/2015 | CR/44/2015-16 Dtd:9/7/15 | SE(K)72/15-16Dt:01/09/16 | K.Abdul Rahiman | 5656794 | 2015-09-01 | 2015-12-31 |  |  | Work completed
5 |  | One time maintenance of vilalge roadsODR's 2015-16-Various roads in Bedadukka-Kuttikole and Chemmanadu grama oanbchayath in Kasaragod District-Package-2 | 130 | GO(MS)No.107/2015/PWD, TVM dated 21/12/2015 | CR/341/2015-16 Dtd:29/2/16 | SE(K)107/16-17Dt:19/7/16 | B.A.Shereef | 12530567 | 2016-07-19 | 2016-11-18 |  |  | Work in progress
6 |  | One time maintenance of village roads ODR's-III-2015-16- in Kasaragod Distriect in Kumbadaje-Badiadka-Bellur and Karadka-package-2 | 150 | GMS)No.76/2015/PWD, dated 18/09/2015 | CR/246/2015-16 Dtd:9/12/15 | SE(K)56/16-17 Dt:08/6/16 | K.V.Yoosaf | 16887916 | 2016-06-08 | 2016-09-07 |  |  | Work in progress
7 |  | One time maintenance of village roads ODRs-2015-16 in Kasaragod Distriect Manjeshwar grama panchayath Package-3 | 60 | GO(MS)No.59/2015/PWD, TVM dated 03/07/2015 | CR/49/2015-16 Dtd:10/7/15 | SE(K)344/15-16 Dt:01/03/16 | K.Abdul Rahiman | 6259728 | 2016-03-02 | 2016-07-01 |  |  | Work completed
8 |  | One time maintenance of village roads ODRs-III 2015-16-Various roads under Mogral Puthur grama panchayath-Package-3 | 119 | GO(MS)No.76/2015/PWD, TVM dated 18/09/2015 | CR/245/2015-16 Dtd:9/12/15 | SE(K)62/16-17 Dt:09/06/16 | M.A.Iqbal | 12520033 | 2016-06-09 | 2016-10-08 |  |  | Work in progress
9 |  | One time maintenance of village roads ODRs 2015-16 in Kasaragod District-Paivalike and Puthige grama panchayath-Package-4 | 74 | GO(MS)No.59/2015/PWD, TVM dated 03/07/2015 | CR/43/2015-16 Dtd:10/7/15 | SE(K)71/15-16 Dt:01/08/16 | K.Abdul Rahiman | 7317431 | 2015-09-01 | 2015-12-31 |  |  | Work in progress
10 |  | One time maintenance of village roads ODRs-III- 2015-16 in Kasaragod District-Changala grama panchayath-Package-4 | 132 | GO(MS)No.2015/PWD, dated18/09/2015 | CR/244/2015-16 Dtd:9/12/15 | SE(K)63/16-17 Dt:08/06/16 | M.A.Iqbal | 13883253 | 2016-06-09 | 2016-10-08 |  |  | Work in progress
11 |  | Pme time maintenance of village roads ODRs 2015-16 in Kasaragod District- Kumbala grama panchayath-Package-5 | 54 | GO(MS)No.59/2015/PPWD, dated 03/07/2015 | CR/48/2015-16 Dtd:10/7/15 | SE(K)230/15-16 Dt:13/11/15 | A.K.Thouseef | 5835381 | 2015-11-16 | 2016-03-15 |  |  | Work in progress
12 |  | One time maintenance of village roads OdRs 2015-16 -Part-I in Kasaragod district- Puthige gramma pabchayath-Package-6 | 90 | GO(MS)No.59/2015/PPWD, dated 03/07/2015 | CR/45/2015-16 Dtd:10/7/15 | SE(K)406/15-16 Dt:04/03/16 | V.P.Abdul khader | 9711134 | 2016-03-04 | 2016-11-03 |  |  | Work in progress
13 |  | One time maintenance of village roads ODRs 2015-16 in Kasaragod District Enmakaje gramma panchayath-Package-7 | 74 |  | CR/46/2015-16 Dtd:10/7/15 | SE(K)343/15-16 Dt:01/03/16 | C.H.Abdul Nizar | 8131582 | 2016-03-01 | 2016-06-30 |  |  | Work in progress
14 |  | One time maintenance of villages Roads ODRs Phase IV Part -I in various roads in kanhangad,madian-Ajanoor,kodom belur,madikai-pullur-periya,pallikkara &badaduka Grama Panchayath in kasaragod district |  | GO(MS)No.107/2015/PPWD, dated 21/12/2015 |  | SE(K)149/16-17 Dt:01/03/16 | V.V.Manojan | 15354670 | 2016-03-01 | 2016-08-31 |  |  | Work in progress
15 |  | One time maintenance of village and ODRs Phase IV-Part -I (Kanhangad and TKR LAC)in various panchayath under PWD Roads section west eleri in kasaragod district Pakage 3 | 110 | GO(MS)No.109/2015/PPWD, dated 21/12/2015 | CR/16/2016-17 Dtd:3.06.2016 | SE(K)143/16-17 Dt:19/08/16 | Simson Vincent | 9887875 | 2016-08-19 | 2016-11-18 |  |  | Work in progress
16 |  | One time maintenance of villages Roads ODRs Phase IV Part -I in various roads in karindalam,kayyur cheemeni-pilicode,cheruvathur,Trikaripur,nileshwar,padanna&valiyaparamba Grama Panchayath in kasaragod districtOne time maintenance of village and ODRs under Roads Section Nileshwar | 190 | GO(MS)No.109/2015/PPWD, dated 21/12/2015 | CR/13/2016-17 Dtd:5.08.2016 | SE(K)153/16-17 Dt:19/08/16 | M.V.Kunhikoran | 16495338 | 2016-08-19 | 18/11/22016 |  |  | Work in progress
6
Pre monsoon 2016-17
1 |  | Urgent potholes filling to Eriya Kanhiradukkam road Km. 0/000 to 3/100. |  |  | AEE/TS/368/16-17 Dt. 22.06.2017 | AEE/H/05/ 2016-17 Dt. 25.07.2016 | Sri, AV Sreedharan | 298364/- |  |  |  |  | in progress ( work pending due to vigilance enquiry )
Post Monsoon 2016-17
1 | Kanhangad | Alamipally Areekadavu road km.0/000 to 2/100 | 14 | SLTF Dt. 05.09.2016 ( CE/R&B/TF/KSGD/03//2016-17 | EE/TS/1308/2016-17 Dtd.02.10.16 | EE/KSD/113/2016-17 Dtd:7/02/2017 | Udma LCCS | 1217334 | 2017-02-07 | 2017-05-06 |  |  | This work is proposed for cancellation and new work arranged
1 | Kasaragod | Kundamkuzhi Moonamkadavu Periya road km.1/200 to 2/700 | 15 | SLTF Dt. 05.09.2016 ( CE/R&B/TF/KSGD/03//2016-17 | EE/TS/1310/2016-17 Dtd.02.10.16 | EE/KSD/80/2016-17 Dtd:21/12/2016 | M.S. Mohammed Rafeeque. Muliyar | 1136017 | 2016-10-02 | 2017-01-01 |  |  | bitumen issued
1 | Trikaripur | OR 2016-17 - BT surface rectification works on Athudra-Kooliyadu-Peringara Road | 20 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [8 empty] | work tendered
2 | Trikaripur | OR 2016-17 - BT surface rectification works on Mavilakadappuram-Valiyaparamba Road (Swa,mi madam portion) | 20 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [8 empty] | Letter submitted for name of work correction. ( Major work in KDP )
3 | Trikaripur | OR 2016-17 - BT surface rectification works on Trikaripur-Payyannur road from Thattarkkadavu Palam to Annoor | 10 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [8 empty] | Quotation submitted for approval
4 | Trikaripur | OR 2016-17 - BT surface rectification works on Cheruvathur-Cheemeni-Thaliyaramada Road from km 0/000 to 2/500 road | 15 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3259/2016-17 dated 14/3/17 |  | Sri. A.K. vinod Karyamkode | [5 empty] | Tendered
5 | Trikaripur | OR 2016-17 - BT surface rectification works on Cheemeni-Palavayal-Odakkolli Road on km 25/000 to 30/000 | 20 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | [8 empty] | Quotation invited
6 | Udma | OR 2016-17 - BT surface rectification works on Bandadukka-Manadukka-Kolichal road from km 0/300 to 3/000 | 15 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 2942/2016-17 Dated: 07/03/2017 | EE/KSD/16/2017-18 Dated: 01-06-2017 | N. Haridasan | 1530615/- | 2017-04-20 | 2017-06-19 | Nil | 2017-05-11 | Completed | 100%
7 | Udma | OR 2016-17 - BT surface rectification works on Bandadukka-Manadukka-Kolichal road from km 5/000 to 7/500 | 15 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 2940/2016-17 Dated: 07/03/2017 | EE/KSD/17/2017-18 Dated: 01-06-2017 | N. Haridasan | 1514546/- | 2017-04-20 | 2017-06-19 | Nil | 2017-05-11 | Time extension Granded up to 31/12/2017
8 | Udma | OR 2016-17 - BT surface rectification works on Bekal-Panayal Road from 0/000 to 1/600 | 25 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3304/16-17 Dt 23/3/17 | EE/KSD/32/2017-18 Dated: 18/07/2017 | Majeed Bendichal | 2615372 | 2017-07-18 | 2018-01-17 |  |  | Not started due to rain
9 | Udma | OR 2016-17 - BT surface rectification works on Bekal-Panayal Road from 1/900 to 3/500 | 25 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3606/16-17 Dt 23/3/17 | EE/KSD/33/2017-18 Dated:18/07//2017 | Majeed Bendichal | 2586500 | 2017-07-18 | 2018-01-17 |  |  | Not started due to rain
10 | Udma | OR 2016-17 - BT surface rectification works on Adoor-Pandy road from km 0/000 to 5/750 | 10 | CE/R&B/TF/KSGD/5/2016-17 DT. 18/02/2017 | 3053/206-17 Dated: 10/03/2017 | EE/KSD/26/2017-18 Dated: 28-06-2017 | N. Haridasan | 1047623/- | 2017-06-28 | 2017-11-27 | Nil |  | Work in Progress
1 | Kanhangad | BT patches and strip BT to Hosdurg-Panathur road Km 24/000 to 26/000 | 15 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2964/16-17 Dt 7/3/17 | EE/KSD/05/17-18 Dt 02/5/17 | Anil Jose, Padimaruth | 1488532/- |  |  |  |  | Bitumen issued
2 | Kanhangad | Surface Rectification by BT patches and strip BT to Odayanchal-Cherupuzha road Km 3/000 to 5/000 | 15 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2973/16-17 Dt 7/3/17 | EE/KSD/04/17-18 Dt 02/5/17 | Anil Jose, Padimaruth | 1430387/- |  |  |  |  | Collection in progress
3 | Kanhangad | Providing BT patches and strip BT to Hosdurg-panathur road Km 32/000 to 33/500 | 12 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2962/16-17 Dt 7/3/17 | EE/KSD/02/17-18 Dt 17/4/17 | TJ Joseph Joy Kallar | 1195551/- |  |  |  |  | in progress 50% completed
4 | Kanhangad | Providing BT patches and strip BT to Hosdurg-panathur road Km 38/000 to 39/000 | 8 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2951/16-17 Dt 7/3/17 | EE/KSD/03/17-18 Dt 17/4/17 | TJ Joseph Joy, Kallar | 796115/- |  |  |  |  | Collection in progress
5 | Kasaragod | Surface rectification to Pernadka - Ramdas nager Road at Km 0/000 to 4/000 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/01/17-18 Dated: 12/04/2017 | Abdul Sherif.M | 931360/- | 2017-04-12 | 2017-06-11 |  |  | Work in Progress
6 | Kasaragod | Providing strip Bt to the Narampady-Ajjimoola-Vodamkallu-Vidyagiri road between Km 0/000 to 5/000 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3422/16-17 Dated:20-03-2017 | EE/KSD/13/17-18 Dated: 22/05/2017 | BA Abdul Khader | 1025985/- | 2017-05-22 | 2017-07-21 |  |  | Work in Progress
7 | Kasaragod | Providing stip BT to the Mulleria-Nattakkal-Ariapadavu road betweeen Km 2/000 and 8/000 | 5 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 2999/16-17 Dated: 09/03/2017 | AEE/KSD/15/2016-17 Dated: 17/08/2017 | B.A Shareef | 477427/- | 2017-04-28 | 2017-06-27 |  |  | Work in Progress
8 | Kasaragod | Providing strip BT to the Nekrampara - Arladka - Pundoor - Narampady - Yethadka Road between Km 9/000 and11/600 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 81/17-18 Dated: 25/04/2017 | EE/KSD/14/2017-18 Dated: 22/05/2017 | B. A Abdul Khader | 1034541/- | 2017-05-22 | 2017-07-21 |  |  | Work Compled
9 | Kasaragod | Surface rectification to Bovikanan - Bevinje Road at Km 3/000 to 4/400 | 8 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/08/17-18 Dated: 08/05/2017 | Araf. P.B | 766487/- | 2017-05-08 | 2017-07-07 |  |  | Work in Progress
10 | Kasaragod | Surface Rectification to Bevinje-Aloor-Iriyanni road Km 0/000 to 1/000 | 7 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/09/17-18 Dated: 08/05/2017 | Araf. P.B | 676860/- | 2017-05-08 | 2017-07-07
11 | Manjeshwar | Re- Construction of collapsed RCC Culver (6m span) at Km 0/900 of Durgipalla - Bejja - Munnipady Road | 20 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 |  | EE/KSD/20/16-17 Dated: 14/06/2017 | Iddin Kunhi. | 1498340/- |  |  |  |  | Work in Progress
12 | Manjeshwar | Surface Rectification to Majeerpalla - Kolyoor Temple Donikallu - Pollakaje - Meeyapadavu Road Km from 0/000 to 1/500 | 15 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3444/16-17 Dated: 20-03-2017 | EE/KSD/6/2017-18 Dated: 04-05-2017 | K Abdul Rahiman | 1416670 | 2017-05-04 | 2017-07-03 |  |  | Work in Progress
13 | Manjeshwar | Providing Strip B-T to Kunjathoor-Kedumbadi-Nandarapadavu Road km from 1/000 to 2/600,4/300 to 6/700 and 8/800 to 9/100 | 10 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3445/16-17 Dated: 20-03-2017 | EE/KSD/9/2017-18 Dated: 04-05-2017 | K Abdul Rahiman | 944015/- | 2017-05-04 | 2017-07-03 |  |  | Work in Progress
14 | Manjeshwar | providing Strip B-T to Majeerpalla-Agra road Km 0/000 to 1/000 | 5 | CE/R&B/TF/KSGD/7/2016-17 DT.25/02/2017 | 3019/16-17 Dated: 19-03-2017 | AEE/KSD/01/17-18 Dated: 21/04/2017 | K Abdul Rahiman | 471636/- | 2017-05-04 | 2017-07-03 |  |  | Work in Progress
1 | Kasaragod | Surface renewal to Perumbalakadavu-Nayammarmoola-Erappakkatta Road km 1/000 to 3/000 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [8 empty] | Substituted Order Dated on 29-03-2017
2 | Kasaragod | Surface renewal to Badiadka-Barla-vidyagiri-Muniyoor Road km 2/000 to 3/000 | 18 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1149/17-18 Dated: 09-06-2017 | [7 empty] | Work in Re Tendering Process
3 | Kasaragod | Surface renewal to Ramdas Nagar-Parakatta Road km 0/000 to 2/250 (balance portion) | 7 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 4194/16-17 Dated: 30/03/2017 | EE/KSD/23/17-18 Dated: 17-06-2017 | V.P.Abdulkhader V.P(H) P.O.Mogral | 753484 | 2017-06-17 | 2017-11-16 |  |  | Work in Progress
4 | Udma | Surface renewal to Periya-Odayamchal road between km 8/500 to 9/500 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1166/17-18 Dt. 14/6/17 | [7 empty] | Tendered
5 | Udma | Surface renewal to Kundamkuzhi-Moonamkadavu-Periya road km 5/000 to 7/000 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1167/17-18 Dt.14/6/17 | [7 empty] | Tendered
6 | Udma | Surface renewal to Bovikanam-Kanthur Road km 5/000 to 6/800 | 18 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 4443/16-17 Dated: 30/03/2017 | [7 empty] | Work in Progress
7 | Udma | Surface renewal to Koliyadukam-Perumbalakadavu road km 0/000 to 2/000 | 24 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 4176/16-17 Dated: 30/03/2017 | EE/KSD/24/17-18 Dated: 17-06-2017 | Mohammed Sunaif.C.M MAH Compound Chengala(PO) | 149854 | 2017-06-17 | 2017-12-16 |  |  | Work in Progress
8 | Udma | Surface renewl to delampady Panjikal road 3/500 to 4/500 | 15 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [8 empty] | Work in Re Tendering Process
9 | Manjeshwar | Surface renewal to Bakery Junction Kavisubramnya Temple thoudugoli road from km 2/230 to 3/000 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 113/17-18 Dated: 27/04/2017 | EE/KSD/22/17-18 Dated: 14-06-2017 | Mohammed Sakeer, Bevinje, Thekkil Ferry | 2209963/- |  |  |  |  | Work in Progress
10 | Manjeshwar | Surface renewal to Kuloor-Chinala Road km 0/000 to 1/500 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 571/17-18 | EE/KSD/27/17-18 Dated: 04/07/2017 | V.P. Abdul Khader | 2183835 | 2017-07-04 | 2018-01-03 |  |  | Work in Progress
11 | Kanhangad | Surface renewal to Anakallu-Pookayam-Malakallu(Extension)km 1/200 to 4/500 | 25 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 574/17-18 Dt.9/5/17 |  | Sebastian MD, Malakkallu | [5 empty] | Tendered
12 | Kanhangad | Surface renewal to Periya-Odayamchal road between km 8/500 to 9/500 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [8 empty] | duplication work as no.4
13 | Kanhangad | Surface renewal to Chamattamvayal-Kalichanadukam road km 3/000 to 4/000 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1151/17-18 Dt.9/6/17 | [7 empty] | Tendered
14 | Kanhangad | surface renewal to Chullikkara-Kuttikole road km 5/000 to 6/500 | 12 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 1006/2017-18 dated 22/5/17 |  | G.S. Rajeev Malakkallu | [5 empty] | Tendered
15 | Kanhangad | Surface renewal to Chullikkara-Kuttikole road km 7/500 to 9/000 | 16 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 573/2017-18 dated 9/5/17 |  | G.S. Rajeev Malakkallu | [5 empty] | Tendered
16 | Trikaripur | Surface renewal to Odayanchal Cherupuzha road km 20/400 to 22/000 | 17 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [8 empty] | Tendered
17 | Trikaripur | Surface renewal to Chittarikkal-Kunnumkai road km 9/000 to 10/500 | 17 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | 575/2017-2018 dt :09/05/2017 Rs/-12L |  | Joseph joy Kallar PO Rajapuram | [5 empty] | Tendered
18 | Trikaripur | Surface renewal to Cheemeni-Palavayal-Odakolli road km 21/500 to 23/000 | 13 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [8 empty] | Tendered
19 | Trikaripur | surface renewal to Peralam-Kamballur road km 0/000 to 1/000 | 8 | CE/R&B/TF/KSGD/9/16-17/ DT. 22/03/2017 | [8 empty] | Tendered
| Kanhangad | Rectification of surface damages to Chemmattamvayal-Kalichanadukkam road km 10/000 to 14/250 | 10 | CE/R&B/TF/KSGD/11/2016-17 DT. 28/03/2017 | 43 /17-18 Dt.22/4/17 | EE/KSD/19/17-18 Dated: 01/07/2017 | Pradyumna.B.K Bekal Fort Kasaragod | 1082830 |  |  |  |  | GSB in progress
| Kanhangad | Rectification of surface damages to Chemmattamvayal-Kalichanadukkam road km 14/300 to 18/600 | 10 | CE/R&B/TF/KSGD/11/2016-17 DT. 28/03/2017 | 42 /17-18 Dt.22/4/17 | EE/KSD/18/17-18 Dated: 31/06/2017 | M. Abdul Basheer ,P.O.Bekal Fort | 1514546 |  |  |  |  | GSB in progress
| Kasaragod | RP 2016-17-Surface renewal to approach road Tb Kasaragod | 15 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [8 empty] | Work in Re Tendering Process
| Kasaragod | RP 2016-17-Surface renewal to Collectors Bengalow-Thamarakkuzhi link road km 0/000 to 0/165 | 5 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 78/17-18 Dated: 25/04/2017 | AEE/KSD/2/17-18 Dated: 11/05/2017 | D.M. Ahamad | 499084/- |  |  |  |  | Work in Progress
| Manjeshwar | RP 2016-17 -Surface renewal to NH Nayabazar-Kuthkodi-Sonkal-Prathap Nagar -Ambedkar road km 1/200 to 1/800 | 20 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 112/2017-18 Dtd:27/04/17 | AEE/KSD/34/17-18 Dated: 02/08//2017 | Abdul Saleem | 1790573 | 2017-08-02 | 2017-11-01 |  |  | Work in Progress
| Kanhangad | RP 2016-17-Surface renewal to Thulasseri-Nileshwaram Azhithala(via) Ajanur Kadappuram road km 4/500 to 6/800 | 20 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 1146 /17-18 Dt.22/4/17 | [7 empty] | Tendered
| Trikaripur | RP 2016-17 -Surface renewal to Chittarikkal-Kunnumkai road km 6/500 to 7/500 | 12 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 1007/17-18 Dt.22/05/17Rs/-12L |  | Joseph joy Kallar PO Rajapuram | 1199971 |  |  |  |  | Tendered
| Trikaripur | RP 2016-17 -Surface renewal to Chittarikkal-Kunnumkai road km 7/500 to 9/000 | 15 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | 883/17-18 Dt.17/05/17Rs/-15L |  | Joseph joy Kallar PO Rajapuram | 1499970 |  |  |  |  | Tendered
| Trikaripur | RP 2016-17-Surface renewal to Trikaripur-Vellappu Ayitti road km 0/300 to 0/900 | 7 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [8 empty] | Tendered
| Trikaripur | RP 2016-17-Surface renewal to Pothamkandam-Anepettypoil-Padiyottuchal road km 1/600 to 2/500 | 10 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [8 empty] | To be cancelled duo to new work in KDP
| Trikaripur | RP 2016-17-Surface renewal to Cheruvathur-Cheemeni-Thaliyammada road km 11/000 to 11/500 | 6 | CE/R&B/TF/KSGD/12/2016-17 DT. 29/03/2017 | [8 empty] | Tendered
| Kasaragod | Surface renewal to Perumbalakadavu-Nayammarmoola-Erappakkatta road km 3/000 to 5/000 | 25 | CE/R&B/TF/KSGD-SUB-1/2016-17 DT. 29/03/2017 | 730/17-18 Dated: 12/05/2017 | [7 empty] | Under Tender
| Kanhangad | RP 2016-17-Surface renewal to Thulasseri-Nileshwaram Azhithala(via) Ajanur Kadappuram road km 3/500 to 4/500 | 13 | CE/R&B/TF/KSGD-SUB-1/2016-17 DT. 29/03/2017 | 1147 /17-18 Dt.09/6/17
| Trikaripur | Resurfacing on Kayyur-Chembrakanam-Palakunnu Road | 20 | CE/R&B/TF/KSGD-S&S-1/2016-17 DT. 29/03/2017 | 918/2017-18 dated 18/5/2017 |  | Udayapuram labour contract Co-op society Ltd., | [5 empty] | Tendered
| Trikaripur | Resurfacing on Thaikadappuram-Azhithala Road | 20 | CE/R&B/TF/KSGD-S&S-1/2016-17 DT. 29/03/2017
| Trikaripur | Resurfacing on Nadakkavu-Udhinur-Machikkadu Road | 12 | CE/R&B/TF/KSGD-S&S-1/2016-17 DT. 29/03/2017 | [8 empty] | ODR
| Manjeshwar | Urgent rectification works between km 23/227 and 33/000 of Kalladuka-Cherkala road | 23.1 | CE/R&B/TF/KSGD-S&S-2/2016-17 DT. 31/03/2017 | 45/17-18 Dated: 22/04/2017 | EE/KSD/11/17-18 Dated: 16-05-2017 | B Abdul Khader | 2307934 | 2017-05-16 | 2017-07-15 |  |  | Completed
| Kasaragod | Urgent rectification works between km 33/000 and 50/500 of Kalladuka-Cherkala road | 24.45 | CE/R&B/TF/KSGD-S&S-2/2016-17 DT. 31/03/2017 | 44/17-18 Dated: 22/04/2017 | EE/KSD/29/2017-18 Dated: 04/07/2017 | Muhammad Kunhi. K., Kettumkal | 2557300/- | 2017-07-04 |  |  |  | Work in Progress
| Kasaragod | Urgent rectification works between km 2/000 and 20/000 of Badiadka-Yethaduka-Soolapadavu raod | 8.85 | CE/R&B/TF/KSGD-S&S-2/2016-17 DT. 31/03/2017 | 81/17-18 Dated: 25/04/2017 | EE/KSD/10/2017-18 Dated: 16/05/2017 | B. A. Shreef | 957016 | 2017-05-16 | 2017-07-15 |  |  | Completed
| Kasaragod | Road Safety Works - Providing metal Crush barrier at various accident spots uinder PWD roads Section, Kasaragod | 14.6 | KSD/2017/668 Dated: 20/03/2017 | 4143/16-17 Dated: 30/03/2017 | EE/KSD/21/2017-18 Dated: 14/06/2017 | Majeed Bendichal | 1311824 | 2017-06-14 | 2017-09-13
PRE MONSOON WORKS 2017-18 ( Other Than SLTF Works)
1 | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Muligadde - Beripadavu Road Km 2/750 to 4/100 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 148/17-18 Dated: 28/04/2017 | AEE/KSD/10/17-18 Dated: 02/08/2017 | K. Abdul Rahiman | 213506/- | 2017-05-23 | 2017-08-22 |  |  | Work in Progress
2 | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Perla - Soorambail Road between Km 3/900 and 5/800 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 156/17-18 Dated: 28/04/2017 | AEE/KSD/14/17-18 Dated: 21/06/2017 | A.K. Badsha | 265837/- | 2017-06-21 |  |  |  | Work in Progress
3 | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Morthana - Miyapadavu Road Km 0/000 to 0/700, 1/400 to 2/400 and 3/500 to 3/800 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 149/17-18 Dated: 28/04/2017 | AEE/KSD/04/17-18 Dated: 01/06/2017 | A.K. Thouseef | 248501/- | 2017-06-01 | 2017-06-30 |  |  | Work in Progress
4 | Manjeshwar | Pre Monsoon works 2017-18 BT Patches and potholes filling of Baikatta - Meeyapadavu Road Km 0/000 to 1/300 and 1/700 to 2/800 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 150/17-18 Dated: 28/04/2017 | AEE/KSD/05/17-18 Dated: 01/06/2017 | A.K. Thouseef | 944015/- | 2017-05-23 | 2017-08-22 |  |  | Work in Progress
5 | Uduma | Pre Monsoon works 2017-18 BT Patches to Kanhirathinkal - Vavadukkam Road between Km 0/000 to 5/000 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 152/17-18 Dated: 28/04/2017 | AEE/KSD/07/17-18 Dated: 22/06/2017 | A.R Abdul Rahiman | 266443/- | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
6 | Uduma | Pre Monsoon works 2017-18 BT Patches and potholes filling of Delampady - Panjikkal Road Km 0/000 to 3/500 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 154/17-18 Dated: 28/04/2017 | AEE/KSD/12/17-18Dated: 16/08/2017 | A.K. Badsha | 244263/- | 2017-06-21 |  |  |  | Work in Progress
7 | Uduma | Pre Monsoon works 2017-18 BT Patches and potholes filling of Bovikanam - Kanathur Road between Km 0/000 to 5/000 | 2.5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 151/17-18 Dated: 28/04/2017 | AEE/KSD/08/17-18 Dated:22/06/2017 | A.R Abdul Rahiman | 266577/- | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
| Udma | Urgent Special Repairs works to Uduma Mullassery road Km. 3/700 to 4/700 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
9 | Kasaragod | Pre Monsoon Works 2017-18 BT Patches to Kasaragod - Kanhangad Old SH | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 179/17-18 Dated: 29/04/2017 | AEE/KSD/06/17-18 Dated:22/06/2017 | A.R Abdul Rahiman | 321859/- | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
10 | Kasaragod | Pre Monsoon works 2017-18 BT Patches and potholes filling of Nellikkatta - Karmamthody Road Km 10/000 to 11/000 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 155/17-18 Dated: 28/04/2017 | AEE/KSD/11/17-18Dated: 16/08/2017 | A.K. Badsha | 320010/- | 2017-06-21 |  |  |  | Work in Progress
11 | Kasaragod | Pre Monsoon Works 2017-18 BT Patches to Madhur - Patla - Kolloangana Road between Km 3/000 to 8/020 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 147/17-18 Dated: 28/04/2017 | AEE/KSD/09/17-18Dated: 22/06/2017 | A.R Abdul Rahiman | 212919/- | 2017-06-05 | 2017-09-04 |  |  | Work in Progress
12 | Kasaragod | Pre Monsoon Works 2017-18 BT Patches and Pot holes filling of Nakrampara - Arladkka - Pundoor - Narampady Road between Km 0/000 to 6/010 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | 153/17-18 Dated: 28/04/2017 | AEE/KSD/13/17-18Dated: 16/08/2017 | A.K. Badsha | 214587/- | 2017-06-21 |  |  |  | Work in Progress
13 | Trikkaripur | Urgent Surface rectification to Payyanur -Kara Thalichalam road Km. 3/700 to 4/500 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
14 | Trikkaripur | Urgent Surface rectification to Cheemeni - Chanadukkam - Kakkadavu road Km. 3/000 to 4/000 | 4 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
15 | Trikkaripur | Urgent Surface rectification to Cheemeni - Chanadukkam - Kakkadavu road Km. 4/000 to 5/000 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
16 | Kanhangad | Urgent Special Repairs works to Chemmattamvayal - Kalichanadukkam road Km. 4/000 to 5/000 | 5 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
17 | Kanhangad | Urgent Special Repairs works to Thuillissery - Nileswaram - Azhithala (via. ) Ajanur kadappuram road Km. 0/000 to 0/500 | 3 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
18 | Kanhangad | Urgent Special Repairs works to T.B Savaparamba - Kotrachal road Km. 3/000 to 4/000 | 2 | CE/R&B/TF/KSGD-01/17-18 Dated: 25-04-2017 | [8 empty] | Quatation submitted for approval
1 | Manjeshwar | Strip BT of Sungathakatta - Nandarapadavu Road Km 0/000 to 1/500 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
2 | Manjeshwar | Strip BT of Morthana - Miyapadavu Road Km 0/700 to 1/400, 2/410 to 3/500 and 3/800 to 6/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
3 | Manjeshwar | Strip BT and Pot holes filling to Meeyapadavu - Baikatta Road Km 0/000 to 3/000 | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
4 | Manjeshwar | Strip BT and Pot holes filling to Chevar - paivalike Road from Km 0/000 to 3/600 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
5 | Manjeshwar | Strip BT to Kadambar Arimala Mazjid Road from Km 0/000 to 2/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
6 | Manjeshwar | Water Logged Portion Concrete Road pavement and CC Drain for Manjeshwaram - Ukkada Road from Km 11/600 to 11/700 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
7 | Manjeshwar | Strip BT and Pot holes filling to Durgipalla Bejja Munnipady Road from Km 0/000 to 2/500 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
8 | Manjeshwar | surface rectification between km 0/000 and 4/000 of Mundyathadukka-Mugu-Puthige Road | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
9 | Manjeshwar | Strip BT and Pot holes filling to Durgipalla Bejja Munnipady Road from Km 2/500 to 5/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
10 | Manjeshwar | Surface Renewal to Kumbla-Kanchikatta-kottekar-Naikapu Road km 3/700 to 4/400 | 12 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
11 | Manjeshwar | Construction of CC culvert and CC Drain at Km 8/300 of Permuda - Bayarpadavu Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
12 | Manjeshwar | Surface Renewal to Soorambail-Vaninagar-Kinningar Road km 1/000 to 2/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
13 | Manjeshwar | Strip BT and Pot holes filling at Km 3/900 to 4/400 of Muligadde - Beripadavu Rod | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
14 | Manjeshwar | Surface Renewal to Perla-Soorambail- Road km 3/900 to 5/800 | 24 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
15 | Manjeshwar | Strip BT and Pot holes filling at Km 4/000 to 6/000 of Ubbathodi - Cheppinadukka - Naikap Road | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
16 | Manjeshwar | Surface Renewal to Adkasthala-Odia- Road km 2/500 to 4/500 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
17 | Manjeshwar | SR to Hidayath Nagar NH Pachilampara Bagavathi Temple Raod 0/000 to 3/000 | 16 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
18 | Kasaragod | Construction of C C drain between km 22/200 and 22/700 of Cherkala - Jalsoor Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
19 | Kasaragod | Construction of slab culvert and providing covering slab at km19/050 of Cherkala - Jalsoor Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
20 | Kasaragod | Construction of slab culvert and CC drain at km3/510 of A P Circle - Gosada- Bolinja Road | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
21 | Kasaragod | Construction of C C drain between km 21/100 and 21/800 of Cherkala - Jalsoor Road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
22 | Kasaragod | Widening and construction of protection wall between km 16/000 and 16/200 Cherkala - Jalsoor Road | 18 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
23 | Kasaragod | surface rectification between km 16/000 and 39/000 of Cherkala - Jalsoor Road | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
24 | Kasaragod | Surface Renewal to Nellikatta-Karmanthody Road km 10/000 to 11/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
25 | Kasaragod | Providing BM & BC bet Km 3/000 to 4/500 at Madhur- Patla Kollamgana road | 50 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
26 | Kasaragod | Surface Renewal to Nekrampara-Arladuka-Kodimoole-Pundoor-Narampady-Yethadka Road km 10/000 to 11/600 | 21 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
27 | Kasaragod | Improvements to Karantakkadu Junction at KM 0/000 to 0/400 of Kasaragod -Madhur road | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
28 | Kasaragod | Surface Renewal to Nekrampara-Arladuka-Kodimoole-Pundoor-Narampady-Yethadka Road km 9/000 to 10/000 | 11 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
29 | Udma | Providing strip BT to Thekkil-Alatty road bet KM 30/400 to 34/555 (MSS) | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
30 | Udma | Surface renewal to Paduppu - Bandadukka Karivedakam road att Km0/000 to 1/800 and 2/210 to 3/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
31 | Udma | Surface rectification to Paduppu Bandamkai Karivedakam Road (km 2/210 to 3/000) | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work substituted
32 | Udma | Ammangod Kallukandam Chathappady road (km 5/000 to 0/000) | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
33 | Udma | Surface rectification to Chaligal-Meengoth-ambalathara road km 3/500 to 4/900 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
34 | Udma | Surface providing strip BT to Thekkil-Alatty road km 16/000 to 17/300 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
35 | Udma | OR 2017-2018 BC surface rectification works on bekal-panayal road between 3/500to 4/000. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
36 | Udma | OR 2017-2018 BC surface rectification works on bekal-panayal road between 4/000 to 5/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
37 | Udma | OR 2017-2018 BC surface rectification works on bekal-panayal road between 5/000 to 6/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
38 | Udma | Surface rectification to Eriya Kanhiradukka, road km 0/000 to 3/000 | 18 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
39 | Udma | Providing covering slab overdrain to Udma Mullacherry road between km 0/000 to 1/000 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
40 | Udma | Widening the carriage way and surface renewal to Bovikanam Bevinje road km 0/000 to 3/000 | 25 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
41 | Udma | Widening the carriage way and surface renewal to Bovikanam Bevinje road km 0/000 to 3/000 | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
42 | Udma | Providing strip BT to Koliyadukkam Perumbalakkadavu road km 0/000 to 5/000 | 5 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
43 | Udma | Providing strip BT to Thekkil-Alatty road bet KM 0/000 to 16/000 | 12 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
44 | Kanhangad | OR 2017-2018 Supplying and Laying Shelmac on various roads under road section kanhangad . | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
45 | Kanhangad | OR 2017-2018 Clearing side drain, jungle clearance, clearing choked culverts and wood cutting in various roads under roads section kanhangad . | 2 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
46 | Kanhangad | Providing strip B.T to Hosdurg Panathur road K.M 26/000 to 28/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2698/2017-18 Dtd:04/10/2017 Rs/-1489000 | [7 empty] | Work under Tendering Process
47 | Kanhangad | Providing strip B.T to Odayanchal Cherupuzha road K.M 5/000 to 6/500. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
48 | Kanhangad | Providing strip B.T to Anakkal Pookayam Malakkallu Road K.M 0/000to 1/200. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
49 | Kanhangad | Providing strip B.T to Odayanchal Cherupuzha Road K.M 0/000to 3/000. | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2693/2017-18 Dtd:04/10/2017 Rs/-1983700 | [7 empty] | Work under Tendering Process
50 | Kanhangad | Providing strip B.T to Chullikkara Kuttikkole Road K.M 6/500 to 7/500. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
51 | Kanhangad | Providing strip B.T to Hosdurg Panathur road K.M 33/500 to 34/500 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
52 | Kanhangad | Urgent surface rectification to Nileswar Edathode road KM.3/000 to 5/000. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
53 | Kanhangad | Urgent surface rectification to Nileswar Edathode road KM.12/000 to 13/000. | 6 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2445/2017-18 Dtd:28/09/2017 Rs/-6 L | [7 empty] | Work under Tendering Process
54 | Kanhangad | Urgent surface rectification to Bangalam Thekkan Bangalam Nileswar block office road KM.0/000 to 2/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
55 | Kanhangad | Urgent surface rectification to Choyyamkode Mukkada office road KM.6/000 to 8/500. | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
56 | Kanhangad | OR 2017-2018 Raising water logged portion and surface rectification between Km 1/000 to 2/000 Thullichery-Nileswar-Azhithala (via) Ajanoor kadappuram road. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
57 | Kanhangad | OR 2017-2018 Raising water logged portion and surface rectification at Nhanikadavu between Km 5/000 to 6/000 T.B Shavaparamba- Kottrachal road. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
58 | Kanhangad | OR 2017-2018 Surface rectification and raising water logged portion between km 7/000 to 8/400 of T.B shavaparamba-kottrachal road | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
59 | Kanhangad | OR 2017-2018 Surface rectification to T.B shavaparamba-kottrachal road between km 1/000 to 2/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
60 | Trikaripur | Supplying and laying shelmac on various roads under Roads Section, West Eleri. | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
61 | Trikaripur | Removal of slipped earth cleaning chalked culverts and removal of fallen trees and wood cutting for various roads under Roads section west eleri. | 2 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
62 | Trikaripur | Supplying and laying shelmac on various roads under Roads Section, Nileswar. | 3 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
63 | Trikaripur | Removal of slipped earth cleaning chalked culverts and removal of fallen trees and wood cutting for various roads under Roads section Nileswar. | 2 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
64 | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha road K.M 26/400 to 28/000 . | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
65 | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha road K.M 28/00 to 29/500 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2661/17-18 Dtd:02/10/17 Rs/-15L | [7 empty] | Work under Tendering Process
66 | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha road K.M 29/500 to 31/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2662/17-18 Dtd:02/10/17 Rs/-15L | [7 empty] | Work under Tendering Process
67 | Trikaripur | Providing strip B.T to Varakkad-Elerithattu Paramba Road K.M 0/000 to 2/600. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2694/17-18 Dtd:04/10/17 Rs/-1496000 | [7 empty] | Work under Tendering Process
68 | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha Road K.M 23/500to 25/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2653/17-18 Dtd:04/10/17 Rs/-15L | [7 empty] | Work under Tendering Process
69 | Trikaripur | Providing strip B.T to Odayanchal Cherupuzha Road K.M 22/000to 23/500 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2696/17-18 Dtd:04/10/17 Rs/-1497000 | [7 empty] | Work under Tendering Process
70 | Trikaripur | Providing strip B.T to Cheemeni-Palavayal-Odakkolli Road K.M 26/500 to 28/000. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 519/17-18 Dtd:24/09/17 Rs/-1488000 | [7 empty] | Work under Tendering Process
71 | Trikaripur | Providing strip B.T to Beemanadi-Mukkada Road K.M 6/000 to 8/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2692/17-18 Dtd:04/10/17 Rs/-1481000 | [7 empty] | Work under Tendering Process
72 | Trikaripur | Providing strip B.T to Cheemeni-Palavayal-Odakkolli Road K.M 25/000 to 26/500. | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | 2692/17-18 Dtd:04/10/17 Rs/-15L | [7 empty] | Work under Tendering Process
73 | Trikaripur | Providing covering slab and repairs existing drain of cheruvathur padna edachakai road K.M 3/000 to 5/000 | 20 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
74 | Trikaripur | Urgent surface rectification to Thrikkaripur Payyannur Byepass road KM.0/000 to 0/500. | 10 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
75 | Trikaripur | Urgent surface rectification to Cheemeni Kakkadavu road KM.7/900 to 8/000 and 9/000 to 11/000 | 15 | CE/R&B/TF/KSD/17-18 Dated: 31/08/2017 | [8 empty] | Work under Tendering Process
1 | Manjeshwar | OR - 2017-18 - Supplying and laying shelmac under Roads Section Manjeswar Rs. 5.00 Lakhs - H/A : 3054-03-337-99 | 5 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
2 | Manjeshwar | OR - 2017-18 - Construction of culvert and CC drain at Km 2/650 of Durgipalla Bejje Munnipady road - Rs. 10.00 Lakhs H/A : 3054-03-337-99 | 10 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
3 | Kasaragod | SR - 2017 -18 - Surface renewal to Mulleria - Nattakkal - Aripadavu road Km 0/000 to 1/000, Rs. 18.00 Lakhs H/A: 3054-03-337-97 | 18 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
4 | Kasaragod | SR - 2017 -18 - Surface renewal to Mulleria - Nattakkal - Aripadavu road Km 1/000 to 2/000, Rs. 18.00 Lakhs H/A: 3054-03-337-97 | 18 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
5 | Kasaragod | SR - 2017-18 - Surface renewal to Mullerial Nattakkal - Aripadavu road km 11/000 to 12/000 Rs. 12.00 Lakhs H/A; 3054-03-337-97 | 12 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
6 | Kasaragod | 1) RP - 2017-18 - Providing MSS between Km 6/000 to 10/310 at Madhur Patla - Kollangana road. Rs. 47.00 Lakhs H/A : 3054-03-337-98 | 47 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
7 | Kasaragod | 2) RP -2017-18 - Supplying and laying shelmac under Roads Section Kasaragod Rs. 3.00 Lakhs H/A: 3054-03-337-98 | 3 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
8 | Uduma | OR - 2017-18 Surface rectification to Paduppu - Bandankai - Karivedakam road Km 0/000 to 1/750 Rs. 15.00 Lakhs H/A: 3054-03-337-99 | 15 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS
9 | Uduma | OR - 2017-18 Surface rectification to Paduppu - Bandankai - Karivedakam road Km 1/800 to 3/000 Rs. 20.00 Lakhs H/A: 3054-03-337-99 | 20 | CE/R&B/KSD/Substitution/2017-18. Dated 03/10/2017 | [8 empty] | Under scrutiny for TS